## Work List
Exported on: 2026-09-27 02:23:31
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: GHANA KALAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RAISEN / BEGUMGANJ | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1730003013/AV/22012034647129 — शांतिधाम निर्माण कार्य ग्राम घानाकलां | Ongoing | 320812.44 | 0 | 2023-10-08
RAISEN / BEGUMGANJ | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1730003013/AV/22012034647131 — शांतिधाम निर्माण कार्य ग्राम जसरथी | Ongoing | 320812.44 | 0 | 2023-10-08
RAISEN / BEGUMGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1730003013/DP/22012034610531 — नाडेब निर्माण पंचायत भवन के पास ग्राम घानाकला | Ongoing | 39930.14 | 0 | 2023-10-08
RAISEN / BEGUMGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coast Line Plantation of Forestry Trees for Comm / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1730003013/DP/22012034610532 — नाडेब निर्माण हनुमान मंदिर के पास ग्राम घानाकला | Ongoing | 39930.14 | 0 | 2023-10-08
RAISEN / BEGUMGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coast Line Plantation of Forestry Trees for Comm / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1730003013/DP/22012034610535 — नाडेब निर्माण नवीन पंचायत भवन घानाकला | Ongoing | 39930.14 | 0 | 2023-10-08
RAISEN / BEGUMGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coast Line Plantation of Forestry Trees for Comm / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1730003013/DP/22012034610536 — नाडेब निर्माण बाबूलाल साहू के मकान के पास ग्राम जसरथी | Ongoing | 39930.14 | 0 | 2023-10-08
RAISEN / BEGUMGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1730003013/DP/22012034610538 — नाडेब निर्माण कुआ चोराहा के पास ग्राम जसरथी | Ongoing | 39711.47 | 0 | 2023-10-08
RAISEN / BEGUMGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1730003013/DP/22012034610540 — नाडेब निर्माण चैनसिंह राजपूत के मकान के पास ग्राम जसरथी | Ongoing | 39711.47 | 0 | 2023-10-08
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730003013/IF/22012035579170 — खेत तालाब निर्माण राम कुमार/ जमना प्रसाद | Approved | 0 | 0 | 2025-04-14
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730003013/IF/22012035579171 — खेत तालाब निर्माण वीरेन्द्र/ जमना प्रसाद | Approved | 0 | 0 | 2025-04-14
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730003013/IF/22012035607051 — एक बगिया मां के नाम ममता रानी जैन | Ongoing | 127822.67 | 0 | 2025-09-03
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/5999278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100075058 | Physically Completed | 27000 | 5505 | 2026-03-09 | 2026-09-06
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/5999279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100086583 | Ongoing | 27000 | 0 | 2026-03-09
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/5999504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100556975 | Ongoing | 27000 | 0 | 2026-03-09
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/5999640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100045639 | Ongoing | 27000 | 3654 | 2026-03-09
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/5999641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100045642 | Physically Completed | 23490 | 2088 | 2026-03-09 | 2026-07-26
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/5999645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100458984 | Ongoing | 27000 | 0 | 2026-03-09
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6002305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100556873 | Physically Completed | 27000 | 1500 | 2026-04-10 | 2026-09-20
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6002309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100560581 | Physically Completed | 27000 | 2088 | 2026-04-13 | 2026-09-20
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6002310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100560648 | Physically Completed | 23490 | 2088 | 2026-03-09 | 2026-07-26
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6002601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126841273 | Ongoing | 27000 | 0 | 2026-03-09
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6004141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100045662 | Ongoing | 27000 | 300 | 2026-04-10
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6004142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100459102 | Ongoing | 27000 | 2088 | 2026-03-09
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100041221 | Ongoing | 27000 | 0 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100045638 | Ongoing | 27000 | 3654 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100045644 | Ongoing | 27000 | 3654 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066591 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100045653 | Ongoing | 27000 | 7308 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100045908 | Ongoing | 27000 | 3654 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066600 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100058621 | Ongoing | 27000 | 0 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100058627 | Ongoing | 27000 | 0 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100058631 | Physically Completed | 23490 | 2088 | 2026-04-10 | 2026-07-19
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100059166 | Ongoing | 27000 | 1305 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100059197 | Physically Completed | 23490 | 5505 | 2026-04-10 | 2026-08-09
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100075019 | Ongoing | 27000 | 3654 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100075024 | Ongoing | 27000 | 4200 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100075044 | Ongoing | 27000 | 3654 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100075059 | Ongoing | 27000 | 0 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100075077 | Ongoing | 27000 | 0 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100075086 | Ongoing | 27000 | 0 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100075087 | Ongoing | 27000 | 5742 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100113790 | Ongoing | 27000 | 3654 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100113794 | Physically Completed | 23490 | 2088 | 2026-04-10 | 2026-07-26
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100113795 | Physically Completed | 23490 | 2088 | 2026-04-13 | 2026-07-26
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100458869 | Ongoing | 27000 | 5742 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100459002 | Ongoing | 27000 | 3654 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100459041 | Physically Completed | 23490 | 5742 | 2026-04-10 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100459043 | Physically Completed | 23490 | 5742 | 2026-04-10 | 2026-07-26
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100462488 | Physically Completed | 27000 | 5742 | 2026-04-10 | 2026-09-06
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066687 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100495459 | Ongoing | 27000 | 0 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100497578 | Physically Completed | 23490 | 2088 | 2026-04-13 | 2026-07-26
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100556584 | Physically Completed | 23490 | 5742 | 2026-04-10 | 2026-07-26
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100556588 | Physically Completed | 23490 | 5742 | 2026-04-10 | 2026-08-09
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100556605 | Ongoing | 27000 | 5742 | 2026-04-13
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100556627 | Ongoing | 27000 | 3654 | 2026-04-13
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100556823 | Ongoing | 27000 | 0 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100556981 | Physically Completed | 27000 | 5742 | 2026-04-10 | 2026-09-06
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100557001 | Ongoing | 27000 | 3654 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100557009 | Physically Completed | 23490 | 0 | 2026-04-13 | 2026-08-02
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100557079 | Ongoing | 27000 | 3654 | 2026-04-13
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100560639 | Ongoing | 27000 | 0 | 2026-04-24
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100560640 | Ongoing | 27000 | 5742 | 2026-04-13
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100560642 | Physically Completed | 23490 | 5742 | 2026-04-13 | 2026-08-09
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066771 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100560651 | Physically Completed | 23490 | 2088 | 2026-04-13 | 2026-07-26
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100560676 | Ongoing | 27000 | 5742 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100560679 | Physically Completed | 23490 | 5742 | 2026-04-10 | 2026-08-09
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100637379 | Ongoing | 27000 | 3654 | 2026-04-10
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100702335 | Physically Completed | 23490 | 2088 | 2026-04-10 | 2026-07-19
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6066873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100707253 | Ongoing | 27000 | 3654 | 2026-04-13
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6089060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126847617 | Physically Completed | 23490 | 2088 | 2026-04-10 | 2026-07-26
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6117574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126073884 | Ongoing | 27000 | 6264 | 2026-04-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6117655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100464482 | Physically Completed | 23490 | 2088 | 2026-04-13 | 2026-07-26
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6117803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100560578 | Physically Completed | 27000 | 2088 | 2026-04-13 | 2026-09-20
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6117804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100560663 | Physically Completed | 23490 | 5742 | 2026-04-13 | 2026-08-23
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6117805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100560684 | Physically Completed | 23490 | 2088 | 2026-04-13 | 2026-07-26
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6118079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100458831 | Ongoing | 27000 | 0 | 2026-04-13
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6118085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100059209 | Ongoing | 27000 | 3654 | 2026-04-13
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6118089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100557019 | Ongoing | 27000 | 5742 | 2026-04-13
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6118654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126818255 | Physically Completed | 23490 | 0 | 2026-04-13 | 2026-08-02
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6118659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126856806 | Ongoing | 27000 | 0 | 2026-04-13
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6118949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100458910 | Ongoing | 27000 | 3654 | 2026-04-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6119491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100556991 | Physically Completed | 23490 | 5742 | 2026-04-13 | 2026-08-09
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6119604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100075036 | Ongoing | 27000 | 3654 | 2026-04-13
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6119605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100075048 | Ongoing | 27000 | 3654 | 2026-04-13
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6119606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100075062 | Ongoing | 27000 | 3654 | 2026-04-13
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6119607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100075073 | Ongoing | 27000 | 0 | 2026-04-13
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6121932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100560506 | Ongoing | 27000 | 3654 | 2026-04-13
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730003013/IF/IAY/6122368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100527243 | Ongoing | 27000 | 3654 | 2026-04-16
RAISEN / BEGUMGANJ | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1730003013/WC/22012034605356 — samudayik talab nirman gram tekapar khurd | Ongoing | 532531.66 | 0 | 2022-03-28
RAISEN / BEGUMGANJ | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1730003013/WC/22012034637137 — तालाब जीर्णोद्धार जंगल जसराथी | Ongoing | 290697.99 | 0 | 2021-04-07
RAISEN / BEGUMGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1730003013/WC/22012035315162 — संकरनपोंड बैठान टेकापार खुर्द | Approved | 0 | 0 | 2025-04-14