## Work List
Exported on: 2026-10-18 11:12:21
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MARKHANDI
Status: Ongoing
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1730003035/IF/22012035313102 — कपिल धारा कूप निर्माण कार्य भाग बाई / गोविन्द प्रसाद ग्राम झिरपनी | Ongoing | 291103.15 | 0 | 2026-03-26
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1730003035/IF/22012035313105 — Kapil dhara koop raghuvar/ buthe markhandi | Ongoing | 326960.09 | 0 | 2026-03-26
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individual | Plantation | 1730003035/IF/22012035607185 — एक बगिया मां के नाम मायारानी झिरपानी | Ongoing | 125843.16 | 0 | 2025-09-03
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730003035/IF/22012035607349 — एक बगिया का नाम स्वाति झिरपानी | Ongoing | 127916.89 | 0 | 2025-09-12
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individual | Plantation | 1730003035/IF/22012035615535 — एक बगिया मां के नाम संतरानी मारखंडी | Ongoing | 127822.67 | 0 | 2025-09-20
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730003035/IF/22012035615777 — एक बगियां मां के नाम त्रिवेनी ग्राम झिरपानी | Ongoing | 125843.16 | 0 | 2025-09-12
RAISEN / BEGUMGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/3152177 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4375290 | Ongoing | 27000 | 0 | 2023-02-21
RAISEN / BEGUMGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/3817989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117593198 | Ongoing | 27000 | 0 | 2022-09-04
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/4854860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100724820 | Ongoing | 27000 | 12600 | 2025-10-08
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/4854861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100724979 | Ongoing | 27000 | 0 | 2025-10-08
RAISEN / BEGUMGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/4856058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131933585 | Ongoing | 27000 | 0 | 2025-02-11
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/5091895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131883026 | Ongoing | 27000 | 0 | 2025-10-08
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/5678198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131883048 | Ongoing | 27000 | 0 | 2025-10-08
RAISEN / BEGUMGANJ | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/569597 — Construction of IAY House -IAY REG. NO. MP4219684 | Ongoing | 27000 | 0 | 2017-03-08
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/5724634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122778270 | Ongoing | 27000 | 12600 | 2026-04-01
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/5787842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102937224 | Ongoing | 27000 | 0 | 2026-04-01
RAISEN / BEGUMGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/5787847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105748299 | Ongoing | 27000 | 0 | 2025-11-05
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/5788042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106024685 | Ongoing | 27000 | 0 | 2026-05-04
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/5999643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100104021 | Ongoing | 27000 | 16800 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6000378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102459289 | Ongoing | 27000 | 16800 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6002056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131933609 | Ongoing | 27000 | 16800 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6002647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131933179 | Ongoing | 27000 | 16800 | 2026-04-01
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6003352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102430962 | Ongoing | 27000 | 16800 | 2026-04-01
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6066640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100105243 | Ongoing | 27000 | 16800 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6066668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100472181 | Ongoing | 27000 | 25200 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6066670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100472195 | Ongoing | 27000 | 16500 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6066671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100472206 | Ongoing | 27000 | 12600 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6066672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100472208 | Ongoing | 27000 | 16800 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6066674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100472212 | Ongoing | 27000 | 16800 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6067367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102428657 | Ongoing | 27000 | 16800 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6072133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115048874 | Ongoing | 27000 | 16800 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6072134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115049186 | Ongoing | 27000 | 16800 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6086118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125348839 | Ongoing | 27000 | 16800 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6086121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125349976 | Ongoing | 27000 | 16800 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6086122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125350328 | Ongoing | 27000 | 16800 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6093984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131882642 | Ongoing | 27000 | 16800 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6093985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131882758 | Ongoing | 27000 | 14700 | 2026-04-18
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6093986 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131882842 | Ongoing | 27000 | 16800 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6093987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131883085 | Ongoing | 27000 | 16800 | 2026-04-18
RAISEN / BEGUMGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730003035/IF/IAY/6094025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131934661 | Ongoing | 27000 | 12600 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1730003035/WC/22012035214281 — बोल्डर चेक डैम अमृत सरोवर के पास ग्राम मारखंडी | Ongoing | 82145.49 | 56700 | 2026-08-16
RAISEN / BEGUMGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1730003035/WC/22012035214282 — बोल्डर चेक डैम बलराम के बगीचा के पास ग्राम मारखंडी | Ongoing | 89837.75 | 56700 | 2026-10-06
RAISEN / BEGUMGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1730003035/WC/22012035214283 — बोल्डर चेक डैम संकरण पौंड के पास ग्राम मरखंडी | Ongoing | 83645.49 | 56700 | 2026-10-06
RAISEN / BEGUMGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1730003035/WC/22012035327409 — संकरण पोंड निर्माण कोहा बाले नाले पर ग्राम मारखंडी | Ongoing | 1468381.54 | 0 | 2026-08-11
RAISEN / BEGUMGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1730003035/WC/22012035328223 — संकरण पोंड निर्माण करौंदा वाले नाले पर ग्राम मारखंडी | Ongoing | 1431709.96 | 0 | 2026-03-10
RAISEN / BEGUMGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1730003035/WC/VB/22012035331074 — बोल्डर चेक डेम निर्माण ब्रम्दानी नाले पर मरखंडी | Ongoing | 70698.95 | 54600 | 2026-08-14
RAISEN / BEGUMGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1730003035/WC/VB/22012035331077 — बोल्डर चेक डेम निर्माण झापर नाले पर मरखंडी | Ongoing | 70698.95 | 54600 | 2026-08-14
RAISEN / BEGUMGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1730003035/WC/VB/22012035331078 — बोल्डर चेक डेम निर्माण भटुआ नाले पर मरखंडी | Ongoing | 70698.95 | 54600 | 2026-08-14
RAISEN / BEGUMGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1730003035/WC/VB/22012035331079 — बोल्डर चेक डेम निर्माण अमृत सरोवर के पास मरखंडी | Ongoing | 70698.95 | 54000 | 2026-08-14
RAISEN / BEGUMGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1730003035/WC/VB/22012035331080 — बोल्डर चेक डेम निर्माण स्टाप डेम के पास मरखंडी | Ongoing | 70698.95 | 54600 | 2026-09-19
RAISEN / BEGUMGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1730003035/WC/VB/22012035331919 — गेबियन निर्माण आमो बाली झोर पर ग्राम मरखंडी | Ongoing | 157720.28 | 14699.02 | 2026-08-14
RAISEN / BEGUMGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1730003035/WC/VB/22012035331920 — गेबियन निर्माण हदुआ नाले पर ग्राम मरखंडी | Ongoing | 157720.28 | 14700 | 2026-08-14
RAISEN / BEGUMGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1730003035/WC/VB/22012035331922 — गेबियन निर्माण बरिया बाले नाले पर ग्राम मरखंडी | Ongoing | 157720.28 | 14700 | 2026-09-19
RAISEN / BEGUMGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1730003035/WC/VB/22012035331924 — गेबियन निर्माण कोहा बाले नाले पर ग्राम मरखंडी | Ongoing | 157720.28 | 14700 | 2026-08-14
RAISEN / BEGUMGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1730003035/WC/VB/22012035331926 — गेबियन निर्माण कोहा के नीचे बाले नाले पर ग्राम मरखंडी | Ongoing | 157720.28 | 14700 | 2026-09-19