## Work List
Exported on: 2026-09-04 14:25:16
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: DHANASARI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RAISEN / BADI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005065/RC/22012034844370 — सी सी सड़क निर्माण कार्य आधार सिंह के मकान से खेड़ापति मंदिर की ओर | Completed | 69000 | 48156.22 | 2025-08-15 | 2026-05-21
RAISEN / BADI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1730005104/DP/22012034593024 — बृक्षारोपण कार्य (मेरी माटी मेरा देश ) सामुदायिक परिसर धनाश्री | Closed | 55847.4 | 0 | 2023-04-14
RAISEN / BADI | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1730005104/IF/22012035124575 — भाई साहब के घर में नाडेप निर्माण् | Closed | 0 | 0 | 2023-04-01
RAISEN / BADI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035124576 — भाई साहब के घर में नाडेप निर्माण् | Completed | 25009.11 | 21688.7 | 2023-07-10 | 2024-12-06
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035349300 — खेत तालाब निर्माण कार्य विजय सिंह के खेत में ग्राम लाझी | Physically Completed | 450885.64 | 429749.07 | 2025-04-24 | 2026-04-27
RAISEN / BADI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730005104/IF/22012035349441 — JGSA 2025 Recharge Structure Ankit Rawat ke koop me | Physically Completed | 25899.46 | 23665 | 2025-04-24 | 2026-04-17
RAISEN / BADI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730005104/IF/22012035349513 — JGSA 2025 Recharge Structure Amit Rawat ke koop me | Physically Completed | 25899.46 | 24640 | 2025-04-24 | 2026-04-17
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035445686 — JGSA 2025 khet talab hargovind/fatthu singh gp dhanasari | Completed | 55865.38 | 54047.84 | 2025-05-03 | 2026-04-20
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035445754 — JGSA 2025 khet talab dhansingh / prahalaad singh gp dhanasari | Completed | 147621.16 | 136514.83 | 2025-05-03 | 2026-04-20
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035562478 — JGSA 2025 Khet Talab Nirman Karya Lakhan Mehra ke khet me | Approved | 0 | 0 | 2025-04-14
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035562480 — JGSA 2025 Khet Talab Nirman Karya Daulat Singh ke khet me | Approved | 0 | 0 | 2025-04-14
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035565277 — JGSA 2025 Khet Talab Nirman Karya Daulat Singh ke khet me | Completed | 55865.38 | 53786.67 | 2025-06-09 | 2026-04-20
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035565281 — JGSA 2025 Khet Talab Nirman Karya Lakhan Mehra ke khet me | Physically Completed | 55865.38 | 35777.67 | 2025-06-19 | 2026-05-27
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035567673 — JGSA 2025 Khet Talab Nirman Karya Shobha ram /Badri prasad | Approved | 0 | 0 | 2025-06-05
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035567677 — JGSA 2025 Khet Talab Nirman Brijmohan Kahar /Badri Kahar | Completed | 55865.38 | 53786.67 | 2025-06-19 | 2026-04-20
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035577847 — JGSA 2025 खेत तालाब निर्माण कार्य श्री मोहनसिंह आत्‍मज श्री देवकरण | Approved | 55865.38 | 0 | 2025-04-14
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035577849 — JGSA 2025 खेत तालाब निर्माण कार्य श्री रामप्रसाद आत्‍मज श्री देवकरण | Approved | 55865.38 | 0 | 2025-04-14
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035577853 — JGSA 2025 खेत तालाब निर्माण कार्य श्री हल्‍कोरी आत्‍मज श्री देवकरण | Approved | 55865.38 | 0 | 2025-04-14
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035577855 — JGSA 2025 खेत तालाब निर्माण कार्य श्री वीरेन्‍द्रसिंह राजपूत आत्‍मज श्री लालचंद | Approved | 55865.38 | 0 | 2025-04-14
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035577858 — JGSA 2025 खेत तालाब निर्माण कार्य श्री जितेन्‍द्र राजपूत आत्‍मज श्री चन्‍दनसिंह | New | 0 | 0 | 2025-04-14
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005104/IF/22012035577859 — JGSA 2025 खेत तालाब निर्माण कार्य श्री जितेन्‍द्र राजपूत आत्‍मज श्री चन्‍दनसिंह | Approved | 55865.38 | 0 | 2025-04-14
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730005104/IF/22012035607545 — एक बगिया मॉ के नाम संध्‍या बाई/देवेन्‍द्र ग्राम पंचायत धनाश्री | Ongoing | 124610.79 | 79146.71 | 2025-09-04
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730005104/IF/22012035607552 — एक बगिया मॉ के नाम सविता/राकेश ग्राम पंचायत धनाश्री | New | 0 | 0 | 2025-07-24
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730005104/IF/22012035607560 — एक बगिया मॉ के नाम कला बाई/धनसिंह ग्राम पंचायत धनाश्री | Ongoing | 127529.59 | 78885.71 | 2025-09-04
RAISEN / BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/4636873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131019793 | Completed | 23490 | 21141 | 2024-09-27 | 2025-07-10
RAISEN / BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/4637265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131428368 | Completed | 23490 | 21267 | 2024-10-09 | 2025-05-09
RAISEN / BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/4642449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132367176 | Completed | 23490 | 22878 | 2024-10-09 | 2026-06-04
RAISEN / BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/4642450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132367203 | Completed | 21870 | 21141 | 2024-09-27 | 2025-02-08
RAISEN / BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/4665869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150183837 | Completed | 21870 | 21870 | 2024-09-28 | 2024-12-06
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5822778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134258307 | Completed | 23490 | 21924 | 2025-12-26 | 2026-03-16
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5822779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134258406 | Completed | 23490 | 22968 | 2025-11-03 | 2025-12-14
RAISEN / BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5822780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134271290 | Physically Completed | 23490 | 0 | 2025-02-07 | 2026-03-15
RAISEN / BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5822781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134271502 | Physically Completed | 23490 | 0 | 2025-02-06 | 2026-03-15
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5824309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131217647 | Completed | 23490 | 23490 | 2025-11-03 | 2025-12-16
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5824310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131217679 | Completed | 23490 | 22185 | 2026-01-17 | 2026-03-01
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5826514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134258099 | Physically Completed | 23490 | 16182 | 2025-12-26 | 2026-03-15
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5826763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131217507 | Completed | 23490 | 23229 | 2025-11-03 | 2025-12-18
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5826764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131217579 | Completed | 23490 | 23229 | 2025-12-10 | 2026-06-04
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5827745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130930335 | Completed | 23490 | 21924 | 2025-11-03 | 2025-12-21
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5843580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131421406 | Completed | 23490 | 20358 | 2025-11-05 | 2025-12-16
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5843858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131428313 | Completed | 23490 | 23490 | 2025-11-03 | 2025-12-28
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5844189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134323052 | Physically Completed | 23490 | 14616 | 2025-11-13 | 2025-12-21
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5844190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134323152 | Completed | 23490 | 23490 | 2025-12-26 | 2026-06-08
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5844191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134323601 | Completed | 23490 | 20358 | 2025-12-25 | 2026-03-01
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5845191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131436887 | Completed | 23490 | 23229 | 2025-12-10 | 2026-01-21
RAISEN / BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5845296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132367168 | Physically Completed | 23490 | 0 | 2025-02-05 | 2025-12-14
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5845346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131026574 | Completed | 23490 | 21663 | 2025-11-03 | 2026-01-09
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5845349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131424808 | Completed | 23490 | 23229 | 2025-11-03 | 2025-12-18
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5845457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132367217 | Completed | 23490 | 23229 | 2025-11-03 | 2026-01-21
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5845505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131418808 | Completed | 23490 | 23229 | 2025-11-03 | 2025-12-14
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5845716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132463706 | Completed | 23490 | 21924 | 2025-11-03 | 2025-12-16
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5845846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131865171 | Completed | 23490 | 23490 | 2025-11-03 | 2026-01-27
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5975904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132465877 | Approved | 23490 | 0 | 2026-02-23
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5977346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131217278 | Approved | 23490 | 0 | 2026-02-23
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5977955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131418819 | Approved | 23490 | 0 | 2026-02-23
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5980292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131727185 | Approved | 23490 | 0 | 2026-02-23
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/5985667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131217617 | Approved | 23490 | 0 | 2026-02-23
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/6218424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131032019 | Approved | 23490 | 0 | 2026-03-20
RAISEN / BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005104/IF/IAY/6219220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131870545 | Approved | 23490 | 0 | 2026-03-20
RAISEN / BADI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005104/RC/22012034653692 — नाली निर्माण कार्य चंदन के घर से शासकीय हेण्‍डपंप तक मेहरागांव खुर्द | Closed | 30000 | 0 | 2023-04-01
RAISEN / BADI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005104/RC/22012034667225 — नाली निर्माण कार्य चंदन के घर से शासकीय हैण्‍डपंप तक | Closed | 0 | 0 | 2023-04-01
RAISEN / BADI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005104/RC/22012034667249 — सीसी सडक निर्माण चंदन के घर से सरकारी हेन्‍डपम्‍प तक | Closed | 28000 | 0 | 2025-01-06
RAISEN / BADI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005104/RC/22012034667262 — सीसी सडक निर्माण कार्य बद्री कहार के घर से प्रा शाला भवन तक | Closed | 23000 | 0 | 2023-04-01
RAISEN / BADI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005104/RC/22012034667311 — करन पटैल के घर से मरिया स्‍कूल गेट तक | Closed | 23000 | 0 | 2023-04-01
RAISEN / BADI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1730005104/RS/22012035127546 — नाली निर्माण कार्य संतोष पटेल के मकान से देवेन्द्र पटेल के घर की ओर धनाश्रि | Completed | 49500 | 49496.7 | 2024-07-25 | 2024-12-06
RAISEN / BADI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1730005104/RS/22012035134140 — कच्ची नाली निर्माण कार्य देवी सिंह के मकान से नदी की ओर | Approved | 0 | 0 | 2024-11-16