## Work List
Exported on: 2026-10-20 09:23:11
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: KATAK
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of SHG/Fed building for Groups / Construction of SHG/Federation Building for Groups | Construction of building/workshed for SHG | 1730007072/AV/22012034626057 — ग्राम राबरा में शान्तिधाम निर्माण कार्य | Completed | 216911.09 | 191043.1 | 2023-06-30 | 2025-06-15
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of SHG/Fed building for Groups / Construction of SHG/Federation Building for Groups | Construction of building/workshed for SHG | 1730007072/AV/22012034627200 — ग्राम कटक में शान्तिधाम निर्माण कार्य | Closed | 226381.46 | 0 | 2022-10-02
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1730007072/AV/22012034652782 — ग्राम कटक में पुलिया निर्माण कार्य गिरधारी आदिवासी के खेत के पास | Closed | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Infra for Liquid Biomanure for Comm / Construction of Infrastructure for Liquid Biomanure for Community | Bio-Fertilizer | 1730007072/AV/22012034661827 — सी सी सह नाली निर्माण कार्य रईस खान से मकान नाले की ओर | Approved | 11000 | 0 | 2024-04-01
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1730007072/DP/22012034595706 — Plantation meri mati mera desh ms school ke pass gram katak | Ongoing | 55847.4 | 32014 | 2023-12-08
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1730007072/FP/22012034638473 — ग्राम कटक में नेचुरल फ्लड चेनल पुनरोद्धार निर्माण कार्य नदी से सनगड़ा की ओर | Completed | 406691.2 | 382540 | 2024-03-16 | 2026-02-25
RAISEN / UDAIPURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730007072/IF/22012035045551 — kapildhara koop nirman kary rajkumar/rama | Closed | 0 | 0 | 2022-10-02
RAISEN / UDAIPURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730007072/IF/22012035045554 — kapildhara koop nirman kary viran/chotelal | Deleted | 0 | 0 | 2022-10-02
RAISEN / UDAIPURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730007072/IF/22012035045556 — kapildhara koop nirman kary keval/mihilal | Deleted | 0 | 0 | 2022-10-02
RAISEN / UDAIPURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730007072/IF/22012035046724 — Kapildhara koop nirman kary Ajaypal / Shobharam | Deleted | 0 | 0 | 2022-10-02
RAISEN / UDAIPURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730007072/IF/22012035046728 — Kapildhara koop nirman kary Brajesh / Ramsevak | Deleted | 0 | 0 | 2022-10-02
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050060 — Nadep nirman kary Lalsahab / Vishal Singh | Deleted | 0 | 0 | 2022-10-02
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050494 — Nadep nirman kary Ram singh / Vishal singh | Deleted | 0 | 0 | 2022-10-02
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050495 — Nadep nirman kary Shriram / Vishal singh | Deleted | 0 | 0 | 2022-10-02
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050497 — Nadep nirman kary Kaluram / chhattar | Deleted | 0 | 0 | 2022-10-02
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050498 — Nadep nirman kary Devi Singh/ Fundi Lal | Completed | 17529.23 | 17038.04 | 2023-02-27 | 2023-06-25
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050499 — Nadep nirman kary Chandan/ Lakhan | Deleted | 0 | 0 | 2022-10-02
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050501 — Nadep nirman kary Bholeshankar/ Lakhan | Deleted | 0 | 0 | 2022-10-02
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050508 — Nadep nirman kary Lakhan/ Khilan singh | Deleted | 0 | 0 | 2022-10-02
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050511 — Nadep nirman kary Rakesh / Shankar | Deleted | 0 | 0 | 2022-10-02
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050512 — Nadep nirman kary Maharaj / Mokam Singh | Completed | 17947.37 | 17038.04 | 2023-02-27 | 2023-07-21
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050515 — Nadep nirman kary Roop Singh/ Dammar Singh | Completed | 17520.24 | 17038.04 | 2023-02-27 | 2023-07-21
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050518 — Nadep nirman kary Gangaram / Dammar Singh | Completed | 17447.37 | 17038.04 | 2023-02-09 | 2023-06-25
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050519 — Nadep nirman kary Gomati Bai / Gopal | Completed | 17447.37 | 17038.04 | 2023-02-09 | 2023-06-25
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050520 — Nadep nirman kary Devi Singh / Koksingh | Completed | 17547.37 | 17038.04 | 2023-02-27 | 2023-07-21
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050525 — Nadep nirman kary Moorat/ Mangal singh | Completed | 17529.23 | 17038.04 | 2023-03-07 | 2024-02-25
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050529 — Nadep nirman kary Omkar Patel / Imrat Patel | Completed | 17547.37 | 17038.04 | 2023-02-09 | 2023-06-25
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050533 — Nadep nirman kary Munni Bai / Mulayam Singh | Completed | 17529.23 | 17038.04 | 2023-02-27 | 2023-06-25
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050539 — Nadep nirman kary Gangaprasad/ Bankelal | Completed | 17547.37 | 17038.04 | 2023-02-09 | 2023-06-25
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050542 — Nadep nirman kary Kodulal / Bankelal | Completed | 17547.37 | 17038.04 | 2023-02-27 | 2023-06-25
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035050544 — Nadep nirman kary Prahlad Singh/ Khilan Singh | Completed | 17529.23 | 17038.04 | 2023-02-27 | 2023-07-21
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035058641 — Nadep Nirman Kary Bholeshankar | Completed | 17547.37 | 17038.04 | 2023-02-27 | 2023-06-25
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035058643 — Nadep Nirman Kary Chandan | Completed | 17547.37 | 17038.04 | 2023-02-27 | 2023-06-25
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035058646 — Nadep Nirman Kary Shriram | Completed | 17547.37 | 16028.04 | 2023-02-09 | 2023-06-25
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035058647 — Nadep Nirman Kary Lakhan | Completed | 17547.37 | 17038.04 | 2023-02-27 | 2023-06-25
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035093207 — MED BANDHAN NIRMAN KARY ACHCHELAL | Completed | 59296.26 | 49402 | 2024-01-12 | 2024-07-21
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035093211 — MED BANDHAN NIRMAN KARY SHANKAR SINGH | Completed | 59296.26 | 49888 | 2024-03-10 | 2024-09-15
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035093215 — MED BANDHAN NIRMAN KARY MAKHANLAL | Completed | 59296.26 | 50805 | 2024-01-12 | 2024-07-21
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035093221 — MED BANDHAN NIRMAN KARY CHOTEVEER | Completed | 59296.26 | 49710 | 2024-03-10 | 2024-09-15
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035093224 — MED BANDHAN NIRMAN KARY SHIVRAJ | Completed | 59296.26 | 46794 | 2024-03-10 | 2024-11-24
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035093231 — MED BANDHAN NIRMAN KARY KAMLESH | Completed | 59296.26 | 50925 | 2024-03-10 | 2024-12-01
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035093236 — MED BANDHAN NIRMAN KARY KEVALSINGH | Completed | 53910.41 | 45247 | 2024-01-12 | 2024-08-01
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035093243 — MED BANDHAN NIRMAN KARY DEVISINGH | Completed | 59296.26 | 51030 | 2024-11-18 | 2025-05-14
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035093248 — MED BANDHAN NIRMAN KARY VEERAN | Completed | 59296.26 | 48816 | 2025-03-16 | 2025-06-15
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035093251 — MED BANDHAN NIRMAN KARY HEMRAJ | Completed | 59296.26 | 48251 | 2024-01-12 | 2024-09-15
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035093253 — MED BANDHAN NIRMAN KARY KALURAM | Completed | 59296.26 | 48209 | 2024-03-10 | 2024-09-15
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035093258 — MED BANDHAN NIRMAN KARY BRASANG | Completed | 59296.26 | 51030 | 2024-11-18 | 2025-05-14
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035093260 — MED BANDHAN NIRMAN KARY HAKAM SINGH | Completed | 59296.26 | 49424 | 2024-03-10 | 2024-11-24
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035093261 — MED BANDHAN NIRMAN KARY JASVANT SINGH | Completed | 59296.26 | 51103 | 2024-01-12 | 2024-09-15
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035093265 — MED BANDHAN NIRMAN KARY PREMBAI | Deleted | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035097073 — MED BANDHAN NIRMAN KARY SUGAN LAL | Completed | 59296.26 | 51030 | 2024-11-18 | 2025-05-14
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035097081 — Nadep nirman kary Lalsahab | Deleted | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035097084 — Nadep nirman kary Ram Singh | Deleted | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035097087 — Nadep nirman kary Kaluram | Deleted | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035097092 — Nadep nirman kary Rakesh | Deleted | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730007072/IF/22012035097096 — MED BANDHAN NIRMAN KARY BHAIYA JI | Completed | 59296.26 | 48938 | 2024-01-12 | 2024-09-15
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035127530 — Nadep Nirman Kary Lalsahab/Vishal | Completed | 18060.78 | 17123.04 | 2023-09-13 | 2024-02-25
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035127532 — Nadep Nirman Kary Kaluram / Chhattar | Completed | 18060.78 | 17123.04 | 2023-09-13 | 2024-02-25
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035127534 — Nadep Nirman Kary Rakesh / Shankar | Completed | 18060.78 | 17123.04 | 2023-09-13 | 2024-02-25
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035127536 — Nadep Nirman Kary Ram Singh / Vishal | Completed | 18060.78 | 17123.04 | 2023-09-13 | 2024-02-25
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035169964 — Nadep Nirman Kary Devi Singh/Maharaj Singh | Closed | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035169970 — Nadep Nirman Kary Vimlesh / Jayram | Closed | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035169973 — Nadep Nirman Kary Ramswaroop / Jayram | Closed | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035169981 — Nadep Nirman Kary Madhav / Rajaram | Closed | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035169996 — Nadep Nirman Kary Shankar / Todal | Closed | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035170002 — Nadep Nirman Kary Narayan / Shankar | Closed | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035170010 — Nadep Nirman Kary Mansingh / Ramlal | Closed | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035170022 — Nadep Nirman Kary Kaluram/Todal Singh | Closed | 17560.78 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730007072/IF/22012035170030 — Nadep Nirman Kary Gulab singh/ Todal Singh | Closed | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730007072/IF/22012035221145 — KAPIL DHARA KOOP NIRMAN KARY FHOOL SINGH / RAMA GOUD | Closed | 282417.57 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730007072/IF/22012035221149 — KAPIL DHARA KOOP NIRMAN KARY AJAYPAL / SHOBHARAM GOUD | Closed | 282417.57 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730007072/IF/22012035221155 — KAPIL DHARA KOOP NIRMAN KARY VIRAN / CHOTELAL ADIWASI | Physically Completed | 286486.14 | 205179.08 | 2024-03-16 | 2026-06-22
RAISEN / UDAIPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730007072/IF/22012035221162 — KAPIL DHARA KOOP NIRMAN KARY KEVAL SINGH / MIHEELAL GOUD | Completed | 282417.57 | 237680 | 2024-06-25 | 2025-05-04
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1730007072/IF/22012035230904 — MED BANDHAN NIRMAN KARY JAIPRAKASH / GORELAL | Approved | 54684.75 | 0 | 2024-06-08
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1730007072/IF/22012035230908 — MED BANDHAN NIRMAN KARY LALSAHAB / VISHAL SINGH | Approved | 54634.75 | 0 | 2024-06-08
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1730007072/IF/22012035230910 — MED BANDHAN NIRMAN KARY RATAN SINGH / LALVEER | Approved | 54684.75 | 0 | 2024-06-08
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1730007072/IF/22012035230914 — MED BANDHAN NIRMAN KARY DEVI SINGH / KOKSINGH | Approved | 54684.75 | 0 | 2024-06-08
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1730007072/IF/22012035230915 — MED BANDHAN NIRMAN KARY SAHAB SINGH/ KHILAN SINGH | Approved | 54684.75 | 0 | 2024-06-08
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1730007072/IF/22012035230920 — MED BANDHAN NIRMAN KARY RATIRAM / MANGALSINGH | Approved | 54684.75 | 0 | 2024-06-08
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1730007072/IF/22012035230923 — MED BANDHAN NIRMAN KARY KHET SINGH / CHOTELAL | Approved | 54684.75 | 0 | 2024-06-08
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1730007072/IF/22012035230926 — MED BANDHAN NIRMAN KARY HAKAM SINGH / NANHE | New | 0 | 0 | 2024-06-08
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1730007072/IF/22012035230929 — MED BANDHAN NIRMAN KARY JAWAHAR SINGH/ HARISINGH | Approved | 54684.75 | 0 | 2024-06-08
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1730007072/IF/22012035230931 — MED BANDHAN NIRMAN KARY RAMSWAROOP / CHOTELAL | Approved | 54684.75 | 0 | 2024-06-08
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1730007072/IF/22012035239354 — KAPILDHARA KOOP NIRMAN BRAJESH / RAMSEVAK ADIWASI | Physically Completed | 199752.04 | 110382 | 2024-07-20 | 2026-06-11
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1730007072/IF/22012035247822 — Kapil dhara koop nirman kary Rajkumar/ Rama Goud | Approved | 0 | 0 | 2024-04-14
RAISEN / UDAIPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1730007072/IF/22012035248872 — Kapil dhara koop nirman kary Rajkumar/ Rama Goud | Completed | 199802.04 | 184736 | 2024-07-20 | 2025-06-29
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730007072/IF/22012035387357 — Khet talab nirman kary Jayprakash / Gorelal | Physically Completed | 450885.64 | 369099 | 2025-04-30 | 2026-04-23
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730007072/IF/22012035387572 — Khet talab nirman kary Ramsvarup Gound / Chotelal Gound | Physically Completed | 450885.64 | 335169 | 2025-04-30 | 2026-05-23
RAISEN / UDAIPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730007072/IF/22012035387936 — JGSA 2025 Recharge structure Kapildhara Koop Babu Adiwasi 1730007028IF22012034516547 | Physically Completed | 25899.46 | 22702.18 | 2025-05-04 | 2026-04-20
RAISEN / UDAIPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1730007072/IF/22012035387977 — JGSA 2025 Recharge structure Kapildhara Koop Lakhan Adiwasi 1730007028IF22012034304685 | Completed | 25899.46 | 24820.18 | 2025-05-04 | 2026-03-28
RAISEN / UDAIPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1730007072/IF/22012035388014 — JGSA 2025 Recharge structure Kapildhara Koop Prahlad Singh Adiwasi 1730007028IF22012034762384 | Completed | 25899.46 | 24610.18 | 2025-05-04 | 2026-03-28
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730007072/IF/22012035436746 — Khet talab nirman kary Hakam singh goud / Nanhe singh goud | Physically Completed | 147621.16 | 121545 | 2025-04-30 | 2026-04-17
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730007072/IF/22012035436757 — Khet talab nirman kary Devi singh goud / Maharaj singh goud | Physically Completed | 147621.16 | 123633 | 2025-04-30 | 2026-04-17
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730007072/IF/22012035436769 — Khet talab nirman kary Jaypram goud / Maharaj goud | Physically Completed | 147621.16 | 121806 | 2025-04-30 | 2026-04-17
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730007072/IF/22012035436778 — Khet talab nirman kary Babu lal uike / Fagulal Uike | Approved | 147621.16 | 0 | 2025-04-14
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730007072/IF/22012035436788 — Khet talab nirman kary Vijay singh uike / Babulal uike | Physically Completed | 147621.16 | 123111 | 2025-04-30 | 2026-04-17
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730007072/IF/22012035436800 — Khet talab nirman kary Makhanlal asiwasi / Shriram Adiwasi | Approved | 147621.16 | 0 | 2025-04-14
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730007072/IF/22012035577882 — JGSA khet Talab Nirman Brajesh | Approved | 55865.38 | 0 | 2025-04-08
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730007072/IF/22012035577886 — JGSA khet Talab Nirman Keval | Approved | 0 | 0 | 2025-04-08
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730007072/IF/22012035577900 — JGSA khet Talab Nirman Lakhanlal | Approved | 0 | 0 | 2025-04-08
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730007072/IF/22012035577904 — JGSA khet Talab Nirman Sukhram | Approved | 55865.38 | 0 | 2025-04-08
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730007072/IF/22012035577908 — JGSA khet Talab Nirman Shivraj | Approved | 55865.38 | 0 | 2025-04-08
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730007072/IF/22012035577910 — JGSA khet Talab Nirman Rambabu Gound | Closed | 55865.38 | 261 | 2025-06-30
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730007072/IF/22012035577914 — JGSA khet Talab Nirman Ajaypal | Approved | 55865.38 | 0 | 2025-04-08
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730007072/IF/22012035577917 — JGSA khet Talab Nirman Sahabi | Approved | 55865.38 | 0 | 2025-04-08
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730007072/IF/22012035577921 — JGSA khet Talab Nirman Kamlesh Adiwasi | Approved | 55865.38 | 0 | 2025-04-08
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730007072/IF/22012035577925 — JGSA khet Talab Nirman Achchelal | Approved | 55865.38 | 0 | 2025-04-08
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730007072/IF/22012035577928 — JGSA khet Talab Nirman Kailash | Approved | 55865.38 | 0 | 2025-04-08
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730007072/IF/22012035577935 — JGSA khet Talab Nirman Brasang Gound | Approved | 55865.38 | 0 | 2025-04-08
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730007072/IF/22012035577937 — JGSA khet Talab Nirman Kaluram | Approved | 55865.38 | 0 | 2025-04-08
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730007072/IF/22012035577942 — JGSA khet Talab Nirman Juna Bai | Closed | 55865.38 | 261 | 2025-06-30
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730007072/IF/22012035577946 — JGSA khet Talab Nirman Bhagchand | Approved | 55865.38 | 0 | 2025-04-08
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/4549362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106570615 | Physically Completed | 23490 | 23229 | 2025-08-27 | 2026-02-28
RAISEN / UDAIPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/4549364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571068 | Ongoing | 27000 | 20736 | 2024-09-29
RAISEN / UDAIPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/4549365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571156 | Completed | 21870 | 21627 | 2024-09-29 | 2025-03-06
RAISEN / UDAIPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/4549366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571347 | Completed | 23490 | 22194 | 2024-11-29 | 2025-05-24
RAISEN / UDAIPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/4602449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124389383 | Physically Completed | 23490 | 22383 | 2024-09-29 | 2026-06-24
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/4602648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123986947 | Physically Completed | 23490 | 22968 | 2025-08-27 | 2026-02-15
RAISEN / UDAIPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/4602649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123987067 | Completed | 21870 | 21627 | 2024-09-29 | 2025-03-06
RAISEN / UDAIPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/4602651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123987397 | Completed | 21870 | 21627 | 2024-09-29 | 2025-03-06
RAISEN / UDAIPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/4602655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123989179 | Completed | 21870 | 21384 | 2024-09-29 | 2025-03-06
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/4603762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124404521 | Physically Completed | 23490 | 23490 | 2025-08-27 | 2026-02-15
RAISEN / UDAIPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/4603882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124436390 | Completed | 23490 | 22014 | 2024-09-29 | 2026-01-23
RAISEN / UDAIPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/4603886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124436695 | Completed | 21870 | 21384 | 2024-09-29 | 2025-03-06
RAISEN / UDAIPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/4614763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125770406 | Physically Completed | 27000 | 22392 | 2024-10-18 | 2026-09-25
RAISEN / UDAIPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/4616544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126099019 | Completed | 27000 | 21663 | 2024-09-29 | 2026-09-25
RAISEN / UDAIPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/4713499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126000180 | Physically Completed | 23490 | 22626 | 2024-10-18 | 2026-06-24
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/4825872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124396586 | Completed | 23490 | 23490 | 2025-08-27 | 2025-10-20
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5821360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125887083 | Ongoing | 27000 | 23163 | 2025-10-26
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5821434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125565897 | Completed | 23490 | 22707 | 2025-10-12 | 2026-03-25
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5822502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125897693 | Ongoing | 27000 | 23163 | 2025-10-26
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5823010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126219105 | Completed | 27000 | 21924 | 2026-02-26 | 2026-09-25
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5823445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124399762 | Completed | 23490 | 23490 | 2025-10-18 | 2026-04-29
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5823766 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125945250 | Physically Completed | 23490 | 23229 | 2026-02-26 | 2026-04-05
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5824384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123985964 | Physically Completed | 23490 | 23490 | 2025-10-18 | 2026-06-24
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5824385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123987636 | Ongoing | 27000 | 7308 | 2026-02-26
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5825185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126097024 | Physically Completed | 27000 | 22524 | 2026-02-26 | 2026-09-25
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5825483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123987939 | Completed | 23490 | 23229 | 2025-10-26 | 2026-01-23
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5825484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123988232 | Physically Completed | 23490 | 21924 | 2025-10-18 | 2026-02-05
RAISEN / UDAIPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5825576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106570525 | Ongoing | 27000 | 1800 | 2025-02-14
RAISEN / UDAIPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5825577 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106570544 | Approved | 27000 | 0 | 2025-02-09
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5825578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571020 | Ongoing | 27000 | 23016 | 2025-10-26
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5825579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571103 | Ongoing | 27000 | 5481 | 2025-10-26
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5825580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571205 | Ongoing | 27000 | 12054 | 2025-10-26
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5825581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571263 | Completed | 23490 | 23229 | 2025-10-12 | 2026-01-23
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5825582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571274 | Ongoing | 27000 | 18516 | 2026-02-27
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5825607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124388774 | Physically Completed | 23490 | 23490 | 2025-10-26 | 2026-06-24
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5825608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124388971 | Physically Completed | 23490 | 23229 | 2025-10-18 | 2026-01-23
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5825817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571310 | Completed | 23490 | 23490 | 2025-10-12 | 2026-01-23
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5825818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571323 | Physically Completed | 27000 | 24555 | 2025-10-12 | 2026-10-04
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5825819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571354 | Completed | 23490 | 23229 | 2025-10-12 | 2026-01-23
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5825820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571422 | Physically Completed | 23490 | 23229 | 2025-10-12 | 2026-06-24
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5825821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571464 | Completed | 23490 | 22446 | 2025-10-12 | 2026-04-29
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5825822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571472 | Completed | 23490 | 23490 | 2025-10-12 | 2026-01-23
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5825823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571485 | Physically Completed | 23490 | 23229 | 2025-10-26 | 2026-02-28
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5826179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123988782 | Physically Completed | 23490 | 23229 | 2025-10-12 | 2026-02-15
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5826180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123988999 | Physically Completed | 23490 | 23490 | 2025-10-18 | 2026-03-15
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5826182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123990654 | Physically Completed | 23490 | 23463 | 2025-10-18 | 2026-08-09
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5826185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123991089 | Physically Completed | 23490 | 18009 | 2025-10-18 | 2026-08-09
RAISEN / UDAIPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5826368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125901174 | Physically Completed | 23490 | 0 | 2025-02-05 | 2026-06-14
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5826599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106570676 | Physically Completed | 23490 | 23229 | 2025-10-12 | 2026-06-24
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5826600 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106570844 | Ongoing | 27000 | 23055 | 2025-10-12
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5826601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106570914 | Physically Completed | 23490 | 11223 | 2025-10-26 | 2026-02-28
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5826602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106570947 | Physically Completed | 23490 | 23229 | 2025-10-26 | 2026-02-28
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5826603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106570998 | Ongoing | 27000 | 3654 | 2025-10-26
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5826844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123845601 | Physically Completed | 23490 | 23490 | 2025-10-18 | 2026-03-15
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5827655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125566737 | Physically Completed | 23490 | 23229 | 2025-10-12 | 2026-02-15
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5828563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124221197 | Physically Completed | 23490 | 20109 | 2025-10-12 | 2026-08-02
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5844458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105833437 | Ongoing | 27000 | 16416 | 2026-02-26
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5844920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106570639 | Ongoing | 27000 | 8820 | 2026-02-26
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5845238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571434 | Ongoing | 27000 | 9108 | 2026-02-26
RAISEN / UDAIPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5845475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571128 | Ongoing | 27000 | 8400 | 2025-02-09
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730007072/IF/IAY/5845476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106571244 | Physically Completed | 23490 | 5220 | 2026-02-26 | 2026-04-05
RAISEN / UDAIPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730007072/IF/IAY/5881833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123986251 | Ongoing | 27000 | 0 | 2026-02-26
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730007072/RC/22012034629113 — सी सी सड़क निर्माण कार्य चरन लाल साहू के मकान से नाले की ओर | Deleted | 0 | 0 | 2023-01-24
RAISEN / UDAIPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730007072/RC/22012034629115 — सी सी सड़क निर्माण कार्य चरन लाल साहू के मकान से नाले की ओर | Closed | 37000 | 0 | 2023-01-24
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730007072/RC/22012034643812 — सीसी रोड सह नाली निर्माण कार्य चरण साहू के मकान से नाले की ओर | Completed | 37000 | 36080 | 2023-07-16 | 2024-03-28
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730007072/RC/22012034665062 — C.C. ROAD SAH NALI NIRMAN KARYA CHATTAR SINGH MEHRA KE MAKAN SE SANTOSH RAJAK KE MAKAN KI OR | Completed | 68000 | 64636 | 2023-12-27 | 2025-06-15
RAISEN / UDAIPURA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1730007072/RC/22012034821047 — cc road sah nali nirman kary prahlad singh ke makan se pm sadak ki or | Approved | 48000 | 0 | 2024-06-29
RAISEN / UDAIPURA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730007072/RC/22012034829976 — सी सी रोड सह नाली निर्माण कार्य प्रह्लाद सिंह के मकान से प्रधानमंत्री सड़क की ओर | Deleted | 0 | 0 | 2024-04-01
RAISEN / UDAIPURA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730007072/RC/22012034829980 — सी सी रोड सह नाली निर्माण कार्य प्रह्लाद सिंह के मकान से प्रधानमंत्री सड़क की ओर | Physically Completed | 48000 | 47502 | 2025-12-10 | 2026-06-19
RAISEN / UDAIPURA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1730007072/RC/22012034843426 — Gravel Khet Sadak Nirman Karan Singh ke Makan se Jairam Adiwasi ke khet ki or GP Katak | Approved | 0 | 0 | 2025-04-14
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1730007072/RS/22012034689825 — स्वच्छता परिसर निर्माण कार्य ग्राम रबरा | Completed | 44000 | 43666 | 2023-09-16 | 2024-03-21
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1730007072/RS/22012034704560 — Samudayik Nedep Nirman Kary Bageecha Mohalla Katak | Closed | 38490.7 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1730007072/RS/22012034704561 — Samudayik Nadep Nirman Kary Harijan Mohalla Katak | Closed | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1730007072/RS/22012034704562 — Samudayik Nadep Nirman Kary Indresh Ke Makan Ke Pass Katak | Closed | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1730007072/RS/22012034704565 — Samudayik Nadep Nirman Kary Ajaypal Ke Makan Ke Pass Katak | Closed | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1730007072/RS/22012034704567 — Samudayik Nadep Nirman Kary Devi singh Ke Makan Ke Pass Katak | Closed | 0 | 0 | 2023-04-01
RAISEN / UDAIPURA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1730007072/RS/22012035137064 — सीसी नाली निर्माण कार्य जालम हरिजन के मकान से शिवराज के मकान की ओर | Approved | 20000 | 0 | 2024-04-15
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1730007072/WH/22012034937883 — Nala path upchar nirman kary gram katak | Deleted | 0 | 0 | 2023-04-24
RAISEN / UDAIPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1730007072/WH/22012034938919 — ग्राम कटक में नेचुरल फ्लड चेनल पुनरोद्धार निर्माण कार्य नदी से सनगड़ा की ओर | Deleted | 0 | 0 | 2023-04-01