## Work List
Exported on: 2026-09-08 16:46:58
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MOODA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BETUL / SHAHPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1731007019/DP/22012034590774 — बसुधा वंदन अम्रत वाटिका‍‌ ग्राम पंचायत मुढा | Ongoing | 55847.4 | 0 | 2023-09-28
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1731007019/FR/22012034321805 — Talab Nirman Karya Babulal Ke Khet Ke Pass Mooda | New | 0 | 0 | 2024-08-16
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1731007019/FR/22012034323950 — FISHRIES TALAB HABLU KE KHET KE PASS KOTHA | Approved | 1465059.43 | 0 | 2024-11-15
BETUL / SHAHPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1731007019/IF/22012034314961 — hiteshi kup phulwati/ramvilash | Ongoing | 210000 | 0 | 2017-04-26
BETUL / SHAHPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1731007019/IF/22012034332772 — Choti Bai Beva / Charad (Hitesi Kapildhara kup) | Ongoing | 200000 | 0 | 2017-04-12
BETUL / SHAHPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1731007019/IF/22012034332787 — Jayram / Bisram ( Hitesi Kapildhara Kup) | Ongoing | 210000 | 0 | 2017-04-19
BETUL / SHAHPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1731007019/IF/22012034332790 — Mitthu / Nanesingh ( Hitesi Kapildhara Kup ) | Ongoing | 210000 | 0 | 2017-04-19
BETUL / SHAHPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1731007019/IF/22012034396002 — Hiteshi Kapildhara Kup Vimal /Madhu | Ongoing | 200000 | 0 | 2018-10-11
BETUL / SHAHPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1731007019/IF/22012034396003 — Hiteshi kapildhara kup Gulab/Sabbu | Ongoing | 200000 | 0 | 2018-10-04
BETUL / SHAHPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1731007019/IF/22012034396007 — Hiteshi Kapildhara KupBhikari/Punna | Ongoing | 200000 | 0 | 2019-01-10
BETUL / SHAHPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1731007019/IF/22012034397929 — Hitesi Kapildhara Kup Rattulal / Suku | Ongoing | 200000 | 0 | 2018-04-19
BETUL / SHAHPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1731007019/IF/22012034407166 — Khet Talab Kanehya / Chhannu | Ongoing | 42900 | 0 | 2018-10-25
BETUL / SHAHPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Piggery Shelter for Individuals / Construction of Piggery Shelter for Individuals | Piggery Shelter | 1731007019/IF/22012034589659 — Pashu Set Nirman Kanti / Mukesh | Ongoing | 101273.16 | 0 | 2020-11-26
BETUL / SHAHPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1731007019/IF/22012034696753 — Pashu Shed Nirman Mamta / Ramnarayan | Ongoing | 63954.59 | 0 | 2021-04-29
BETUL / SHAHPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1731007019/IF/22012034825389 — Nadep Nirman Dukadi / Doma | Ongoing | 12630.91 | 0 | 2021-10-08
BETUL / SHAHPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1731007019/IF/22012034825404 — Nadep Nirman Manohar / Natthu | Ongoing | 16852.01 | 0 | 2021-10-08
BETUL / SHAHPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1731007019/IF/22012034825458 — Pashu Shed Nirman Kamal / Ramsingh | Ongoing | 102645.51 | 0 | 2021-10-08
BETUL / SHAHPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1731007019/IF/22012035107841 — Khet Talab Nirman Rampal/Baliram gram mooda | Ongoing | 477300.32 | 0 | 2023-10-05
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1731007019/IF/22012035261425 — PASHU SHED NIRMAN KARYA HARESINGH /SUKALSINGH | Approved | 0 | 0 | 2024-08-16
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1731007019/IF/22012035261435 — BAKRI SHED NIRMAN KARYA SHIV / RAMSINGH MOODA | Approved | 0 | 0 | 2024-08-17
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1731007019/IF/22012035268234 — KHET TALAB BIRAJ/NANHU TETARMAL | New | 0 | 0 | 2024-08-16
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1731007019/IF/22012035268235 — KHET TALAB BIRAJ/NANHU TETARMAL | Ongoing | 420123.57 | 0 | 2024-11-18
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1731007019/IF/22012035268239 — KHET TALAB SHANKER/NANHU TETARMAL | Ongoing | 419938.72 | 0 | 2024-11-18
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1731007019/IF/22012035279722 — KHET TALAB MADHU KE KHET KE PASS KOT | Ongoing | 420123.57 | 0 | 2025-01-02
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1731007019/IF/22012035321202 — hiteshi kapildhara koop nirman kesav/ Gangaran mooda | New | 0 | 0 | 2025-04-01
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1731007019/IF/22012035321744 — Hiteshi kapil dhara koop kanhaiya/chhanu mooda | Approved | 0 | 0 | 2025-04-01
BETUL / SHAHPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1731007019/IF/22012035363924 — JGSA 2025 Recharge Structure Kapildhara Kup Kuvarlal / Bisan G P 1731007019 | New | 0 | 0 | 2025-04-15
BETUL / SHAHPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1731007019/IF/22012035363986 — JGSA 2025 Recharge Structure Kapildhara Kup Santram / Jagan G P 1731007019 | New | 0 | 0 | 2025-04-15
BETUL / SHAHPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1731007019/IF/22012035364260 — JGSA 2025 Recharge Structure Kapildhara Kup Ramlal / Kalu G P 1731007019 | New | 0 | 0 | 2025-04-15
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1731007019/IF/22012035441531 — Khet Talab Maniram/Babulall dodramau | New | 0 | 0 | 2025-04-15
BETUL / SHAHPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1731007019/IF/9993703180 — Hiteshi KAPIL DHARA KUP KALLU / BUDDHU | Ongoing | 243000 | 0 | 2016-01-13
BETUL / SHAHPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/104780 — Construction of IAY House -IAY REG. NO. MP-31-007-019-003/3092 | Approved | 27000 | 0 | 2015-09-15
BETUL / SHAHPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/3957556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151543618 | Ongoing | 27000 | 0 | 2023-09-05
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/4555271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114115387 | Ongoing | 27000 | 0 | 2025-01-02
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/4613167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125702775 | Ongoing | 27000 | 0 | 2025-01-16
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/4620108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126168321 | Ongoing | 27000 | 0 | 2026-02-06
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/4641185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132065411 | Ongoing | 27000 | 0 | 2025-02-06
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/4641189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132065769 | Ongoing | 27000 | 0 | 2026-02-20
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/4831139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132067597 | Ongoing | 27000 | 0 | 2026-02-20
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/4887356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114117353 | Ongoing | 27000 | 0 | 2026-03-19
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/4887357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114118880 | Physically Completed | 23490 | 0 | 2025-12-10 | 2026-07-26
BETUL / SHAHPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5164126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129871076 | Ongoing | 27000 | 0 | 2026-07-14
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5170154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114118701 | Physically Completed | 23490 | 0 | 2025-12-10 | 2026-08-23
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5171630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114117139 | Approved | 27000 | 0 | 2025-02-17
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5179993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125021684 | Ongoing | 27000 | 0 | 2025-12-12
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5229899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126625641 | Ongoing | 27000 | 0 | 2025-04-11
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5246354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100958990 | Approved | 27000 | 0 | 2025-02-17
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5248575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124528909 | Physically Completed | 23490 | 0 | 2026-02-20 | 2026-08-23
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5254551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132065594 | Ongoing | 27000 | 0 | 2025-12-12
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5261888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132065993 | Ongoing | 27000 | 0 | 2025-12-12
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5271289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124308596 | Ongoing | 27000 | 0 | 2025-12-12
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5278607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125018088 | Ongoing | 27000 | 0 | 2026-02-20
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5279431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125028719 | Ongoing | 27000 | 0 | 2026-02-06
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5290370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125013423 | Ongoing | 27000 | 0 | 2026-02-20
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5291123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129872094 | Approved | 27000 | 0 | 2025-03-01
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5293973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125023881 | Physically Completed | 23490 | 0 | 2025-12-12 | 2026-08-23
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5295592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125005547 | Ongoing | 27000 | 0 | 2025-12-12
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5297526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129871818 | Ongoing | 27000 | 0 | 2026-03-19
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5298403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129871452 | Approved | 27000 | 0 | 2025-02-17
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5300255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125016857 | Ongoing | 27000 | 0 | 2026-02-06
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5303053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132066085 | Ongoing | 27000 | 0 | 2026-02-20
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5307195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114117286 | Physically Completed | 23490 | 0 | 2026-02-06 | 2026-08-23
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5311557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125024854 | Ongoing | 27000 | 0 | 2025-12-12
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5315573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106647160 | Ongoing | 27000 | 0 | 2025-04-11
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5318068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114117922 | Ongoing | 27000 | 0 | 2025-12-10
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5319080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106527486 | Ongoing | 27000 | 0 | 2025-04-11
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5319601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125016265 | Ongoing | 27000 | 0 | 2025-12-12
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5326151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114115736 | Ongoing | 27000 | 0 | 2026-01-12
BETUL / SHAHPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5327940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125010913 | Approved | 27000 | 0 | 2025-02-22
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5329736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125009536 | Physically Completed | 23490 | 0 | 2025-12-12 | 2026-08-23
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5329786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129872189 | Ongoing | 27000 | 0 | 2025-12-12
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5331403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125008490 | Physically Completed | 23490 | 0 | 2026-01-12 | 2026-08-23
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5332491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150905104 | Physically Completed | 23490 | 0 | 2025-12-10 | 2026-08-23
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5341817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129871952 | Physically Completed | 27000 | 0 | 2025-12-12 | 2026-08-30
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5341942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125017414 | Ongoing | 27000 | 0 | 2025-12-12
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5342678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126177092 | Ongoing | 27000 | 0 | 2025-12-12
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5407400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114116140 | Ongoing | 27000 | 0 | 2025-12-12
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5609552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151189869 | Physically Completed | 23490 | 0 | 2026-02-06 | 2026-08-02
BETUL / SHAHPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5611269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114119381 | Physically Completed | 23490 | 0 | 2025-12-10 | 2026-08-02
BETUL / SHAHPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1731007019/IF/IAY/5988447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125685187 | Ongoing | 27000 | 0 | 2026-07-14
BETUL / SHAHPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1731007019/LD/22012034577735 — Ma ki Bagia P. S. School Tetermaal G.P. Mooda | Ongoing | 51332 | 0 | 2022-04-05
BETUL / SHAHPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1731007019/RS/22012035133571 — BHU NADEP NIRMAN 10 UNIT PANCHAM SIVPRASAD RAMPRASAD KAMAL SUKKAN PRAMOD HARLAL MULAYAM NEHARU BISAN | Ongoing | 90681.08 | 0 | 2025-01-02
BETUL / SHAHPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1731007019/WC/22012034886861 — STOP DAM NIRMAAN KARYA RAMPAL KE KHET KE PASS | Ongoing | 108925 | 0 | 2022-03-03
BETUL / SHAHPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1731007019/WC/22012035221936 — TALAB NIRMAN KARYA BABULAL KE KHET KE PASS MOODA | Approved | 0 | 0 | 2024-08-16
BETUL / SHAHPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1731007019/WH/22012034450175 — Talab Jirnouddhar Kary Kallu Ke Khet Ke Pas Gram Tetarmal | Ongoing | 361720.38 | 0 | 2022-02-14
BETUL / SHAHPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1731/DP/22012034555477 — Bamboo Plantation 10 He. MOODA | Ongoing | 1510614 | 0 | 2022-05-23