## Work List
Exported on: 2026-10-06 14:04:50
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: CHATARKHEDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732001015/AV/22012034470453 — प्रथमिक शाला चतरखेड़ा बाउड्रीवाल निर्माण कार्य | Completed | 26487 | 17952 | 2019-10-30 | 2020-01-29
NARMADAPURAM / SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732001015/AV/22012034470454 — प्राथमिक शाला भवन राजीव ग्राम चतराखेड़ा में बॉऊन्ड्रीवाल निर्माण कार्य | Completed | 35317 | 19008 | 2019-11-27 | 2020-01-22
NARMADAPURAM / SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001015/AV/22012034508879 — SHANTI DHAM NIRMAN KARY CHATARKHEDA | Deleted | 0 | 0 | 2020-01-26
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & Maintenance of Play field for Community / Repair and Maintenance of Play field for Community | Repair & Maint of Community infrastructure | 1732001015/AV/22012034509293 — खेल मैदान निर्माण कार्य शासकीय हाई स्कूल चतरखेड़ा | Completed | 393576.46 | 246640 | 2020-05-13 | 2021-10-06
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & Maintenance of Play field for Community / Repair and Maintenance of Play field for Community | Repair & Maint of Community infrastructure | 1732001015/AV/22012034509295 — खेल मैदान निर्माण कार्य शासकीय उच्चतर माध्यमिक शाला चतरखेड़ा | Completed | 215276.77 | 145830 | 2020-05-13 | 2021-10-06
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732001015/AV/22012034582564 — डायनिंग टेबिल निर्माण प्राथमिक शाला राजीव ग्राम चतरखेड़ा | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1732001015/DP/22012034542996 — माँ की बगिया प्राथमिक शाला चतरखेड़ा 23370701302 | Completed | 16976.64 | 7146 | 2022-04-05 | 2023-12-15
NARMADAPURAM / SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1732001015/DP/22012034542998 — माँ की बगिया प्राथमिक शाला राजीव ग्राम चतरखेड़ा 23370701304 | Completed | 16976.64 | 4896 | 2022-04-05 | 2024-06-20
NARMADAPURAM / SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1732001015/DP/22012034604167 — वसुधा वंदन अमृत वाटिका महोत्सव ग्राम पंचायत चतरखेडा | Deleted | 0 | 0 | 2023-07-25
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Avenue Plantation for Community | Plantation | 1732001015/DP/22012034627410 — वृक्षारोपण कार्य प्राथमिक शाला परिसर और सड़क किनारे चतरखेडा | Ongoing | 259479.75 | 16754 | 2025-02-17
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732001015/FP/22012034365763 — NALA GEHRIKARAN GRAM PANCHAYAT CHATERKHEDA | Deleted | 0 | 0 | 2020-04-14
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732001015/FP/22012034366009 — badh niyantaran hetu jal nikashi ka karya | Completed | 266140.98 | 241680 | 2020-06-17 | 2020-09-28
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732001015/FP/22012034369574 — badh niyantaran karya jal nikasi hetu | Deleted | 0 | 0 | 2021-01-21
NARMADAPURAM / SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732001015/FP/22012034633735 — बाढ़ नियन्त्रण हेतु जल निकासी कार्य बड़े मंदिर से बाबरी रोड नाले पर | Deleted | 0 | 0 | 2023-04-14
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001015/IF/22012034341633 — वृक्षारोपण कार्य बावरी रोड से राजीव ग्राम चतरखेड़ा में सड़क के दोनों और ईकाई 1 | Completed | 335000 | 92042 | 2017-05-24 | 2022-12-05
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001015/IF/22012034343898 — व्रक्षारोपण कार्य हाईस्कूल खेल मेदान मे ईकाई 2 | Completed | 335000 | 99690 | 2017-05-31 | 2022-12-05
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001015/IF/22012034349550 — बाँसरोपणकार्य नहर किनारे सिवनी माइनर इकाई 3 चतरखेड़ा | Completed | 535000 | 43166 | 2017-06-14 | 2019-11-15
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001015/IF/22012034352379 — बांसरोपण कार्य नहर किनारे 6 माइनर पर इकाई 4 | Completed | 535000 | 25980 | 2017-06-21 | 2019-07-12
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001015/IF/22012034352389 — बाँसरोपण कार्य नहर किनारे सिवनी माइनर झकलाय रोड पर इकाई 5 | Completed | 535000 | 38480 | 2017-06-21 | 2019-11-15
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001015/IF/22012034377664 — खेत की मेढ़ पर व्रक्षारोपन मदनलाल /द्वारकाप्रसाद | Completed | 187600 | 5432 | 2017-10-11 | 2019-07-12
NARMADAPURAM / SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1732001015/IF/22012035554877 — कूप रिचार्ज पिट आशीष शर्मा के खेत वाले कुएं पर चतरखेड़ा | Physically Completed | 25899.46 | 24658 | 2025-05-29 | 2026-04-06
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732001015/IF/22012035561097 — KHET TALAB NIRMAN KARYA ASHISH SHARMA KE KHET PAR CHATARKHEDA | Approved | 0 | 0 | 2025-04-14
NARMADAPURAM / SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732001015/IF/9993667631 — पशुशेड विजयसिंह लखनलाल चतरखेडा | Completed | 88073 | 65937 | 2015-06-29 | 2018-08-22
NARMADAPURAM / SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732001015/IF/9993667632 — पशुशेड शंकरलाल कुंजीलाल चतरखेडा | Completed | 88073 | 69650 | 2015-06-29 | 2018-08-22
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001015/IF/9993677728 — मेद्बंधान सुखदेव रामदयाल | Completed | 25502 | 954 | 2015-09-30 | 2016-06-28
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001015/IF/9993677737 — मेद्बंधान रामदीन मांगीलाल | Completed | 25502 | 636 | 2015-09-30 | 2016-06-28
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1131277 — Construction of IAY House -IAY REG. NO. MP2422520 | Completed | 15480 | 15480 | 2017-06-21 | 2017-11-27
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1170453 — Construction of IAY House -IAY REG. NO. MP2430468 | Completed | 15480 | 15480 | 2017-06-21 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1206898 — Construction of IAY House -IAY REG. NO. MP2430574 | Completed | 15480 | 15660 | 2018-06-27 | 2019-01-07
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1206910 — Construction of IAY House -IAY REG. NO. MP2470631 | Completed | 15480 | 13572 | 2018-06-06 | 2018-08-20
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1212254 — Construction of IAY House -IAY REG. NO. MP2414582 | Completed | 15480 | 15660 | 2018-05-30 | 2018-10-08
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1212297 — Construction of IAY House -IAY REG. NO. MP2435080 | Completed | 15480 | 15660 | 2018-06-06 | 2018-10-08
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1288995 — Construction of IAY House -IAY REG. NO. MP2473257 | Completed | 15480 | 15660 | 2018-05-09 | 2018-10-08
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1289602 — Construction of IAY House -IAY REG. NO. MP2496664 | Completed | 15480 | 15660 | 2018-05-30 | 2018-09-22
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1290522 — Construction of IAY House -IAY REG. NO. MP2528135 | Completed | 15480 | 15660 | 2018-05-09 | 2018-08-29
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1292209 — Construction of IAY House -IAY REG. NO. MP2585940 | Completed | 15480 | 15660 | 2018-05-09 | 2018-10-15
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1830267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2912580 | Completed | 15660 | 15660 | 2018-06-20 | 2018-12-05
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1858492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4275177 | Completed | 15660 | 15660 | 2018-08-01 | 2018-12-05
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1859076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4700657 | Completed | 15660 | 15660 | 2018-08-01 | 2018-12-05
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1910993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4726208 | Completed | 15660 | 15660 | 2018-08-08 | 2018-12-05
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1910996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4728675 | Completed | 15660 | 15660 | 2018-08-08 | 2018-12-05
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1911002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4735280 | Completed | 15660 | 15660 | 2018-08-08 | 2018-12-14
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1923029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4287160 | Completed | 15660 | 15660 | 2018-08-08 | 2018-12-25
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1923961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4715515 | Completed | 17100 | 17142 | 2018-08-08 | 2021-09-12
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1926125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4103771 | Completed | 15660 | 15660 | 2018-08-15 | 2018-12-05
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1926197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4346204 | Completed | 15660 | 15660 | 2018-08-15 | 2018-11-19
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1926212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4385728 | Completed | 15660 | 15660 | 2018-08-15 | 2018-11-30
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1926219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4417458 | Completed | 15660 | 15660 | 2018-08-15 | 2019-01-10
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1926399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4984066 | Completed | 15660 | 15660 | 2018-08-15 | 2018-10-31
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/1926433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5054388 | Completed | 15660 | 15660 | 2018-08-15 | 2019-01-07
NARMADAPURAM / SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/3704076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100858425 | Completed | 18360 | 18156 | 2022-05-17 | 2022-08-10
NARMADAPURAM / SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/3705719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100871084 | Completed | 18360 | 18156 | 2022-05-17 | 2022-08-22
NARMADAPURAM / SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/3735382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126317695 | Completed | 18360 | 18156 | 2022-05-17 | 2022-08-02
NARMADAPURAM / SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/40735 — Construction of IAY House -IAY REG. NO. MP-32-001-015-001/7 | Completed | 14310 | 14242 | 2016-01-06 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/40736 — Construction of IAY House -IAY REG. NO. MP-32-001-015-001/9 | Completed | 14310 | 14242 | 2016-01-06 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/40737 — Construction of IAY House -IAY REG. NO. MP-32-001-015-001/13 | Completed | 14310 | 14242 | 2016-01-06 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/415044 — Construction of IAY House -IAY REG. NO. MP1295537 | Completed | 15030 | 15180 | 2017-02-01 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/4176755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100866115 | Completed | 18360 | 18360 | 2022-07-05 | 2022-09-27
NARMADAPURAM / SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/417831 — Construction of IAY House -IAY REG. NO. MP1312795 | Completed | 15030 | 15270 | 2017-02-01 | 2017-11-13
NARMADAPURAM / SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/431881 — Construction of IAY House -IAY REG. NO. MP1407933 | Completed | 15030 | 15210 | 2017-02-01 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/4552305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113965722 | Completed | 21870 | 21870 | 2024-09-25 | 2025-03-17
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/4552313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113966701 | Completed | 23490 | 21978 | 2024-09-25 | 2025-09-30
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/4564656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116290394 | Completed | 21870 | 21870 | 2024-09-25 | 2025-02-25
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/4619368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126927993 | Completed | 23490 | 22014 | 2024-11-27 | 2025-08-06
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/4620212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126938063 | Completed | 21870 | 21870 | 2024-11-20 | 2025-02-25
NARMADAPURAM / SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/51011 — Construction of IAY House -IAY REG. NO. MP-32-001-015-001/10 | Completed | 14310 | 14409 | 2016-01-06 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/5119052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126676679 | Completed | 23490 | 23310 | 2025-03-20 | 2025-09-30
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/5119743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126908540 | Completed | 23490 | 23130 | 2025-03-20 | 2025-08-06
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/5120416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127621071 | Completed | 23490 | 23130 | 2025-03-20 | 2025-08-06
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/5128899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113542842 | Completed | 23490 | 23490 | 2025-04-02 | 2025-10-08
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/5662230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113965989 | Completed | 23490 | 23490 | 2025-07-09 | 2026-01-20
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/5662231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113968486 | Completed | 23490 | 22995 | 2025-07-09 | 2026-01-20
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/5692101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146809656 | Completed | 23490 | 23490 | 2025-07-23 | 2026-05-19
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/5692123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121589681 | Completed | 23490 | 23490 | 2025-07-23 | 2025-11-11
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001015/IF/IAY/5866412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113965388 | Ongoing | 27000 | 24567 | 2026-01-28
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/660481 — Construction of IAY House -IAY REG. NO. MP1409025 | Completed | 15030 | 15480 | 2017-05-10 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/660701 — Construction of IAY House -IAY REG. NO. MP1448394 | Completed | 15030 | 15480 | 2017-05-10 | 2017-11-27
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/661006 — Construction of IAY House -IAY REG. NO. MP1493262 | Completed | 15030 | 15480 | 2017-05-10 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/669410 — Construction of IAY House -IAY REG. NO. MP2273430 | Completed | 15030 | 15480 | 2017-05-10 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/669692 — Construction of IAY House -IAY REG. NO. MP2290125 | Completed | 15030 | 15480 | 2017-05-03 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/669728 — Construction of IAY House -IAY REG. NO. MP2293797 | Completed | 15030 | 15480 | 2017-05-10 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/670334 — Construction of IAY House -IAY REG. NO. MP2333948 | Completed | 15030 | 15480 | 2017-05-10 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/670432 — Construction of IAY House -IAY REG. NO. MP2338164 | Completed | 15030 | 15480 | 2017-05-03 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/670436 — Construction of IAY House -IAY REG. NO. MP2338202 | Completed | 15030 | 15504 | 2017-05-10 | 2018-06-25
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/670438 — Construction of IAY House -IAY REG. NO. MP2338207 | Completed | 15030 | 15480 | 2017-05-03 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/671464 — Construction of IAY House -IAY REG. NO. MP2414155 | Completed | 15030 | 15480 | 2017-05-10 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/671480 — Construction of IAY House -IAY REG. NO. MP2414556 | Completed | 15030 | 15528 | 2017-05-03 | 2018-05-10
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/671622 — Construction of IAY House -IAY REG. NO. MP2422220 | Completed | 15030 | 15480 | 2017-05-03 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/671628 — Construction of IAY House -IAY REG. NO. MP2422328 | Completed | 15030 | 15480 | 2017-05-10 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/671629 — Construction of IAY House -IAY REG. NO. MP2422387 | Completed | 15030 | 15480 | 2017-05-10 | 2017-11-13
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/671965 — Construction of IAY House -IAY REG. NO. MP2462828 | Completed | 15030 | 15480 | 2017-05-03 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/672262 — Construction of IAY House -IAY REG. NO. MP2496706 | Completed | 15030 | 15480 | 2017-05-03 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/672561 — Construction of IAY House -IAY REG. NO. MP2518436 | Completed | 15030 | 15480 | 2017-05-03 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/672743 — Construction of IAY House -IAY REG. NO. MP2527888 | Completed | 15030 | 15480 | 2017-05-17 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/676110 — Construction of IAY House -IAY REG. NO. MP2912290 | Completed | 15030 | 15480 | 2017-05-10 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/676332 — Construction of IAY House -IAY REG. NO. MP2938652 | Completed | 15030 | 15480 | 2017-05-03 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/677054 — Construction of IAY House -IAY REG. NO. MP3019519 | Completed | 15030 | 15480 | 2017-05-03 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/677056 — Construction of IAY House -IAY REG. NO. MP3019547 | Completed | 15030 | 15480 | 2017-05-10 | 2017-11-09
NARMADAPURAM / SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/677058 — Construction of IAY House -IAY REG. NO. MP3019593 | Completed | 15030 | 15660 | 2018-05-09 | 2018-07-31
NARMADAPURAM / SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732001015/IF/IAY/683411 — Construction of IAY House -IAY REG. NO. MP3983213 | Approved | 27000 | 0 | 2017-03-15
NARMADAPURAM / SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1732001015/LD/22012034312657 — SHANTI DHAM NIRMAN KARYA CHATARKHEDA | Completed | 180000 | 5160 | 2017-05-17 | 2019-08-05
NARMADAPURAM / SEONI MALWA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1732001015/LD/3799401878 — खेल मैदान प्राथमि‍क शाला चतरखेडा | Completed | 176027 | 17682 | 2013-08-12 | 2014-04-30
NARMADAPURAM / SEONI MALWA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034155611 — P.P.C.C. road Nali Jagdishprasad ke ghar se shan | Completed | 77641 | 40110 | 2013-01-25 | 2013-03-25
NARMADAPURAM / SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034168534 — पंच परमेश्‍वर रोड लक्ष्‍मण के घर से संगम के घर की | Completed | 111215 | 77032 | 2013-05-29 | 2014-04-30
NARMADAPURAM / SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034185017 — पंच परमेश्‍वर रोड रवि‍ गौर के घर से आंगनवाडी की ओर | Completed | 148133 | 89842 | 2013-09-23 | 2014-01-30
NARMADAPURAM / SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034207856 — सासंद निधि सी.सी.रोड एवं नाली निर्माण झकलाय रोड पर | Completed | 61168 | 3212 | 2014-02-24 | 2016-09-07
NARMADAPURAM / SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034229608 — पंचपरमेश्‍वर रोड खेडापति से लेकर धमेन्‍द्र के खले तक चतरखेडा | Completed | 187826 | 93141 | 2014-10-01 | 2018-07-30
NARMADAPURAM / SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034229610 — पंचपरमेश्‍वर रोड धमेन्‍द्र के खले से नारायणसिह के | Completed | 187826 | 113519.6 | 2014-10-01 | 2016-09-07
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034266138 — पंचपरमेश्‍वर रोड मोहनलाल के घर से कैलाश के घर की ओर चतरखेडा | Completed | 125217 | 93170 | 2015-06-10 | 2017-12-27
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034266139 — पंचपरमेश्‍वर रोड संतोष के घर से अभिमन्‍यु के घर तक चतरखेडा | Completed | 109565 | 88583 | 2015-06-10 | 2018-07-30
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001015/RC/22012034294884 — पंचपरमेश्वर रोड एवम नाली निर्माण प्रेम गौर के घर से आगंनवाडी भवन की और चतरखेडा | Completed | 79287 | 55991 | 2016-01-06 | 2019-07-12
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001015/RC/22012034306925 — सी.सी. रोड एवम नाली निर्माण् | Deleted | 0 | 0 | 2016-01-26
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001015/RC/22012034306928 — सी.सी.रोड एवम नाली निर्माण् | Deleted | 0 | 0 | 2016-01-26
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001015/RC/22012034306931 — सी.सी.रोड एवम नाली निर्माण् | Deleted | 0 | 0 | 2016-01-26
NARMADAPURAM / SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034321638 — c.c.road nali nirmanharisingh ke ghar se naale ki or | Deleted | 69472 | 0 | 2017-01-25
NARMADAPURAM / SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034324221 — C C ROAD NIRMAN | Deleted | 0 | 0 | 2017-04-01
NARMADAPURAM / SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034324586 — C C ROAD NIRMAN | Suspended | 0 | 0 | 2019-07-10
NARMADAPURAM / SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034327127 — c.c.road nirman hanuman mandir se khedapati c.c. road ki aur chatarkheda | Completed | 28800 | 17060 | 2017-02-15 | 2019-07-12
NARMADAPURAM / SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034374270 — सी सी रोड एवं नाली नि‍मार्ण कार्य राजीव ग्राम मे तेजीलाल के घर से चरनसिंह के घर की और | Deleted | 0 | 0 | 2018-04-01
NARMADAPURAM / SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034398217 — सी.सी.रोड व नाली निर्माण कार्य राजीव ग्राम मे प्राथमिकशाला के पास से मिश्रीलाल के घर की और | Completed | 85605 | 77250 | 2019-02-27 | 2019-12-26
NARMADAPURAM / SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034438966 — c c road nirman karya | Deleted | 0 | 0 | 2019-04-14
NARMADAPURAM / SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034439983 — c.c.roed evam nali nirman | Deleted | 0 | 0 | 2018-12-29
NARMADAPURAM / SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034445770 — सी.सी. रोड एवं नाली निर्माण कार्य तेजीलाल के घर से | Completed | 85605 | 77604 | 2019-02-27 | 2020-02-22
NARMADAPURAM / SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034446175 — सी.सी. नाली निर्माण कार्य श्री राम जानकी मंदिर से जगदीश प्रसाद के घर की और | Deleted | 29700 | 0 | 2016-10-02
NARMADAPURAM / SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034446182 — सी.सी. नाली निर्माण कार्य रूपराम के घर से देशमुख बाबा(नाले)की और | Deleted | 37125 | 0 | 2016-10-02
NARMADAPURAM / SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034446185 — सी.सी. रोड एवं नाली निर्माण कार्य कमल रघुवंशी के घर से अमीरसिंह के घर की और | Deleted | 0 | 0 | 2016-10-02
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034512653 — C.C.ROAD EVAM NALI NIRMAN KARYA GHANSHYAM KE GHAR SE MALTI BAI KE GHAR KI AUR RAJEEV GRAM 90 MEETER | Completed | 69511 | 68400 | 2020-11-11 | 2020-12-22
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034512654 — C.C.ROAD NIRMAN KARYA NARMADAPRASAD RAGHUWANSHI KE GHAR SE LALSINGH MEHRA KE GHAR KI AUR 40MEETER | Completed | 18242 | 18240 | 2021-02-10 | 2021-02-23
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034512655 — C.C.ROAD NIRMAN KARYA RADHESHYAM PATEL KE KHALE SE SANTOSH PATEL KE KHALE KI AUR | Completed | 35983 | 35340 | 2021-02-24 | 2021-04-04
NARMADAPURAM / SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034512656 — C.C.ROAD EVAM NALI NIRMAN KARYA | Deleted | 0 | 0 | 2019-10-02
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034545193 — C.C.ROAD & NALI NIRMAN KARYA | Deleted | 0 | 0 | 2020-04-14
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034545194 — C.C. ROAD EVAM NALI NIRMAN KARYA DURGALAL KE GHAR SE GANNULAL KE GHAR KI AUR 80 meeter | Completed | 62942 | 61560 | 2020-10-21 | 2020-12-22
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034561921 — C.C.ROAD EVAM NALI NIRMAN KARYA NARMADA PRASAD GOUR KE GHAR SE MAIN ROAD KI AUR | Deleted | 0 | 0 | 2021-01-21
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034606621 — C C ROAD NIRMAN KARYA SOSAYTI KE PASS SE OMPRAKASH RAGHUWANSHI KE GHAR KI AUR CHATARKHEDA | Completed | 142685 | 69094 | 2022-02-15 | 2024-05-08
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034606622 — C C ROAD NIRMAN KARYA SOSAYTI KE PASS SE OMPRAKASH RAGHUWANSHI KE GHAR KI AUR CHATARKHEDA | Deleted | 0 | 0 | 2021-08-16
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034606623 — C C ROAD NIRMAN KARYA SOSAYTI KE PASS SE OMPRAKASH RAGHUWANSHI KE GHAR KI AUR CHATARKHEDA | Deleted | 0 | 0 | 2021-08-16
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034606652 — C C ROAD NIRMAN KARYA SOSAYTI KE PASS SE OMPRAKASH RAGHUWANSHI KE GHAR KI AUR CHATARKHEDA | Deleted | 0 | 0 | 2021-08-16
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034606653 — C C ROAD NIRMAN KARYA SOSAYTI KE PASS SE OMPRAKASH RAGHUWANSHI KE GHAR KI AUR CHATARKHEDA | Deleted | 0 | 0 | 2021-08-16
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034606654 — C C ROAD NIRMAN KARYA SOSAYTI KE PASS SE OMPRAKASH RAGHUWANSHI KE GHAR KI AUR CHATARKHEDA | Deleted | 0 | 0 | 2021-08-16
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034606655 — C C ROAD NIRMAN KARYA SOSAYTI KE PASS SE OMPRAKASH RAGHUWANSHI KE GHAR KI AUR CHATARKHEDA | Deleted | 142685 | 0 | 2021-08-16
NARMADAPURAM / SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034607680 — CC ROAD NALI NIRMAN | Deleted | 0 | 0 | 2022-04-01
NARMADAPURAM / SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034620862 — C C ROAD NIRMAN KARYA KELASH PATEL KE GHAR SE PWD ROAD KI AUR CHATARKHEDA | Completed | 13200 | 13039 | 2023-06-06 | 2024-05-28
NARMADAPURAM / SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034660661 — सी सी रोड निर्माण कार्य हरिसिंह लोवंशी के घर से राजेश के घर की और | Completed | 57363 | 51119 | 2023-10-06 | 2024-03-04
NARMADAPURAM / SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034660675 — सी सी रोड निर्माण कार्य देशमुख बाबा से बाबरी रोड की और | Completed | 29182 | 28214 | 2023-10-06 | 2024-05-08
NARMADAPURAM / SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of WBM Roads for Community / Construction of WBM Roads for Community | Construction of Road and Culvert | 1732001015/RC/22012034820762 — C C ROAD NIRMAN KARYA DEVENDRA PARASHAR KE GHAR SE MAIN ROAD KI AUR CHATARKHEDA | Completed | 47210 | 46636.96 | 2024-07-02 | 2024-10-23
NARMADAPURAM / SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1732001015/RC/22012034821817 — C C ROAD NIRMAN KARYA DWARKA LOWANSHI WALE HANDPUMP SE MAIN ROAD KI AUR CHATARKHEDA | Completed | 38920 | 38888.16 | 2024-07-09 | 2024-09-18
NARMADAPURAM / SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001015/RC/22012034835995 — C C ROAD NIRMAN KARY MUKHAY MARG SE KAMAL KISHORE KE GHAR KI AUR RAJEEV GRAM CHATARKHEDA | Completed | 37836 | 37020.99 | 2025-02-24 | 2025-10-08
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1732001015/RC/22012034845447 — C C ROAD NIRMAN BABRI ROAD SE VISHRAM MALVIYA KE GHAR KI AUR CHATARKHEDA | Completed | 68380 | 68318.04 | 2025-07-16 | 2025-11-06
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of WBM Roads for Community / Construction of WBM Road for Community | Construction of Road and Culvert | 1732001015/RC/22012034851456 — C C ROAD NIRMAN KARY SHANKAR MANDIR SE KERWAR JI KE GHAR KI AUR CHATARKHEDA | Physically Completed | 66600 | 65753.26 | 2026-02-04 | 2026-08-11
NARMADAPURAM / SEONI MALWA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001015/RC/53 — ग्रेवल रोड निमार्ण चतरखेडा | Suspended | 473181 | 340 | 2008-10-01
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001015/RS/22012034287132 — शोचालय निर्माण बाबूलाल / परमू चतरखेडा | Completed | 3180 | 3180 | 2015-10-07 | 2015-10-19
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001015/RS/22012034287136 — शोचालय निर्माण दगडू /मनोहर चतरखेडा | Completed | 3180 | 3180 | 2015-10-07 | 2015-10-19
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001015/RS/22012034287137 — शोचालय निर्माण धन्नालाल/बलदेव चतरखेडा | Completed | 3180 | 3180 | 2015-10-07 | 2015-10-19
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001015/RS/22012034287174 — शोचालय निर्माड कल्लु/बाजीलाल चतरखेदा | Completed | 3180 | 3180 | 2015-10-07 | 2015-10-19
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001015/RS/22012034288179 — शोचालय निर्माढ तेजीलाल/पान्डु | Completed | 3180 | 3180 | 2015-10-28 | 2015-11-09
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001015/RS/22012034288358 — सोचालय निर्माँण भागीरथ/गेन्दालाल | Completed | 3180 | 3180 | 2015-10-28 | 2015-11-09
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001015/RS/22012034288361 — सोचालय निर्माण कल्लु/रामदयाल | Completed | 3180 | 3180 | 2015-10-28 | 2015-11-09
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001015/RS/22012034288365 — सोचालय निर्माण रामदयाल /सम्भु | Completed | 3180 | 3180 | 2015-10-28 | 2015-11-09
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001015/RS/22012034290345 — शोचालय निर्माण भगवानदास/ रामलाल | Deleted | 3180 | 0 | 2015-08-15
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001015/RS/22012034290351 — शोचालय निर्माण बाजी लाल /पांडु | Deleted | 3180 | 0 | 2015-08-15
NARMADAPURAM / SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001015/RS/22012034290356 — शोचालय निर्माण दीपक /रामदीन | Deleted | 3180 | 0 | 2015-10-28
NARMADAPURAM / SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034438633 — C.C.NALI NIRMAN KARYA SHREE RAM JANKI MANDIR SE JAGDISH PRASAD KE GHAR KI AUR | Completed | 29700 | 29538 | 2019-02-27 | 2019-09-13
NARMADAPURAM / SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034438638 — C.C.NALI NIRMAN KARYA KAMAL RAGHUWANSHI KE GHAR SE AMEER SINGH KE GHAR KI AUR | Deleted | 0 | 0 | 2016-10-02
NARMADAPURAM / SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034438639 — C.C.NALI NIRMAN KARYA ROOPRAM RAGHUWANSHI KE GHAR SE DESHMUKH BABA KI AUR | Completed | 37125 | 31632 | 2019-02-27 | 2019-10-01
NARMADAPURAM / SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034438642 — C.C.NALI NIRMAN KARYA KAMAL RAGHUWANSHI KE GHAR SE AMEER SINGH KE GHAR KI AUR | Completed | 29700 | 14736 | 2019-02-27 | 2019-10-01
NARMADAPURAM / SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034478586 — C.C. NALI NIRMAN SHERSINGH KE GHAR SE RAMBABU PATEL KE GHAR KI AUR | Deleted | 0 | 0 | 2019-10-02
NARMADAPURAM / SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034478587 — C.C.NALI NIRMAN NARMADA PRASAD KE GHAR SE JITENDRA RAGHUWANSHI KE GHAR KI AUR | Deleted | 0 | 0 | 2019-10-02
NARMADAPURAM / SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034478588 — C.C.NALI NIRMAN KARYA VIJAYSINGH RAGHUWANSHI KE GHAR SE DEVI CHABUTRA KI AUR | Completed | 5568 | 5280 | 2020-03-11 | 2020-03-26
NARMADAPURAM / SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034478589 — C.C.NALI NIRMAN KARYA PAWAN RATHOR KE GHAR SE DHANIYA BAI KE GHAR KI AUR | Deleted | 0 | 0 | 2019-10-02
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034478590 — R.C.C.NALI NIRMAN KARYA BABRI ROAD PAR SHIVA SOLANKI KE GHAR SE NALE KI AUR 85 MEETER | Completed | 31110 | 30870 | 2021-03-10 | 2021-04-10
NARMADAPURAM / SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034478591 — C.C.NALI NIRMAN KARYA ISHVARDAS KE GHAR SE RAMVILAS KE GHAR KI AUR | Deleted | 0 | 0 | 2019-10-02
NARMADAPURAM / SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034480521 — C.C.NALI NIRMAN KARYA MADAN LAL PATHAK KE GHAR SE SHANKAR LAL KE GHAR KI AUR | Completed | 2228 | 2112 | 2020-03-11 | 2020-03-20
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034498478 — वाटर वे क्लीनिंग ब्रिज न कंदेली ब्रिज | Completed | 109930 | 83376 | 2021-05-04 | 2021-09-10
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034510769 — RCC NALI NIRMAN KARYA GAMBHIR RAGHUWANSHI KE GHAR SE ASHOK RAGHUWANSHI KE GHAR KI AUR | Deleted | 0 | 0 | 2021-01-21
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034510770 — C C NALI NIRMAN KARY ISHWARDAS MALVIYA KE GHAR SE RAMVILASH RAGHUWANSHI KE GHAR KI AUR | Deleted | 0 | 0 | 2021-01-21
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034510771 — C.C. NALI NIRMAN KARYA SHRI RAM JAMADAR KE GHAR SE JITENDRA RAGHUWANSHI KE GHAR KI AUR | Deleted | 0 | 0 | 2021-01-21
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001015/RS/22012034526575 — samudayik nadep prathmik shala chatarkheda ke pass | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001015/RS/22012034526580 — samudayik nadep deshmukh baba ke pass chatarkheda | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001015/RS/22012034526583 — samudayik nadep sosayti ke pass chatarkheda | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001015/RS/22012034526586 — samudayik nadep sashkiya bhumi par bhilpura road chatarkheda | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001015/RS/22012034526587 — samudayik nadep khedapati mandir ke pass chatarkheda | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001015/RS/22012034526589 — samudayik nadep khedapati mandir ke pass chatarkheda | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001015/RS/22012034526607 — sokhta gadda sokpit prathmik shala handpump ke pass chatarkheda | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034526611 — sokhta gadda sokpit yatri pratikshalay ke pass chatarkheda | Completed | 91916.92 | 29412 | 2021-08-18 | 2025-05-16
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034526615 — sokhta gadda sokpit high school handpump chatarkheda | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034526616 — sokhta gadda sokpit sosayti handpump ke pass chatarkheda | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034526619 — sokhta gadda sokpit prathmik shala handpump ke pass rajeev gram chatarkheda | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001015/RS/22012034580327 — नाडेप निर्माण कार्य यूनिट संख्या 05 ग्राम पंचायात चतरखेडा | Closed | 126446.88 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034619956 — आर सी सी नाली निर्माण कार्य गंभीर रघुवंशी के घर से अशोक रघुवंशी के घर कि और | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034619957 — आर सी सी नाली निर्माण कार्य हरिसिंह लोवंशी के घर से राजेश चौहान के घर की और रोड के दोनों साइड | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034658994 — RCC NALI NIRMAN KARYA SOSAYTI KE PASS SE OPPRAKASH KE GHAR KI AUR CHATARKHEDA | Deleted | 0 | 0 | 2022-04-14
NARMADAPURAM / SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012034698516 — RCC NALI NIRMAN KARYA GAMBHIR RAGHUWANSHI KE GHAR SE ASHOK RAGHUWANSHI KE GHAR KI AUR | Completed | 37748 | 37306 | 2023-07-26 | 2024-05-28
NARMADAPURAM / SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012035115041 — सी सी नाली निर्माण कार्य हरिसिंह लोवंशी के घर से राजेश के घर की और चतरखेड़ा | Completed | 48071 | 39248 | 2023-10-06 | 2024-03-04
NARMADAPURAM / SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001015/RS/22012035115045 — सी सी नाली निर्माण कार्य श्री राम रघुवंशी के घर से जीतेन्द्र रघुवंशी के घर की और चतरखेड़ा | Completed | 17982 | 17894 | 2023-10-06 | 2024-08-29
NARMADAPURAM / SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012035115050 — सी सी नाली निर्माण कार्य ईश्वर दास मालवीय के घर से मेन रोड की और चतरखेड़ा | Completed | 16102 | 15534 | 2023-10-06 | 2024-05-08
NARMADAPURAM / SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012035115053 — सी सी नाली निर्माण कार्य देवदास मालवीय के घर से राजेश सराठे के घर की और चतरखेड़ा | Completed | 10460 | 9716 | 2023-10-06 | 2024-03-04
NARMADAPURAM / SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012035128643 — C C NALI NIRMAN KARYA DWARKA LOWANSHI WALE HANDPUMP SE MAIN ROAD KI AUR CHATARKHEDA | Completed | 12575 | 12140.28 | 2024-07-02 | 2024-09-18
NARMADAPURAM / SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012035128660 — C C NALI NIRMAN KARYA DEVENDRA PARASHAR KE GHAR SE MAIN ROAD KI AUR CHATARKHEDA | Completed | 10898 | 9476.7 | 2024-07-02 | 2024-10-23
NARMADAPURAM / SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001015/RS/22012035128663 — RCC NALI NIRMAN KARYA ABHIMANYU VARMA KE GHAR SE MOHAN RAGHUWANSHI KE GHAR KI AUR CHATARKHEDA | Completed | 35271 | 35174.52 | 2024-07-02 | 2025-12-06
NARMADAPURAM / SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001015/SK/923 — Bharat Nirman Rajeev Gandhi Sewa Kendra,CHATARKHEDA | Completed | 118101 | 95242 | 2013-09-23 | 2019-03-27
NARMADAPURAM / SEONI MALWA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001015/WC/197 — निर्मलनीर चतरखेडा | Suspended | 139383 | 2275 | 2009-02-17
NARMADAPURAM / SEONI MALWA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001015/WC/22012034382858 — तालाब नि‍मार्ण कार्य | Deleted | 0 | 0 | 2018-04-01
NARMADAPURAM / SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1732001015/WC/22012034577512 — C.P.T. NIRMAN KARYA RAJEEV GRAM ME SHASKIYA BHUMI PAR ROAD SAID | Completed | 204597.7 | 106536 | 2021-04-06 | 2021-10-06
NARMADAPURAM / SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732001015/WC/22012034621603 — badh niyantaran hetu jal nikasi karyav | Deleted | 0 | 0 | 2021-01-21
NARMADAPURAM / SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1732001015/WC/22012034621611 — C.P.T NIRMAN KARYA TORANIYA GOHE SE BAGHAAI MATA KI AUR | Deleted | 0 | 0 | 2021-01-21
NARMADAPURAM / SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1732001015/WC/22012034621622 — C.P.T NIRMAN KARYA KHEDAPATI ROAD SE RAJEEV GRAM PAHUCH GOHE KI AUR | Deleted | 0 | 0 | 2021-01-21
NARMADAPURAM / SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1732001015/WC/22012034621624 — C.P.T NIRMAN KARYA jhaklay ROAD SE KHATKAD GOHE KI AUR | Deleted | 0 | 0 | 2021-01-21
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1732001015/WC/22012034638643 — CTR BADH NIYANTARAN HETU JAL NIKASI KARYA BABRI ROAD SE KANDELI NADI KI AUR CHATARKHEDA | Closed | 63912.36 | 0 | 2021-04-01
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1732001015/WC/22012034638662 — CTR KACHCHI NALI NIRMAN KARYA TORANIYA GOHE SE BAGHAI MATA KI AUR CHATARKHEDA | Completed | 98119.78 | 83376 | 2021-07-06 | 2021-10-06
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1732001015/WC/22012034638667 — CTR KACHCHI NALI NIRMAN KARYA KHEDAPATI ROAD SE RAJEEV GRAM KI AUR CHATARKHEDA | Completed | 98821.28 | 93798 | 2021-06-01 | 2021-10-06
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1732001015/WC/22012034638673 — CTR KACHCHI NALI NIRMAN KARYA JHAKLAY ROAD SE SURESH PATEL KE KHET KI AUR CHATARKHEDA | Completed | 99422.03 | 88008 | 2021-09-14 | 2022-03-07
NARMADAPURAM / SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732001015/WC/22012034782042 — CTR PRATHMIK SHALA ME ROOF WATER HARVESTING CHATARKHEDA | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732001015/WC/22012034782046 — CTR E PANCHAYAT KAKSH ME ROOF WATER HARVESTING KARYA CHATARKHEDA | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732001015/WC/22012034782049 — CTR AAGANWADI KENDRA 01 PER ROOF WATER HARVESTING CHATARKHEDA | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732001015/WC/22012034782058 — CTR PRATHMIK SHALA KE ATIRIKT KAKSH AAGANWADHI KENDRA 03 PER ROOF WATER HARVETING KARYA CHATARKHEDA | Deleted | 0 | 0 | 2021-04-14
NARMADAPURAM / SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coast Line Plntation-Coastal Shelter Belt-Comm / Along the coast Line Plantation of Coastal Shelter Belt Trees for Community | Plantation | 1732001015/WC/22012034811564 — CTR माँ की बगिया शासकीय माध्यमिक शाला चतरखेड़ा | Deleted | 0 | 0 | 2021-08-16
NARMADAPURAM / SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1732001015/WC/22012034876643 — CTR कच्ची नाली निर्माण कार्य श्याम सिंह के खेत से संतोष के खेत की और | Deleted | 0 | 0 | 2021-10-02
NARMADAPURAM / SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1732001015/WC/22012034889805 — जल निकासी हेतु कच्ची नाली निर्माण कार्य छोटेराम के खेत से दामोदर के खेत की और चतरखेड़ा | Completed | 104990.87 | 35989 | 2022-05-17 | 2025-05-16
NARMADAPURAM / SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1732001015/WC/22012034889806 — CTR कच्ची नाली निर्माण कार्य छोटेराम के खेत से दामोदर के खेत की और | Deleted | 0 | 0 | 2021-10-02
NARMADAPURAM / SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1732001015/WC/22012034889808 — जल निकासी हेतु कच्ची नाली निर्माण कार्य केलाश पटेल के खेत से रामविलास के खेत की और | Deleted | 0 | 0 | 2021-10-02
NARMADAPURAM / SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1732001015/WC/22012034889809 — CTR कच्ची नाली निर्माण कार्य केलाश पटेल के खेत से रामविलास के खेत की और | Deleted | 0 | 0 | 2021-10-02
NARMADAPURAM / SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001015/WC/22012034894770 — पुलिया मय स्टॉपडेम तोरानिया नाले पर पटेल बाबा की और चतरखेड़ा | Deleted | 0 | 0 | 2021-10-02
NARMADAPURAM / SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1732001015/WC/22012034979308 — जल निकासी हेतु कच्ची नाली निर्माण कार्य शरद के खेत से राजू के खेत कि और | Physically Completed | 139596.3 | 44915.36 | 2022-05-24 | 2026-06-05
NARMADAPURAM / SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732001015/WC/22012034979311 — जल निकासी हेतु कच्ची नाली निर्माण कार्य रंजीत सिंह के खेत से कमलेश के खेत कि और | Completed | 126629.55 | 38024 | 2022-05-24 | 2025-04-17
NARMADAPURAM / SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1732001015/WC/22012035015480 — CTR जल निकासी हेतु कच्ची नाली निर्माण कार्य झकलाय रोड से संतोष के खेत की और ग्राम चतरखेड़ा | Completed | 139046.12 | 118249 | 2022-11-22 | 2024-10-19
NARMADAPURAM / SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1732001015/WC/22012035015499 — CTR जल निकासी हेतु कच्ची नाली निर्माण कार्य गणेशप्रसाद के खेत से नाले की और ग्राम चतरखेड़ा | Completed | 142933.43 | 91265 | 2023-08-01 | 2025-03-17
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001015/WC/22012035203318 — Badh niyantran hetu nala upchar kary Bade mandir se Babri Road ki aur Nale par Chatarkheda | Completed | 64610.56 | 50787 | 2024-06-25 | 2025-04-16
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001015/WC/22012035203323 — JAL NIKASHI KARYA BADE MANDIR SE BABRI ROAD KI AUR CHATARKHEDA | Deleted | 0 | 0 | 2024-04-14
NARMADAPURAM / SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1732001015/WC/22012035296264 — RECHARGE PIT RAMKISHOR KE GHAR KE PASS RAJIV GRAM CHATARKHEDA | Deleted | 0 | 0 | 2025-04-14