## Work List
Exported on: 2026-09-10 22:25:16
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: CHATARKHEDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1732001015/DP/22012034627410 — वृक्षारोपण कार्य प्राथमिक शाला परिसर और सड़क किनारे चतरखेडा | Ongoing | 259479.75 | 0 | 2025-02-17
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001015/IF/22012035561097 — KHET TALAB NIRMAN KARYA ASHISH SHARMA KE KHET PAR CHATARKHEDA | Approved | 0 | 0 | 2025-04-14
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/5866412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113965388 | Ongoing | 27000 | 4671 | 2026-01-28
NARMADAPURAM / SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001015/IF/IAY/683411 — Construction of IAY House -IAY REG. NO. MP3983213 | Approved | 27000 | 0 | 2017-03-15
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of WBM Roads for Community / Construction of WBM Roads for Community | Construction of Road and Culvert | 1732001015/RC/22012034851456 — C C ROAD NIRMAN KARY SHANKAR MANDIR SE KERWAR JI KE GHAR KI AUR CHATARKHEDA | Physically Completed | 66600 | 0 | 2026-02-04 | 2026-08-11