## Work List
Exported on: 2026-10-01 12:11:34
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BAWADIYABHAU
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1732001018/AV/22012034511740 — शांति धाम निर्माण बाबडिया भाऊ | Ongoing | 194312.08 | 0 | 2020-07-06
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Construction of Road and Culvert | 1732001018/AV/22012034602429 — पेपर ब्लाक निर्माण कार्य मिडिल स्कूल परिसर मे बाबड़िया भाऊ | Ongoing | 30705 | 0 | 2021-11-18
NARMADAPURAM / SEONI MALWA | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1732001018/AV/22012034609369 — यात्री प्रतिक्षालय जीरावेह रोड पर बस स्टेंड के पास बाबडिया भाऊ | Ongoing | 19773 | 0 | 2021-11-18
NARMADAPURAM / SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1732001018/DP/22012034604294 — VASUDHA VANDAN AMRIT VATIKA PRATHMIK SWASTHYA KENDRA BABADIYA BHAU | Ongoing | 55847.4 | 1800 | 2023-08-17
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1732001018/FP/22012034368820 — construction of drain for flood water babadiya bhau | Ongoing | 342677.2 | 0 | 2021-01-11
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001018/IF/IAY/4600173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123868475 | Completed | 23490 | 0 | 2024-10-10 | 2026-08-20
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001018/IF/IAY/4666241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151229090 | Completed | 23490 | 0 | 2024-11-21 | 2026-08-20
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001018/IF/IAY/4666622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151295108 | Ongoing | 27000 | 0 | 2025-02-06
NARMADAPURAM / SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001018/RC/22012034834818 — C C ROD NIRMAN KARYA SHASKIYA HIGH SCHOOL BABADIYA BHAU | New | 0 | 0 | 2024-10-02
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001018/RC/22012034845489 — C C ROD NIRMAN KARYA UNNAYANIKARAN SANTOSH KE GHAR SE GULABSINGH KE GHAR KI OR BABADIYA BHAU | Physically Completed | 47105 | 0 | 2025-07-11 | 2026-08-25
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001018/RC/22012034848717 — C C ROD NIRMAN KARYA HARIOM VARMA KE GHAR SE BALAI VALE NALE KI OR BABADIYA BHAU | Physically Completed | 53452 | 0 | 2025-11-20 | 2026-08-25
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001018/RC/22012034848720 — C C ROD NIRMAN KARYA UNNAYANIKARAN AVINASH KE GHAR SE KAILASH KE GHAR KI OR BABADIYA BHAU | Approved | 20447 | 0 | 2025-04-14
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001018/RC/22012034851379 — c c rod nirman gyansingh ke ghar se prakash ke khet ki or babadiya bhau | Physically Completed | 75795 | 0 | 2025-12-25 | 2026-08-25
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001018/RC/22012034853498 — C C ROD NIRMAN DONO SIDE PATTI VIJAY VARMA KE GHAR SE KUNWARSINGH KE GHAR KI OR BABADIYA BHAU | Approved | 36000 | 0 | 2026-01-24
NARMADAPURAM / SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001018/RS/22012035127821 — R C C NALI NIRMAN GURU MAHARAJ MANDIR SE PULIYA KI OR BABADIYA BHAU | Approved | 0 | 0 | 2024-06-05
NARMADAPURAM / SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732001018/WC/22012034774014 — CTR SOKHTA GADDA MIDDLE SCHOOL KE PASS BABADIYA BHAU | Ongoing | 71023.53 | 0 | 2021-08-12