## Work List
Exported on: 2026-09-07 06:45:05
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: CHAUTLAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / SEONI MALWA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1732001034/DP/22012034426993 — बृक्षारोपण कार्य सडक के दोनो चौंतलाय | Ongoing | 342000 | 0 | 2018-08-20
NARMADAPURAM / SEONI MALWA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1732001034/DP/22012034426995 — बृक्षारोपण कार्य शांति धाम के चारो ओर | Ongoing | 342000 | 0 | 2018-08-20
NARMADAPURAM / SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1732001034/DP/22012034564886 — बृक्षारोपण कार्य(शा.प्राथमिक ,माध्यमिक, नविन प्राथमिक शाला पहाड़ी ) चौतलाय | Ongoing | 409218.19 | 0 | 2022-09-26
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732001034/IF/22012035607493 — EK BAGIYA MA KE NAME DURGA LOWANSHI EK KHET ME CHOUTLAI | Approved | 0 | 0 | 2025-08-01
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/3787033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134848442 | Ongoing | 27000 | 0 | 2025-09-18
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/3787035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134848784 | Ongoing | 27000 | 16800 | 2025-09-25
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/3787037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134851354 | Ongoing | 27000 | 0 | 2025-09-18
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5154036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106279998 | Ongoing | 27000 | 0 | 2025-07-29
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5166362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119964881 | Ongoing | 27000 | 8400 | 2025-08-08
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5166829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134851908 | Ongoing | 27000 | 0 | 2025-07-29
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5167654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115937086 | Ongoing | 27000 | 0 | 2025-05-27
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5171537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105435337 | Completed | 23490 | 0 | 2025-04-15 | 2026-08-17
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5173167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134850441 | Ongoing | 27000 | 0 | 2025-04-29
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5179388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102343157 | Ongoing | 27000 | 0 | 2025-04-15
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5180015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102339912 | Completed | 23490 | 0 | 2025-07-08 | 2026-08-17
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5181940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121761540 | Ongoing | 27000 | 0 | 2025-04-29
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5184351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115937505 | Ongoing | 27000 | 0 | 2025-04-15
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5184662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102341970 | Ongoing | 27000 | 0 | 2025-05-27
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5186265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123746265 | Ongoing | 27000 | 0 | 2025-05-06
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5187896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134851504 | Ongoing | 27000 | 0 | 2025-08-26
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5196299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102340909 | Ongoing | 27000 | 0 | 2025-05-27
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5210255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123542511 | Ongoing | 27000 | 2100 | 2025-04-29
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5217695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134847716 | Ongoing | 27000 | 0 | 2025-07-29
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5221782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100887620 | Completed | 23490 | 0 | 2025-05-13 | 2026-08-20
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5223634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102341158 | Completed | 23490 | 0 | 2025-05-13 | 2026-08-20
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5227330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115937785 | Ongoing | 27000 | 0 | 2025-05-27
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5241983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106280308 | Ongoing | 27000 | 0 | 2025-05-27
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5243286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102340387 | Ongoing | 27000 | 0 | 2025-05-27
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5439777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123745771 | Completed | 23490 | 0 | 2025-07-29 | 2026-08-19
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5444232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134845176 | Ongoing | 27000 | 0 | 2025-07-29
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5444233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134845580 | Ongoing | 27000 | 0 | 2025-08-08
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5445198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134850816 | Ongoing | 27000 | 0 | 2025-07-29
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5445791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120929611 | Ongoing | 27000 | 0 | 2025-09-24
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5445829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134849898 | Ongoing | 27000 | 0 | 2025-07-15
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5446885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116136745 | Ongoing | 27000 | 0 | 2025-08-08
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5446886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116136786 | Ongoing | 27000 | 0 | 2025-07-08
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5448048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119964211 | Completed | 23490 | 0 | 2025-09-18 | 2026-08-20
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5478093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116942213 | Ongoing | 27000 | 0 | 2025-07-08
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5478216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115937267 | Ongoing | 27000 | 0 | 2025-07-29
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5478677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106279907 | Completed | 23490 | 0 | 2025-07-08 | 2026-08-20
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5480139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113501806 | Ongoing | 27000 | 0 | 2025-07-08
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5606988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134851622 | Ongoing | 27000 | 0 | 2025-08-08
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5607054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120929447 | Ongoing | 27000 | 0 | 2025-08-26
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5607117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119963148 | Ongoing | 27000 | 0 | 2025-09-25
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5607212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123746720 | Ongoing | 27000 | 0 | 2025-08-05
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5607310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102343105 | Ongoing | 27000 | 0 | 2025-07-29
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5661199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113511042 | Ongoing | 27000 | 14700 | 2025-09-25
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5661314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120930971 | Ongoing | 27000 | 0 | 2025-09-18
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5662035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102342116 | Ongoing | 27000 | 2100 | 2025-09-18
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5662634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134848248 | Ongoing | 27000 | 0 | 2025-09-25
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5691718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100887669 | Ongoing | 27000 | 0 | 2025-09-25
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5692071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134852796 | Ongoing | 27000 | 0 | 2025-09-25
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5812972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134847880 | Approved | 27000 | 0 | 2024-10-21
NARMADAPURAM / SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5866365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102340031 | Ongoing | 27000 | 8400 | 2026-04-22
NARMADAPURAM / SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5866386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115937228 | Ongoing | 27000 | 6300 | 2026-04-22
NARMADAPURAM / SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5866415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106279437 | Ongoing | 27000 | 12600 | 2026-04-22
NARMADAPURAM / SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5906599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123745267 | Ongoing | 27000 | 0 | 2026-05-04
NARMADAPURAM / SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5907232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134847090 | Ongoing | 27000 | 0 | 2026-05-04
NARMADAPURAM / SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5914461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120927795 | Ongoing | 27000 | 0 | 2026-04-22
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5919997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134851760 | Approved | 27000 | 0 | 2025-03-06
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5922329 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134852492 | Approved | 27000 | 0 | 2025-07-07
NARMADAPURAM / SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001034/IF/IAY/5924051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123540123 | Ongoing | 27000 | 0 | 2026-04-22
NARMADAPURAM / SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1732001034/RS/22012035135145 — बस स्टैंड के पास महिला एवं पुरुष पेशाब घर | Ongoing | 22411 | 0 | 2025-01-14
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-fields-Comm / Block Plantation of Biodrainage Trees in fields for Community | Plantation | 1732001034/WC/22012035206059 — braksharopan karya shakti mata talab and divider par | Ongoing | 453563.17 | 0 | 2024-06-24
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732001034/WH/22012034942895 — तालाब जीर्णोद्धारकार्य शक्ति माता मंदिर के पास चौतालय | New | 0 | 0 | 2024-10-02
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732001034/WH/22012034942896 — तालाब जीर्णोद्धारकार्य शक्ति माता मंदिर के पास चौतालय | New | 0 | 0 | 2024-10-02
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732001034/WH/22012034942899 — तालाब जीर्णोद्धारकार्य शक्ति माता मंदिर के पास चौतालय | New | 0 | 0 | 2024-10-02
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732001034/WH/22012034942900 — तालाब जीर्णोद्धारकार्य शक्ति माता मंदिर के पास चौतालय | New | 0 | 0 | 2024-10-02
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732001034/WH/22012034942901 — Ghujuu | New | 0 | 0 | 2024-10-01
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732001034/WH/22012034942917 — talab jinuddhar karya choutlay | New | 0 | 0 | 2024-10-02
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732001034/WH/22012034942918 — talab jinuddhar karya choutlay | New | 0 | 0 | 2024-10-02
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732001034/WH/22012034942920 — talan jinuddhar karya | New | 0 | 0 | 2025-01-05
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732001034/WH/22012034943095 — talab jinudhar karya choutlay | New | 0 | 0 | 2024-10-02