## Work List
Exported on: 2026-10-09 00:59:04
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SATAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1732001049/DP/22012034596583 — BASUDHA VANDAN AMRIT VATIKA E KAKCCH PARISAR SANTAI | Ongoing | 55847.4 | 0 | 2023-08-15
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1732001049/IF/22012035301455 — KAPILDHARA KUP NIRMAN KAARY KISHORI / IMRAT GRAM MORIYA GP SATAI | Ongoing | 318228.64 | 0 | 2025-02-28
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1732001049/IF/22012035320309 — KAPILDHARA KUP NIRMAN KAARY AMAR SINGH /DHANNU GRAM MORIYA GP SATAI | New | 0 | 0 | 2025-04-01
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1732001049/IF/22012035562981 — kapildhara koop recharge bajulla /puniya gangiya satai | Approved | 0 | 0 | 2025-04-14
NARMADAPURAM / SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/37673 — Construction of IAY House -IAY REG. NO. MP-32-001-049-001/02 | Approved | 27000 | 0 | 2015-11-17
NARMADAPURAM / SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/37674 — Construction of IAY House -IAY REG. NO. MP-32-001-049-001/08 | Approved | 27000 | 0 | 2015-11-17
NARMADAPURAM / SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/37676 — Construction of IAY House -IAY REG. NO. MP-32-001-049-003/6 | Approved | 27000 | 0 | 2015-11-17
NARMADAPURAM / SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/37677 — Construction of IAY House -IAY REG. NO. MP-32-001-049-001/002 | Approved | 27000 | 0 | 2015-11-17
NARMADAPURAM / SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/46610 — Construction of IAY House -IAY REG. NO. MP-32-001-049-001/24479217 | Approved | 27000 | 0 | 2015-12-02
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/4664712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150535663 | Completed | 23490 | 0 | 2024-10-18 | 2026-08-21
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/4664724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150538273 | Completed | 23490 | 0 | 2024-10-18 | 2026-08-21
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/4665562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150558985 | Ongoing | 27000 | 0 | 2024-11-22
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/4665569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150561098 | Completed | 23490 | 0 | 2024-10-18 | 2026-08-21
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/4873442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150542785 | Ongoing | 27000 | 0 | 2025-03-07
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/5106803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150535644 | Ongoing | 27000 | 0 | 2025-03-21
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/5112508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145653411 | Approved | 27000 | 0 | 2025-03-01
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/5115754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150555343 | Ongoing | 27000 | 0 | 2025-03-21
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/5115755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150559026 | Ongoing | 27000 | 0 | 2025-03-21
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/5116776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100851782 | Ongoing | 27000 | 0 | 2025-03-21
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/5131745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146413067 | Ongoing | 27000 | 0 | 2025-03-21
NARMADAPURAM / SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/5724316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145653397 | Ongoing | 27000 | 6300 | 2026-09-01
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/5727580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146124130 | Approved | 27000 | 0 | 2025-03-01
NARMADAPURAM / SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001049/IF/IAY/5812962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150535621 | Ongoing | 27000 | 12900 | 2026-08-10
NARMADAPURAM / SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001049/RC/22012034505994 — C.C.ROAD EVAM NALI NIRMAN NARMADA KE GHAR SE RAMGOPAL KE GHAR KI OR SANTAI | Ongoing | 66100 | 0 | 2019-11-28
NARMADAPURAM / SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001049/RC/22012034836399 — CC ROAD EVAM NALI NIRMAN KAARY MEN ROAD SE MADHYAMIK SHALA MATDAN KENDR KI AUR | Ongoing | 61724 | 0 | 2025-02-18
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001049/RC/22012034847160 — CC ROAD NIRMAN MOHAN KE GHAR SE VIJAY KE GHAR KI AUR SATAI GP SATAI | Ongoing | 102610 | 0 | 2025-10-30
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001049/RC/22012034847161 — CC ROAD NIRMAN RAMSHANKAR KE GHAR SE DHANSINGH KE GHAR KI AUR SATAI | Approved | 51305 | 0 | 2025-04-14
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001049/RC/22012034847942 — CC ROAD NIRMAN KISHOR KE GHAR SE DONO KI AUR GRAM SANTAI GP SANTAI | Ongoing | 61566 | 0 | 2025-09-18
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001049/RC/22012034852619 — CC ROAD NIRMAN RAMSHANKAR KE GHAR SE DHANSINGH KE GHAR KI AUR SANTAI | Approved | 51305 | 0 | 2025-04-24
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001049/RC/22012034852620 — CC ROAD NIRMAN SUNIL KE GHAR SE RAMPRASHAD KE GHAR KI AUR SANATAI | Approved | 76950 | 0 | 2025-04-24
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001049/RC/22012034853070 — CC ROAD NIRMAN SUNIL KE GHAR SE RAMPRASHAD KE GHAR KI AUR SATAI | Approved | 76950 | 0 | 2025-04-14
NARMADAPURAM / SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732001049/RS/22012035133960 — RCC NALI NIRMAN WORK MAHESH KE GHAR SE DEVI SINGH KE GHAR KI OR SANTAI | Approved | 53995 | 0 | 2024-08-16