## Work List
Exported on: 2026-10-07 19:10:43
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: VATKIURF IKALANI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1732001067/AV/22012034390740 — anganbadi nirman kary batki | Ongoing | 180000 | 0 | 2018-10-01
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1732001067/AV/22012034597356 — Boundary wall nirman high school parisar iklani gram panchayat vatkiurfiklani 230 miter | Ongoing | 844061.3 | 0 | 2021-11-03
NARMADAPURAM / SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1732001067/DP/22012034558079 — अमृत सरोवर बंड पर प्लांटेशन कार्य बटकी इकलानी | Ongoing | 411218.19 | 0 | 2023-10-06
NARMADAPURAM / SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line-coast Plntation-Farm Forstry Trees-Individual / Line Plantation of Forestry Trees for Individual | Plantation | 1732001067/IF/22012034842619 — CTR NANDAN FALOUDYAN RAMKISHAN BATKI GP VATKI URFIKLANI | Ongoing | 117912.51 | 0 | 2021-08-27
NARMADAPURAM / SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Line Plantation of Forestry Trees for Individual | Plantation | 1732001067/IF/22012034842625 — CTR NANDAN FALOUTHAYAN VISANIYA BAI / IMRAT LAL BATKI GP VATKI URFIKLANI | Ongoing | 117912.51 | 0 | 2021-08-27
NARMADAPURAM / SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1732001067/IF/22012034961398 — koop nirman guldar babu lal iklani | Ongoing | 275502.52 | 0 | 2024-03-15
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732001067/IF/22012035349413 — khet talab sukhram /bhangu | Approved | 0 | 0 | 2025-04-14
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732001067/IF/22012035383918 — khet talab ramdas /sukhram | New | 0 | 0 | 2025-04-14
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/4665065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151031432 | Completed | 23490 | 0 | 2024-12-20 | 2026-08-19
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/4985395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105292553 | Completed | 23490 | 0 | 2025-03-19 | 2026-08-19
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/4985398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105293013 | Completed | 23490 | 0 | 2025-03-19 | 2026-07-30
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/4987110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103129098 | Completed | 23490 | 0 | 2025-03-19 | 2026-08-19
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/4987113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103129320 | Ongoing | 27000 | 4200 | 2025-03-19
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/4988264 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105539320 | Ongoing | 27000 | 0 | 2025-03-19
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/4988265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105539480 | Completed | 23490 | 0 | 2025-03-19 | 2026-08-19
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/4988267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105539583 | Ongoing | 27000 | 0 | 2025-03-19
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/4988268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105539669 | Completed | 23490 | 0 | 2025-03-19 | 2026-08-19
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/4988270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105540057 | Completed | 23490 | 0 | 2025-03-19 | 2026-08-19
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/4988271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105540340 | Ongoing | 27000 | 4800 | 2025-03-19
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/4988297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105548682 | Completed | 23490 | 0 | 2025-03-19 | 2026-08-19
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/4988298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105548800 | Ongoing | 27000 | 0 | 2025-03-19
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/4988302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105549149 | Ongoing | 27000 | 0 | 2025-08-01
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/4992755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113910746 | Completed | 23490 | 0 | 2025-08-01 | 2026-08-19
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/5113815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102248475 | Ongoing | 27000 | 0 | 2025-04-25
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/5117134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151032061 | Ongoing | 27000 | 0 | 2025-08-29
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/5472883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103416972 | Completed | 23490 | 0 | 2025-06-20 | 2026-08-19
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/5813065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105539858 | Ongoing | 27000 | 6300 | 2026-03-20
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/5853673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105549003 | Approved | 27000 | 0 | 2025-02-22
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/5853719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113927562 | Completed | 23490 | 0 | 2025-11-07 | 2026-08-19
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/5853739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151061045 | Ongoing | 27000 | 0 | 2025-11-07
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/5853741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105292798 | Ongoing | 27000 | 0 | 2025-11-07
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001067/IF/IAY/6246982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104916677 | Approved | 27000 | 0 | 2025-02-22
NARMADAPURAM / SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001067/RC/22012034582312 — सी सी रोड व् नाली निर्माण शिव चरण के घर से प्रेम सिंह के घर की और बटकी | Ongoing | 39333 | 0 | 2022-05-27
NARMADAPURAM / SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1732001067/RC/22012034681895 — c c chouk nirman mangal bhavan ke pass iklani | Ongoing | 59918 | 0 | 2024-03-15
NARMADAPURAM / SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Road for Community | Construction of Road and Culvert | 1732001067/RC/22012034681908 — c c road makhan lal ke ghar se ramvilash ke ghar ki or batki | Ongoing | 60726 | 0 | 2024-03-15
NARMADAPURAM / SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732001067/RS/22012034524665 — CTR SOKTA GADDA ANGANBADIKE PASS SCHOOL ME BADI ME V.N 9 OR 10 GP VATKIURFIKLANI | Ongoing | 94672.22 | 0 | 2021-06-18
NARMADAPURAM / SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Bio-drainage Plantation for Community | Plantation | 1732001067/WC/22012034812762 — CTR SAMUDAYIK BRAKCHA ROPAN SHANTI DHAM KE PASS GRAM PANCHAYAT VATKI URF IKLANI GRAM IKLANI | Ongoing | 394489.84 | 0 | 2021-08-28
NARMADAPURAM / SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-fields-Comm / Bio-drainage Plantation for Community | Plantation | 1732001067/WC/22012034824292 — CTR SAMUDAYIK BLOCK PLANTESION PANCHAYAT BHAVAN MANGAL BHAVAN OR ANGANBADI SCHOOL GP VATKIIKLANI | Ongoing | 175559.5 | 0 | 2021-09-17
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001067/WC/22012035203783 — talab gahri karan iklani | Approved | 0 | 0 | 2024-06-10
NARMADAPURAM / SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1732001067/WC/22012035222253 — hodi nirman vatki | Approved | 14748 | 0 | 2024-08-16