## Work List
Exported on: 2026-10-07 03:49:16
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JIRAVEH
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen Shed for Government School for Community | Constr of Kitchen Shed | 1732001081/AV/22012034540019 — काम धेनु गौशाला निर्माण ग्राम पंचायत जीरावेह ग्राम डेठी | Completed | 3804449.17 | 0 | 2020-12-21 | 2026-08-27
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732001081/IF/22012035532878 — खेत तालाब निर्माण कार्य इमरत लाल कीर पिता भूरेलाल ग्राम डेठी ग्राम पंचायत जीरावेह | Approved | 0 | 0 | 2025-04-14
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732001081/IF/22012035588655 — एक बगिया माँ के नाम POOJA KAHAR GP JIRAVEH | Ongoing | 269386.03 | 0 | 2025-09-07
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732001081/IF/22012035607585 — EK BAGIYA MA KE NAME LALI BAI KEER / IMRAT LAL KEER KE KHET ME DETHI | New | 0 | 0 | 2025-08-01
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732001081/IF/22012035607587 — EK BAGIYA MA KE NAME LALI BAI KEER / IMRAT LAL KEER KE KHET ME DETHI | Approved | 0 | 0 | 2025-08-01
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732001081/IF/22012035607594 — EK BAGIYA MA KE NAME LALATA BAI KEER KE KHET ME DETHI | Ongoing | 269386.03 | 0 | 2025-09-07
NARMADAPURAM / SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732001081/IF/22012035607598 — EK BAGIYA MA KE NAME POOJA KAHAR KE KHET ME DETHI | New | 0 | 0 | 2025-08-01
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001081/IF/IAY/4664032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149769959 | Completed | 23490 | 0 | 2024-10-28 | 2026-08-20
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001081/IF/IAY/4668317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150912537 | Completed | 21870 | 0 | 2024-10-09 | 2026-08-20
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001081/IF/IAY/4914989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151274468 | Completed | 23490 | 0 | 2025-03-21 | 2026-08-20
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001081/IF/IAY/5118671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106743948 | Ongoing | 27000 | 0 | 2025-03-26
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001081/IF/IAY/5124610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125351403 | Completed | 23490 | 0 | 2025-03-20 | 2026-08-20
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001081/IF/IAY/5126067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150910122 | Completed | 23490 | 0 | 2025-03-20 | 2026-08-20
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001081/IF/IAY/5126108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106155974 | Completed | 23490 | 0 | 2025-03-20 | 2026-08-19
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001081/IF/IAY/5129160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149770012 | Completed | 23490 | 0 | 2025-03-20 | 2026-08-19
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001081/IF/IAY/5130473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151273805 | Completed | 23490 | 0 | 2025-03-20 | 2026-08-19
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001081/IF/IAY/5130474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151273954 | Ongoing | 27000 | 0 | 2025-03-26
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001081/IF/IAY/5131700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151280941 | Completed | 23490 | 0 | 2025-03-20 | 2026-08-20
NARMADAPURAM / SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001081/IF/IAY/6342289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151300510 | Approved | 27000 | 0 | 2025-02-13
NARMADAPURAM / SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034825983 — सी सी रोड निर्माण महेश के घर से ओमप्रकाश के खले कि और ग्राम जीरावेह | Ongoing | 36480 | 0 | 2024-12-30
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034849539 — सी सी रोड निर्माण मानु पटेल के घर से बजरंग मंदिर कि और ग्राम जीरावेह | Approved | 50381 | 0 | 2025-04-14
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034849868 — सी सी रोड कि साइड पट्टी निर्माण मानु पटेल के घर से बजरंग मंदिर कि और ग्राम जीरावेह | Ongoing | 50381 | 8050.85 | 2026-02-16
NARMADAPURAM / SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034851604 — सी सी रोड निर्माण चंदू के घर से गुलाब के घर कि और ग्राम डेठी | Ongoing | 30228 | 0 | 2026-02-02