## Work List
Exported on: 2026-10-12 10:03:10
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: RANIPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / KESLA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732002019/AV/22012034401183 — आगन बाड़ी भवन घोघरनाला तवानगर | Completed | 180000 | 177522 | 2019-03-11 | 2024-11-08
NARMADAPURAM / KESLA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732002019/AV/22012034467502 — बाउंडीबांल निर्माण कार्य शासकीय हायर सेकडरी स्कूल तवानगर | Completed | 152226 | 148168 | 2019-08-21 | 2020-06-09
NARMADAPURAM / KESLA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732002019/AV/22012034513382 — पक्की बाउंड्रीबाल निर्माण कार्य -प्राथमिक शाला रानीपुर भवन तवानगर | Completed | 385572 | 386819.96 | 2020-07-27 | 2021-03-31
NARMADAPURAM / KESLA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732002019/AV/22012034552402 — पक्की बाउंड्रीवाल निर्माण कार्य बालक मा. शाला तवानगर :-160 मीटर | Completed | 157373 | 155960.28 | 2021-03-26 | 2024-09-23
NARMADAPURAM / KESLA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1732002019/AV/22012034575391 — डाइनिंग बेंच और टेबल निर्माण - प्राथमिक शाला रानीपुर | Completed | 16093.2 | 12237 | 2021-07-07 | 2023-07-05
NARMADAPURAM / KESLA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & Maint of Food grain storage building / Repair and Maintenance of Food grain Storage Building for Community | Repair & Maint of Community infrastructure | 1732002019/AV/22012034575392 — डाइनिंग बेंच और टेबल निर्माण - शासकीय कन्या माध्यमिक शाला तवानगर [ भाग 1] | Closed | 16093.2 | 0 | 2021-04-14
NARMADAPURAM / KESLA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1732002019/AV/22012034575394 — डाइनिंग बेंच और टेबल निर्माण -शासकीय कन्या माध्यमिक शाला तवानगर [ भाग 2]] | Closed | 16093.2 | 0 | 2021-04-14
NARMADAPURAM / KESLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1732002019/DP/22012034534017 — Nutrition garden gov. girls m. school tawanagar | Ongoing | 16976.64 | 9044 | 2021-11-25
NARMADAPURAM / KESLA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Avenue Plantation for Community | Plantation | 1732002019/DP/22012034586903 — amrat vatika karya:- mangal bhawan me | Ongoing | 55847.4 | 11130.06 | 2023-09-05
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88209 — निर्मल वाटिका तुलसीया/रामचरन | Completed | 3568 | 2376 | 2012-03-05 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88210 — निर्मल वाटिका कविता/सीताराम | Completed | 3568 | 2376 | 2012-03-05 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88211 — निर्मल वाटिका सन्‍तराम/गुलाब | Completed | 3568 | 2376 | 2012-03-05 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88212 — निर्मल वाटिका रामचन्‍द्र/पाण्‍डू | Completed | 3568 | 2374 | 2012-03-05 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88213 — निर्मल वाटिका नर्मदा/सुंदर | Completed | 3568 | 2374 | 2012-03-05 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88214 — निर्मल वाटिका रमेश/प्रभाकर | Completed | 3568 | 2376 | 2012-03-05 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88215 — निर्मल वाटिका कौशल्‍या/जयराम | Completed | 3568 | 2376 | 2012-03-05 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88216 — निर्मल वाटिका लीला/नन्‍हेलाल | Completed | 3568 | 2376 | 2012-03-05 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88217 — निर्मल वाटिका बाबूलाल/रामसुमेर | Completed | 3568 | 2374 | 2012-02-27 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88218 — निर्मल वाटिका सुरेश/कोमलसिंह | Completed | 3568 | 2374 | 2012-02-27 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88219 — निर्मल वाटिका रमेश/मोतीलाल | Completed | 3568 | 2374 | 2012-02-27 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88220 — निर्मल वाटिका यशवन्‍त/गुंलाब | Completed | 3568 | 2374 | 2012-03-05 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88221 — निर्मल वाटिका सुरेश/कोमल | Completed | 3568 | 2374 | 2012-02-27 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88222 — निर्मल वाटिका रेना/भीकमसिंह | Completed | 3568 | 2374 | 2012-02-27 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88223 — निर्मल वाटिका तारासिंह/दशरथ | Completed | 3568 | 2374 | 2012-02-27 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88224 — निर्मल वाटिका अशोक/इमरतलाल | Completed | 3568 | 2374 | 2012-02-27 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88225 — निर्मल वाटिका बेला/मेहताब | Completed | 3568 | 2374 | 2012-02-27 | 2012-03-22
NARMADAPURAM / KESLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1732002019/DP/88226 — निर्मल वाटिका भानदास/पण्‍डरी | Completed | 3568 | 2376 | 2012-02-27 | 2012-03-22
NARMADAPURAM / KESLA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732002019/IF/22012034342096 — rode side plantation- santi dham ke pas ranipur tawanagar -durgabai / kadan | Completed | 335000 | 35230 | 2017-05-22 | 2021-03-31
NARMADAPURAM / KESLA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732002019/IF/22012034342098 — vraksha ropan - road side plantation -market se police thana ki or -deenanath/kasdan | Completed | 335000 | 34744 | 2017-05-22 | 2021-03-31
NARMADAPURAM / KESLA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732002019/IF/22012034346674 — block plantation- bad maidan tawanagar- virendra/sanilal dhurve | Completed | 534460 | 34888 | 2017-06-05 | 2021-03-31
NARMADAPURAM / KESLA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732002019/IF/22012034346693 — road side plantation- high school tawanagar-Arjun/ramesh kumre | Completed | 335000 | 18180 | 2017-06-05 | 2021-03-31
NARMADAPURAM / KESLA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732002019/IF/22012034351740 — block plantation-madal school tawanagar-mahesh/shriram gulwake | Completed | 534460 | 19516 | 2017-06-19 | 2021-03-06
NARMADAPURAM / KESLA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732002019/IF/22012034351965 — road side plantation-madal chatrawas tawanagar-deepak/ramesh dongre | Completed | 335000 | 16416 | 2017-06-19 | 2021-03-06
NARMADAPURAM / KESLA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732002019/IF/22012034357867 — ROAD SIDE PLANTATION-TRANSFARMER SE MENAN HOTEL KI OR-JITENDRA/MOTISINGH RAJPUT | Completed | 335000 | 26632 | 2017-06-28 | 2021-03-31
NARMADAPURAM / KESLA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732002019/IF/22012034358599 — road side plantation - primary school ranipur se hospital ki or- vishal /nitish viswas | Closed | 335000 | 0 | 2017-06-29
NARMADAPURAM / KESLA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Compost Pit for Individual / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1732002019/IF/22012034896816 — individual soak pit-construction mahesh,tikaram,narmada,haricharan,tulsiram-5 num. | Physically Completed | 24680.1 | 19406.44 | 2022-05-17 | 2026-04-24
NARMADAPURAM / KESLA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1732002019/IF/22012034917873 — individual soak pit-construction kishor,sukharam,lakhan,puniya,gappu-5 num. | Physically Completed | 24680.1 | 19610.44 | 2022-05-17 | 2026-04-24
NARMADAPURAM / KESLA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1732002019/IF/22012035029691 — individual soak pit-construction madan,damodar,monu,moti,balkisan,mishri,laxmi,sasikala,kamles,guddu | Physically Completed | 51143.75 | 38359.95 | 2022-11-15 | 2026-04-24
NARMADAPURAM / KESLA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Compost Pit for Individual / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1732002019/IF/22012035035364 — individual soak pit-construction sajjan,santosh kahar,prempal,sharvan,ramdayal lavaskar | Closed | 29468.44 | 0 | 2023-01-31
NARMADAPURAM / KESLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732002019/IF/22012035572994 — Agri horti plantation for benificiary | Approved | 0 | 0 | 2025-04-01
NARMADAPURAM / KESLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732002019/IF/22012035573606 — नंदन फलोद्वान | Approved | 0 | 0 | 2025-04-01
NARMADAPURAM / KESLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732002019/IF/22012035573910 — नंदन फलोद्वान १०० पौधे | Approved | 0 | 0 | 2025-04-01
NARMADAPURAM / KESLA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732002019/IF/IAY/1662871 — Construction of IAY House -IAY REG. NO. MP2030003 | Closed | 17100 | 0 | 2018-04-08
NARMADAPURAM / KESLA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732002019/IF/IAY/867836 — Construction of IAY House -IAY REG. NO. MP1705299 | Approved | 27000 | 0 | 2017-04-01
NARMADAPURAM / KESLA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1732002019/LD/22012034227175 — शांति धाम रानीपुर् | Completed | 364543 | 135132.52 | 2015-06-29 | 2018-11-12
NARMADAPURAM / KESLA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034168278 — सीसीरोड व नाली मेन रोड से पीपल के पेड की ओर | Completed | 129947 | 128316 | 2013-06-03 | 2013-10-28
NARMADAPURAM / KESLA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034181627 — सीसीरोड व नाली मुन्‍नाखां के घर से साहू चक्‍की की | Completed | 155931 | 109691.9 | 2013-09-16 | 2014-01-30
NARMADAPURAM / KESLA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034199730 — सीसीरोड व नाली गोंडी मोहल्‍ला मेन रोड से बटटीबाई क | Completed | 128864 | 123730.17 | 2014-01-20 | 2014-06-30
NARMADAPURAM / KESLA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034289461 — सीसीरोड मेन रोड से रीता ठाकुर के घर की ओर | Completed | 109029 | 89517 | 2015-11-23 | 2016-08-16
NARMADAPURAM / KESLA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034289468 — सी.सी.रोड निर्माण मेन रोड से उदय के घर की ओर | Completed | 109029 | 103191 | 2015-12-14 | 2016-08-16
NARMADAPURAM / KESLA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034297610 — सी.सी.रोड नाली निर्माण्‍ केनाल गेट से 15 चेन गेट की ओर | Completed | 66683 | 49572 | 2016-02-01 | 2016-08-16
NARMADAPURAM / KESLA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034306952 — सी.सी.रोड़ एवम् नाली निर्माण मेन रोड़ से संदीप सराठे के घर की ओर | Deleted | 0 | 0 | 2016-01-26
NARMADAPURAM / KESLA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034306963 — सी.सी.रोड़ एवम् नाली निर्माण मेन रोड़ से पप्पू लोहार के घर की ओर | Deleted | 0 | 0 | 2016-01-26
NARMADAPURAM / KESLA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034306966 — सी.सी.रोड मेन रोड से सोनू के घर की ओर | Deleted | 0 | 0 | 2016-01-26
NARMADAPURAM / KESLA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034306972 — सी.सी.रोड़ निर्माण मेन रोड़ से सोनू के घर की ओर | Deleted | 0 | 0 | 2016-01-26
NARMADAPURAM / KESLA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034316637 — सी सी रोड नाली निर्माण वार्ड क्रमांक 2 में मेन रोड से मधु वेंडर के घर की ओर | Completed | 177530 | 173256.1 | 2016-11-28 | 2017-08-02
NARMADAPURAM / KESLA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034322111 — CC ROAD & NALI NIRMAN | Closed | 0 | 0 | 2017-01-26
NARMADAPURAM / KESLA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034322666 — नहर से पवन के घर तक | Closed | 0 | 0 | 2017-01-26
NARMADAPURAM / KESLA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034324413 — सी.सी.रोड एवं नाली निर्माण्‍ा मेन रोड से कमल के घर तक | Completed | 1268000 | 183211.01 | 2017-02-06 | 2018-07-02
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034349062 — सी. सी. रोड नाली निर्माण काली कमला के घर से काशीनाथ के घर तक | Completed | 475500 | 68160 | 2017-08-14 | 2018-07-26
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034349064 — सी. सी. रोड निर्माण मंगल भवन के पास से जायसवाल के घर तक | Completed | 634000 | 16680 | 2017-08-23 | 2019-05-13
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034360444 — सी.सी. रोड एवं नाली निर्माण मेन रोड से बजरंग मंदिर तक | Completed | 317000 | 35088 | 2017-09-18 | 2018-07-02
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034362861 — सी.सी.रोड नाली निर्माण मेन रोड से साहू वकील के घर की ओर | Completed | 634000 | 77128 | 2017-10-09 | 2018-07-02
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034373684 — cc road nirman | Closed | 0 | 0 | 2017-08-15
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034375248 — c.c, road or nali nirma gulwake | Closed | 0 | 0 | 2017-05-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034375257 — c.c.road or nali nirman post office ke pas se madhu bendar ke ghar tak | Closed | 0 | 0 | 2017-05-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034375262 — c.c.road nali nirman manish ke ghar se rajesh tak ke ghar tak | Closed | 0 | 0 | 2017-08-15
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034375278 — c.c. road nali nirman matan market se kahar mohlla tak | Closed | 0 | 0 | 2017-08-15
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034375280 — c.c. road nali nirman kevli kuddi ke ghar se deepak katare ke ghar tak | Closed | 0 | 0 | 2017-05-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034375286 — men road se makhan pandit ke ghar ki or | Closed | 0 | 0 | 2017-08-15
NARMADAPURAM / KESLA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034442692 — CC Road nirman | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / KESLA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of WBM Roads for Community / Construction of WBM Roads for Community | Construction of Road and Culvert | 1732002019/RC/22012034442948 — सी.सी. निर्माण बबीता के घर से रूपेश के घर तक | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / KESLA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034513853 — सी.सी. रोड व दोनों तरफ नाली निर्माण कार्य मेन रोड से बसंत साहू के घर की ओर | Closed | 199200 | 0 | 2019-04-14
NARMADAPURAM / KESLA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034516461 — c.c.road nali nirman noori bhaijan ke ghar se bindu ke ghar tak | Closed | 0 | 0 | 2019-08-15
NARMADAPURAM / KESLA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034516462 — c.c.road nirman post office ke pas se madhu beldar ke ghar tak | Closed | 0 | 0 | 2019-08-15
NARMADAPURAM / KESLA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034516465 — c.c.road nali nirman men road se sonu ke ghar tak | Closed | 0 | 0 | 2019-08-15
NARMADAPURAM / KESLA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034516468 — c.c.road nali nirman ambedkar park se bhura louhar ke ghar tak | Closed | 0 | 0 | 2019-08-15
NARMADAPURAM / KESLA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034562653 — सी. सी.निर्माण कमल लाइन मेन के घर से मधु बेल्डर के घर तक | Closed | 0 | 0 | 2020-10-02
NARMADAPURAM / KESLA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034598090 — सीसी रोड निर्माण कार्य - जनपद निधि सीसी रोड से नूरी भाईजान के घर की और तथा | Completed | 103658 | 97885 | 2021-12-06 | 2024-12-03
NARMADAPURAM / KESLA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034598099 — सीसी रोड व नाली निर्माण कार्य - मनीष साहू के घर से राजू पंडित के घर की ओर रानीपुर | Closed | 16878 | 0 | 2021-10-02
NARMADAPURAM / KESLA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1732002019/RC/22012034607655 — गोड़ी मोहल्ला से मत्सय तालाब की ओरजाने वाला मार्ग ग्रेवल मार्ग | Closed | 0 | 0 | 2022-01-24
NARMADAPURAM / KESLA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1732002019/RC/22012034607656 — गोड़ी मोहल्ला से मत्सय तालाब की ओरजाने वाला मार्ग ग्रेवल मार्ग | Closed | 0 | 0 | 2022-01-24
NARMADAPURAM / KESLA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034626077 — सी.सी.रोड निर्माण अंबेडकर पार्क से जगदीश राठौर के घर की ओर | Completed | 49725 | 48620 | 2023-07-18 | 2024-12-03
NARMADAPURAM / KESLA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034658165 — सी.सी.रोड निर्माण POST OFFICE से सक्सेना के घर तक | Ongoing | 55116 | 54357 | 2024-03-05
NARMADAPURAM / KESLA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034660571 — CC Nali Nirman Post Office se Saksena Ke Ghar Ki or | Ongoing | 50370 | 17695 | 2024-03-05
NARMADAPURAM / KESLA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034831131 — सी. सी.रोड निर्माण मेन रोड विनय बेलवंशी के घर की ओर | Physically Completed | 26891 | 26728.83 | 2025-01-07 | 2026-06-01
NARMADAPURAM / KESLA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034831138 — सी. सी.रोड निर्माण बलबीर के घर से प्रांशुल के घर की ओर | Ongoing | 59227 | 55647 | 2025-01-07
NARMADAPURAM / KESLA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034837504 — सी.सी. रोड निर्माण रामनाथ के घर से खिम्मू के घर की ओर | Ongoing | 28761 | 13042.08 | 2025-11-25
NARMADAPURAM / KESLA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732002019/RC/22012034837515 — सी.सी. रोड निर्माण राजू की दुकान से रामसिंह के घर की ओर | Ongoing | 42598 | 28917 | 2025-03-18
NARMADAPURAM / KESLA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/443 — अर्थवर्क एवं ग्रेवल कार्य मुरमीकरण | Completed | 494000 | 1449 | 2008-04-02 | 2023-07-19
NARMADAPURAM / KESLA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732002019/RC/78971 — डीआर कालोनी में सीसी रोड एवं नाली निर्माण | Completed | 150376 | 72432 | 2012-06-10 | 2012-08-28
NARMADAPURAM / KESLA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034252824 — iihl Ganesh sing to teekaram group 1 | Deleted | 54000 | 0 | 2014-04-01
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034361296 — sochalay nirman -munnalal /kaluram manjhi | Completed | 12000 | 10120 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034361481 — sochalay nirman nanakram /sankarlal manjhi | Completed | 12000 | 10464 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034361482 — sochalay nirman - ramesh / nanhelal kahar | Completed | 12000 | 10120 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034361483 — sochalay nirman - jayprakash /kanhaiyalal kahar | Completed | 12000 | 10120 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034361484 — sochalay nirman - raju /dularey yadav | Completed | 12000 | 10120 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034361487 — sochalay nirman -mahesh /nirpat kahar | Completed | 12000 | 10464 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034361488 — sochalay nirman- kishor/ gotulal kahar | Completed | 12000 | 10120 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034361489 — sochalay nirman -gappu /omkar kahar | Completed | 12000 | 10120 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034361490 — sochalay nirman - jayda bee/ israk kha | Completed | 12000 | 10120 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034361491 — sochalay nirman -sahebrao / isnaji mahge | Completed | 12000 | 9948 | 2017-08-10 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034363373 — sochalay nirman sukharam /emrat kahar | Completed | 12000 | 10120 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034363375 — sochalay nirman ramesh/benisingh kumre | Completed | 12000 | 1720 | 2017-08-07 | 2019-04-11
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034366951 — sochalay nirman - kanhaiya /chetu ivne | Completed | 12000 | 9948 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034367027 — sochalay nirman - jamnabai /parnu | Completed | 12000 | 9948 | 2017-08-10 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034367057 — sochalay nirman - mahesh /manaklal janoriya | Completed | 12000 | 9260 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034367062 — sochalay nirman - dhansingh / bhutalal | Completed | 12000 | 10292 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034367072 — sochalay nirman - dhanraj / bhutalal | Completed | 12000 | 10120 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034367074 — sochalay nirman - sarita /manoj | Completed | 12000 | 10980 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034367075 — sochalay nirman - ghasiram /setansingh | Completed | 12000 | 9948 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034367704 — sochalay nirman - sahabrao mahge | Deleted | 0 | 0 | 2017-05-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034367784 — sochalay nirman - gangaram /ramdayal kahar | Completed | 12000 | 9432 | 2017-08-07 | 2017-12-19
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034375833 — sochalay nirman jayram / babulal kahar | Closed | 100000 | 0 | 2017-09-25
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034376097 — sochalay nirman ashok /ramesh | Closed | 120000 | 0 | 2017-09-25
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034376098 — sochalay nirman jashok /ramesh | Closed | 0 | 0 | 2017-05-18
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034376101 — sochalay nirman - jabbar khan/bahhur khan | Closed | 12000 | 0 | 2017-09-25
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034376103 — sochalay nirman - isvariprasad / ramkhripal tiwari | Closed | 100000 | 0 | 2017-09-24
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034376104 — sochalay nirman - gulab singh / jiwan | Closed | 120000 | 0 | 2017-09-24
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034376173 — souchalay nirman udaysingh / dadesingh | Closed | 100000 | 0 | 2017-09-25
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034376176 — sochalay nirman sankarlal /channu | Closed | 100000 | 0 | 2017-09-25
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034376177 — sochalay nirman umesh/khudda parte | Closed | 100000 | 0 | 2017-09-25
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034376178 — sochalay nirman- manjulata /ramesh | Closed | 100000 | 0 | 2017-09-25
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034376180 — sochalay nirman jaswant /sukharam | Closed | 0 | 0 | 2017-06-18
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034376181 — sochalay nirman tilakwati /khudda | Closed | 100000 | 0 | 2017-09-25
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034376430 — sochalay nirman panjabrao/bhagulal | Closed | 72100 | 0 | 2017-09-25
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034376433 — sochalay nirman urmila/shivram | Closed | 100000 | 0 | 2017-09-25
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034376435 — sochalay nirman kalicharan/ imratlal | Closed | 100000 | 0 | 2017-09-25
NARMADAPURAM / KESLA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732002019/RS/22012034376436 — sochalay nirman haricharan/bhurelal | Closed | 100000 | 0 | 2017-09-25
NARMADAPURAM / KESLA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732002019/RS/22012034437496 — nadep nirman ward numbar 1 me | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / KESLA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732002019/RS/22012034437497 — nadep nirman ward numbar 2 me | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / KESLA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732002019/RS/22012034437498 — nadep nirman ward numbar 4 me | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / KESLA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732002019/RS/22012034437499 — nadep nirman pnb bank ke pas | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / KESLA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732002019/RS/22012034437500 — nadep nirman hospital ke samne | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / KESLA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732002019/RS/22012034442241 — पी.एन.बी बैंक के पास नाडेप निर्माण | Completed | 12284.01 | 11790 | 2020-07-13 | 2021-03-09
NARMADAPURAM / KESLA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732002019/RS/22012034442242 — सबजी मार्केट के पास नाडेप निर्माण | Closed | 0 | 0 | 2019-04-14
NARMADAPURAM / KESLA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732002019/RS/22012034442243 — सबजी मार्केट के पीछे नाडेप निर्माण | Completed | 12284.01 | 10812 | 2020-02-17 | 2021-03-09
NARMADAPURAM / KESLA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732002019/RS/22012034442322 — मछली मार्केट मे नाडेप निर्माण | Completed | 12284.01 | 11178 | 2020-02-17 | 2021-03-09
NARMADAPURAM / KESLA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732002019/RS/22012034442323 — मेन मार्केट के पीछे नाडेप निर्माण | Completed | 12284.01 | 10798 | 2020-02-17 | 2021-03-09
NARMADAPURAM / KESLA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732002019/RS/22012034442324 — संभू के घर के सामने नाडेप निर्माण | Completed | 12284.01 | 11220 | 2020-07-13 | 2021-03-09
NARMADAPURAM / KESLA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732002019/RS/22012034442325 — कहार मोहल्ला मे नाडेप निर्माण | Completed | 12284.01 | 11220 | 2020-07-13 | 2021-03-09
NARMADAPURAM / KESLA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1732002019/RS/22012034498732 — सामुदायिक स्वछता परिसर यात्री स्टैंड के पास रानीपुर | Completed | 43700 | 42940 | 2020-10-26 | 2021-03-06
NARMADAPURAM / KESLA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1732002019/RS/22012034509003 — सामुदायिक स्वछता परिसर सब्जी बाजार के पास | Completed | 72833 | 38340 | 2021-02-26 | 2022-12-07
NARMADAPURAM / KESLA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732002019/RS/22012034528104 — construction of segregation shed-ranipur-shanti dham ke pas | Completed | 299503.15 | 240188.88 | 2021-08-16 | 2025-02-21
NARMADAPURAM / KESLA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732002019/RS/22012034528121 — construction of community Nadep-ward no. 16 - hospital ke samne tawanagar | Completed | 12630.91 | 9213.91 | 2021-09-13 | 2024-12-03
NARMADAPURAM / KESLA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732002019/RS/22012034528139 — construction of community Nadep-ward no. 17- chandni chouk aaganbadi ke samne tawanagar | Completed | 12630.91 | 9203.15 | 2021-09-13 | 2024-12-03
NARMADAPURAM / KESLA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732002019/RS/22012034619922 — Nali nirman karya - manish sahu ke ghar se raju pandit ke ghar ki or ranipur | Completed | 16878 | 15944 | 2022-01-03 | 2022-12-07
NARMADAPURAM / KESLA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732002019/RS/22012034643968 — sauk pit | Closed | 0 | 0 | 2022-01-24
NARMADAPURAM / KESLA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732002019/RS/22012034643970 — sauk pit | Closed | 0 | 0 | 2022-01-24
NARMADAPURAM / KESLA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732002019/RS/22012034643973 — sauk pit | Closed | 0 | 0 | 2022-01-24
NARMADAPURAM / KESLA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732002019/RS/22012034685754 — नाली निर्माण अंबेडकर पार्क से जगदीश राठौर के घर की ओर | Completed | 15015 | 14607 | 2024-01-02 | 2025-02-21
NARMADAPURAM / KESLA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair & Maintenance of Storm Water Drain for Community | Solid and Liquid Waste Management | 1732002019/RS/22012034685755 — आर. सी .सी.नाली निर्माण दिलीप देशमुख के घर से तारों के घर तक | Ongoing | 30035 | 13506 | 2024-03-19
NARMADAPURAM / KESLA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732002019/RS/22012034685756 — आर. सी .सी.नाली निर्माण दिलीप देशमुख के घर से तारों के घर तक | Closed | 0 | 0 | 2022-10-02
NARMADAPURAM / KESLA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732002019/RS/22012035113648 — सी.सी.नाली निर्माण Post office से सक्सेना के घर की ओर | Closed | 0 | 0 | 2023-04-14
NARMADAPURAM / KESLA | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732002019/SK/576 — Bharat Nirman Rajeev Gandhi Sewa Kendra,RANIPUR | Completed | 118101 | 97951 | 2013-12-16 | 2015-09-30
NARMADAPURAM / KESLA | 2019-2020 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maintenance of Earthen Spur for Community / Repair and Maintenance of Earthen Spur for Community | Repair & maint of Water Harvesting Structures | 1732002019/WC/22012034463463 — नवीन पुलिया के पास नाले की गहरीकरण तथा गाली पिचिंग निर्माण | Closed | 0 | 0 | 2019-05-20
NARMADAPURAM / KESLA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732002019/WC/22012034548644 — बोल्डर चेक डेम निर्माण - पंजाब नेशनल बैंक के पीछे नाला पर | Completed | 25759.78 | 13010 | 2020-05-18 | 2025-02-21
NARMADAPURAM / KESLA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732002019/WC/22012034548648 — बोल्डर चेक डेम निर्माण -चपरासी लाइन के पास नाला पर | Completed | 18318.9 | 11400 | 2020-05-11 | 2023-09-19
NARMADAPURAM / KESLA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732002019/WC/22012034548650 — बोल्डर चेक डेम निर्माण- हाट बाजार के पास नाला पर | Completed | 22783.44 | 12540 | 2020-05-11 | 2023-09-19
NARMADAPURAM / KESLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732002019/WC/22012034649814 — CTR- WATER HARVESTING WORK:-BUILDING PANCHAYAT BHAWAN | Completed | 25173.14 | 19588.03 | 2021-08-16 | 2025-02-21
NARMADAPURAM / KESLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732002019/WC/22012034649837 — CTR- WATER HARVESTING WORK:-BUILDING H.S.SCHOOL TAWANAGAR BHAWAN | Completed | 25173.14 | 19136.04 | 2021-08-16 | 2025-02-21
NARMADAPURAM / KESLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732002019/WC/22012034660092 — sokhata gadda durga chouk kuaa ke pas | Closed | 0 | 0 | 2021-04-14
NARMADAPURAM / KESLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732002019/WC/22012034660118 — sokhata gadda kahar mohalla handpump ke pas | Closed | 0 | 0 | 2021-04-14
NARMADAPURAM / KESLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732002019/WC/22012034660121 — sokhata gadda kahar mohalla handpump ke pas | Closed | 0 | 0 | 2021-04-14
NARMADAPURAM / KESLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732002019/WC/22012034660170 — sokhata gadda parwati kahar ke ghar ke pas hand pump ke pas | Closed | 0 | 0 | 2021-04-14
NARMADAPURAM / KESLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732002019/WC/22012034660187 — sokhata gadda men market hand pump ke pas | Closed | 0 | 0 | 2021-04-14
NARMADAPURAM / KESLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732002019/WC/22012034670882 — CTR-RECHARGE PIT- Durga chouk kuaa ke pas | Completed | 14467.3 | 10392 | 2021-05-31 | 2022-12-21
NARMADAPURAM / KESLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732002019/WC/22012034670895 — CTR-CONSTRUCTION OF COMMUNITY RECHARGR PIT-Kahar mohalla handpump ke pas | Completed | 14467.3 | 10422 | 2021-05-24 | 2022-12-21
NARMADAPURAM / KESLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732002019/WC/22012034670902 — CTR-CONSTRUCTION OF COMMUNITY RECHARG PIT- parwati kahar ke ghar ke pas hand pump par | Closed | 0 | 0 | 2021-04-14
NARMADAPURAM / KESLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732002019/WC/22012034670904 — CTR-CONSTRUCTION OF COMMUNITY RECHARG PIT- parwati kahar ke ghar ke pas hand pump par | Completed | 14467.3 | 13099 | 2021-05-24 | 2024-01-03
NARMADAPURAM / KESLA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732002019/WC/22012035092779 — individual soak pit-sajjan,santosh,prempal,sarvan,ramdayal | Physically Completed | 48457.45 | 41852.62 | 2024-03-06 | 2026-04-04
NARMADAPURAM / KESLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732002019/WC/22012035282618 — dugwell recharge structure post office ke pas kuaa | Physically Completed | 25899.46 | 20462 | 2025-05-06 | 2026-03-26
NARMADAPURAM / KESLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732002019/WC/22012035283143 — dugwell recharge structure deena nath ke ghar ke piche kuaa par | Physically Completed | 25899.46 | 17591 | 2025-05-06 | 2026-03-26
NARMADAPURAM / KESLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732002019/WC/22012035312298 — dugwell recharge structure new coloney kuaa par | Physically Completed | 25899.46 | 24116.01 | 2025-06-10 | 2026-03-26
NARMADAPURAM / KESLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732002019/WC/22012035312616 — dugwell recharge structure sukhram ke ghar ke pas | Physically Completed | 25899.46 | 25406.11 | 2025-06-10 | 2026-03-26
NARMADAPURAM / KESLA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732002019/WC/तवानगर /21/67 — शोकफिट निर्माण कार्य रानीपुर | Completed | 11470 | 18887 | 2008-05-23 | 2008-08-06