## Work List
Exported on: 2026-10-11 12:40:49
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: DAMDAM
Status: Physically Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003014/IF/IAY/3653760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150091621 | Physically Completed | 23490 | 18225 | 2024-11-07 | 2025-07-19
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003014/IF/IAY/5003743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118222035 | Physically Completed | 23490 | 23103 | 2025-03-20 | 2026-03-03
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003014/IF/IAY/5009220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121952870 | Physically Completed | 23490 | 23418 | 2025-03-27 | 2025-12-16
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003014/IF/IAY/5106117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150113574 | Physically Completed | 23490 | 23418 | 2025-03-27 | 2026-02-24
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003014/IF/IAY/5114972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119838877 | Physically Completed | 23490 | 23229 | 2025-04-10 | 2026-04-12
NARMADAPURAM / HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003014/RC/22012034544281 — DAMDAM CHANDRABHAN CHOUREY KE GHAR SE RAMSWARUP CHOUREY KI GHAR KI AUR NALI NIRMAN | Physically Completed | 3475 | 3230 | 2020-10-17 | 2021-09-13
NARMADAPURAM / HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003014/RC/22012034546280 — DAMDAM VIJAY PATEL KE GHAR SE LAKHAN MALVIYA KE GHAR TAK C C NALI NIRMAN | Physically Completed | 14594 | 13680 | 2020-12-12 | 2021-09-13