## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732003015/AV/22012034462830 — SONASAWARI SCHOOL PARISAR ME BAUNDIWALL NIRMAN | Completed | 374000 | 145064 | 2019-07-29 - 2020-03-24
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Rpair & maint of brick/stone Kharanja Roads - Comm / Repair and maintenance of Kharanja (brick/stone) Roads for Community | Repair & Maint of Community infrastructure | 1732003015/AV/22012034466006 — yyhgjuhklij | Deleted | 0 | 0 | 2019-06-22 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732003015/AV/22012034504914 — SONASAWARI SAMUDAYIK BHAVAN NIRMAN | Completed | 400000 | 249851 | 2020-01-06 - 2026-04-27
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732003015/AV/22012034504915 — SONASAWARI YATRI PRATIKSHALAY NIRMAN IATARSI SAKET TIRAHE PAR | Completed | 100000 | 99238.1 | 2019-12-20 - 2020-12-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732003015/AV/22012034508693 — SONASWARI ME 14 DUKAN NIRMAN (PART A+B+C) | Physically Completed | 151722 | 44080 | 2020-07-13 - 2021-02-28
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair and maintenance of GP building / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1732003015/AV/22012034567184 — MOW aaganwadi bhawan 02 | Completed | 45570 | 45421 | 2021-06-11 - 2022-05-23
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732003015/AV/22012034657311 — Shala Parisar me Boundary wall nirman kary | New | 0 | 0 | 2024-06-08 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732003015/AV/22012034657313 — Shala Parisar me Boundary wall nirman kary | Approved | 73586 | 0 | 2024-06-08 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732003015/DP/22012034432886 — sarvajanik sthan par phoudhropan gram sonasawari | Physically Completed | 543860 | 31940 | 2018-11-05 - 2021-02-28
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1732003015/DP/22012034537501 — CTR-Plantation middle school sonsaver | Ongoing | 394489.84 | 91710 | 2021-09-24 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732003015/DP/22012034595305 — Sonasanwari - Vasudha Vandan - Amrit Vatika - School Parisar me | Ongoing | 55847.4 | 15646 | 2023-08-09 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003015/IF/22012034348272 — SALA PARISAR ME PHOUDROPAN GRAM SONASAWARI | Completed | 335000 | 37492 | 2017-06-18 - 2018-11-13
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003015/IF/22012034350841 — Sonasawari me nadi kinare bansh ropan | Completed | 335000 | 37492 | 2017-06-18 - 2018-11-13
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003015/IF/22012034352846 — Sonasawari me nadi kinare bansh ropan 02 | Completed | 335000 | 35428 | 2017-06-19 - 2018-11-13
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003015/IF/22012034358474 — PLANTION ON MEDH SONASAWARI 01 | Closed | 187600 | 0 | 2017-07-01 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1732003015/IF/22012034434851 — phoudhropan sarvjanik sthan par gram sonasawari 01 | Closed | 543860 | 0 | 2018-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/22012034544656 — Pashu shed nirman Malti bai/ Babulal Badkur | Deleted | 0 | 0 | 2020-01-26 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/22012034544665 — Pashu shed nirman Usha Bai/Nandkishor Badkur | Deleted | 0 | 0 | 2020-01-26 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/22012034544667 — Pashu shed nirman Preeti Badkur/ Mohandas Badkur | Deleted | 0 | 0 | 2020-01-26 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/22012034544670 — Pashu shed nirman Mamta Badkur/ Paramsukh Badkur | Deleted | 0 | 0 | 2020-01-26 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/22012034544671 — Pashu shed nirman Baby Chourey/ Sanjeev Chourey | Deleted | 0 | 0 | 2020-01-26 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/22012034544673 — Pashu shed nirman Heera bai/ Umashankar Choudhary | Deleted | 0 | 0 | 2020-01-26 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/22012034544674 — Pashu shed nirman Gayatri bai/ Ramkishor malaiya | Deleted | 0 | 0 | 2020-01-26 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/22012034594596 — Pashu shed nirman Maltibai/ Babulal Badkur | Physically Completed | 63830.2 | 55968 | 2021-02-08 - 2021-09-13
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/22012034594601 — Pashu shed nirman Ushabai Badkur/ Nandkishhor Badkur | Physically Completed | 63830.2 | 57699 | 2021-02-19 - 2021-09-13
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/22012034594602 — Pashu shed nirman Preeti Badkur/ Mohandas Badkur | Closed | 63830.2 | 0 | 2020-04-21 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/22012034594604 — Pashu shed nirman Mamta Badkur/ Paramsukh Badkur | Ongoing | 63830.2 | 3800 | 2021-01-25 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/22012034594605 — Pashu shed nirman Baby chourey/ Sanjeev chourey | Ongoing | 63830.2 | 1140 | 2021-01-25 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/22012034594607 — Pashu shed nirman Heera choudhary/ Umashankar choudhary | Ongoing | 63830.2 | 6187 | 2021-12-31 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/22012034594608 — Pashu shed nirman Gayatri Malaiya/ Ramkishor Malaiya | Physically Completed | 63830.2 | 57605 | 2021-02-01 - 2021-09-13
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732003015/IF/22012035555944 — CTR JGSA Basant / Tulsiram Mehra ke khet me Khet Talab Nirman | Ongoing | 147621.16 | 17226 | 2025-05-30 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1732003015/IF/22012035555948 — CTR-JGSA-Archana patel ke Kup ke pash recharge Pit | Completed | 17843 | 17748 | 2025-05-29 - 2026-04-01
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/9993668851 — Sonasawari Pasu Sed Nirman Gendalal/Omkar | Completed | 123000 | 119828.99 | 2015-07-04 - 2017-11-19
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/9993668895 — Sonasawari Pasu Sed Nirman Trun/Nepal | Completed | 123000 | 119328.52 | 2015-07-04 - 2016-09-27
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003015/IF/9993669658 — सोनासांवरी पशुशेड निर्माण नारायणप्रसाद/सीताराम | Deleted | 123000 | 0 | 2015-07-20 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003015/IF/9993678510 — DARWARPATEL/GANESHRAM MEDH BANDHAN SONASAVWRI | Completed | 48888 | 40068 | 2015-10-05 - 2019-02-20
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003015/IF/9993678644 — SHYAMSUNDAR/NANHELAL MEDH BANDHAN SONASAVWRI | Completed | 48888 | 35298 | 2015-10-05 - 2019-02-20
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003015/IF/9993678814 — DHANRAJ/GANESHRAM MEDH BADHANM SONASAVWRI | Completed | 48888 | 25758 | 2015-10-12 - 2019-02-20
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003015/IF/9993678828 — SONASAVRI MEDH BANDHAN KUNDANLAL/KODURAM | Completed | 48888 | 25917 | 2015-10-12 - 2019-02-20
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003015/IF/9993683912 — SONASAVWRI MEDH BHANDHAN BASANT/ TULSIRAM | Closed | 48888 | 0 | 2015-09-23 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003015/IF/9993687177 — DILIP / KUNDANLAL MEDH BANDHAN SONASAVWRI | Completed | 48888 | 397 | 2015-11-09 - 2019-02-20
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003015/IF/9993687195 — RAMESH /SALIGRAM MEDH BANDHAN SONASAVWRI | Completed | 48888 | 350 | 2015-11-09 - 2019-02-20
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1088174 — Construction of IAY House -IAY REG. NO. MP2908390 | Completed | 15480 | 10416 | 2017-05-15 - 2019-04-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1570538 — Construction of IAY House -IAY REG. NO. MP2937653 | Completed | 15480 | 16704 | 2018-05-28 - 2018-08-29
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1570541 — Construction of IAY House -IAY REG. NO. MP3020659 | Completed | 15480 | 16704 | 2018-05-28 - 2018-08-29
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1570561 — Construction of IAY House -IAY REG. NO. MP3532194 | Completed | 15480 | 15660 | 2018-05-28 - 2018-12-12
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1570580 — Construction of IAY House -IAY REG. NO. MP3020501 | Completed | 15480 | 15660 | 2018-06-18 - 2018-12-12
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1918613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4857478 | Completed | 15660 | 14784 | 2019-12-02 - 2020-03-24
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1918614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4857590 | Completed | 15660 | 15660 | 2018-10-01 - 2018-11-13
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1919015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4816812 | Completed | 15660 | 15186 | 2018-11-19 - 2019-12-02
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1919019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4830100 | Completed | 15660 | 14616 | 2018-11-05 - 2019-03-28
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1919025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4859881 | Completed | 15660 | 15660 | 2018-11-05 - 2019-03-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1919029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4868606 | Completed | 15660 | 13572 | 2018-10-01 - 2019-03-28
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1919615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5012274 | Completed | 15660 | 14616 | 2018-09-24 - 2019-07-22
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1919662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5146194 | Completed | 15660 | 15660 | 2018-11-05 - 2019-03-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1919667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5152946 | Completed | 15660 | 15660 | 2018-11-26 - 2019-03-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1919669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5158302 | Completed | 15660 | 15660 | 2018-10-01 - 2018-12-12
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1919670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5158422 | Completed | 15660 | 15660 | 2018-11-26 - 2019-03-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1919674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5164027 | Completed | 15660 | 14616 | 2018-11-26 - 2019-07-22
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1919759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5087825 | Completed | 15660 | 15312 | 2018-09-10 - 2019-03-28
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1919760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5090258 | Completed | 15660 | 16704 | 2018-09-10 - 2018-12-05
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1919763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5095777 | Completed | 15660 | 15660 | 2018-10-22 - 2019-03-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1922383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4219781 | Completed | 15660 | 15660 | 2018-09-10 - 2019-03-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1926435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5056288 | Completed | 15660 | 15660 | 2018-10-01 - 2019-08-18
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1926450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5094452 | Completed | 15660 | 15660 | 2018-10-01 - 2018-12-26
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1926456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5111352 | Completed | 15660 | 15660 | 2018-11-19 - 2019-03-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1928271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4185244 | Completed | 15660 | 13572 | 2018-11-19 - 2019-03-28
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1928407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4971744 | Completed | 15660 | 15660 | 2018-10-22 - 2019-03-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1928408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4971705 | Completed | 15660 | 15660 | 2018-10-29 - 2018-12-26
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1934710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5079904 | Completed | 15660 | 15660 | 2018-11-05 - 2019-03-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1934720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4799948 | Completed | 15660 | 15660 | 2018-11-19 - 2019-03-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/1935026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4246906 | Completed | 15660 | 15660 | 2018-11-12 - 2019-03-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/229739 — Construction of IAY House -IAY REG. NO. MP1300714 | Completed | 15030 | 14745 | 2017-02-21 - 2019-03-28
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/2298183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5116267 | Completed | 15840 | 16232 | 2019-10-28 - 2020-07-27
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/2298197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5181134 | Completed | 15840 | 16232 | 2019-10-28 - 2020-07-27
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/234435 — Construction of IAY House -IAY REG. NO. MP1393294 | Completed | 15030 | 14515 | 2017-02-21 - 2018-11-13
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/3651934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106231646 | Completed | 18360 | 18360 | 2022-06-02 - 2023-01-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/3652147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126604599 | Completed | 18360 | 17952 | 2022-06-16 - 2023-04-28
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/3652709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116343261 | Completed | 18360 | 18360 | 2022-06-16 - 2023-01-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/3652791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117458111 | Completed | 18360 | 18360 | 2022-06-16 - 2023-01-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/3652976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118376895 | Completed | 18360 | 18360 | 2022-06-02 - 2023-01-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/3652977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118402720 | Completed | 18360 | 18360 | 2022-06-02 - 2023-01-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/3653474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121562030 | Completed | 18360 | 18360 | 2022-06-16 - 2023-01-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/3692289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115204596 | Completed | 18360 | 18360 | 2022-06-09 - 2023-01-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/3759084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118372978 | Completed | 18360 | 18360 | 2022-06-02 - 2023-01-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/3775314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120640298 | Completed | 18360 | 18360 | 2022-06-16 - 2023-01-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/40756 — Construction of IAY House -IAY REG. NO. MP-32-003-015-001/124 | Completed | 14310 | 7314 | 2015-12-14 - 2019-03-28
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/40760 — Construction of IAY House -IAY REG. NO. MP-32-003-015-001/53 | Completed | 14310 | 7314 | 2015-12-21 - 2019-03-28
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/4155274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119738702 | Completed | 18360 | 17799 | 2022-06-16 - 2023-07-30
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/4324379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150662818 | Completed | 18360 | 18360 | 2022-09-15 - 2023-02-27
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/4566781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116341339 | Completed | 23490 | 22014 | 2025-01-09 - 2025-09-24
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/4579804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119314313 | Completed | 21870 | 21870 | 2024-10-10 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/4579881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119327776 | Completed | 21870 | 21870 | 2024-10-24 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/4584055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120641861 | Completed | 21870 | 21870 | 2024-11-07 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/4624166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126581555 | Completed | 23490 | 22392 | 2025-01-30 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/4666364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150672573 | Completed | 21870 | 21870 | 2025-01-09 - 2025-03-17
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/4701348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119314022 | Completed | 23490 | 22014 | 2025-01-09 - 2025-12-03
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/4879880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118372842 | Completed | 23490 | 22392 | 2025-01-30 - 2025-12-03
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5000153 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116890439 | Completed | 23490 | 23274 | 2025-03-20 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5000512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117455724 | Completed | 23490 | 23274 | 2025-03-20 - 2025-12-03
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5000566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117465219 | Completed | 23490 | 23274 | 2025-03-20 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5004222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118361458 | Completed | 23490 | 23058 | 2025-03-20 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5004247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118364936 | Completed | 23490 | 23274 | 2025-03-20 - 2025-12-03
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5004305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118382360 | Completed | 23490 | 23274 | 2025-03-20 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5004350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118399587 | Completed | 23490 | 23013 | 2025-03-20 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5004352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118400085 | Completed | 23490 | 23013 | 2025-03-20 - 2025-12-03
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5004355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118402462 | Completed | 23490 | 23013 | 2025-03-20 - 2025-12-03
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5004874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118176154 | Completed | 23490 | 23274 | 2025-03-20 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5006051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119290642 | Physically Completed | 23490 | 23229 | 2025-06-26 - 2026-02-03
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5007551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120610289 | Completed | 23490 | 23490 | 2025-06-19 - 2026-04-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5007619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120643149 | Ongoing | 23490 | 2916 | 2025-03-20 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5008515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119380832 | Completed | 23490 | 23274 | 2025-03-20 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5009517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121562334 | Ongoing | 23490 | 17532 | 2025-03-20 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5019737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126028099 | Completed | 23490 | 23274 | 2025-03-20 - 2025-12-03
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5020231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126597025 | Ongoing | 23490 | 17793 | 2025-03-20 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5020268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126603156 | Completed | 23490 | 23013 | 2025-03-20 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5020319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126612143 | Completed | 23490 | 23013 | 2025-03-20 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5020361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126620012 | Completed | 23490 | 23013 | 2025-03-20 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5020379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126623373 | Completed | 23490 | 23274 | 2025-03-20 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5085764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127522637 | Completed | 23490 | 23490 | 2025-06-19 - 2026-04-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5085773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127524621 | Ongoing | 23490 | 10224 | 2025-03-20 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5085780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127526509 | Completed | 23490 | 23274 | 2025-03-20 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5103233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148906172 | Completed | 23490 | 23013 | 2025-03-20 - 2025-12-03
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5106281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150184895 | Completed | 23490 | 23274 | 2025-03-20 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5106285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150187922 | Approved | 23490 | 0 | 2025-02-23 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5106461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150252824 | Physically Completed | 23490 | 23274 | 2025-03-20 - 2026-02-03
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5107058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150612187 | Completed | 23490 | 23274 | 2025-03-20 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/517792 — Construction of IAY House -IAY REG. NO. MP2505026 | Completed | 15030 | 15205 | 2017-02-21 - 2019-03-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/521499 — Construction of IAY House -IAY REG. NO. MP2589889 | Completed | 15030 | 14488 | 2017-02-21 - 2019-03-28
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/53736 — Construction of IAY House -IAY REG. NO. MP-32-003-015-001/1 | Deleted | 14310 | 0 | 2016-05-23 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5460242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119313447 | Ongoing | 23490 | 1827 | 2025-08-23 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5463505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120639017 | Completed | 23490 | 23490 | 2025-05-29 - 2025-12-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5463984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126596185 | Completed | 23490 | 23490 | 2025-08-23 - 2026-04-25
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5465127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119738736 | Ongoing | 23490 | 2349 | 2025-08-28 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5532727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150678838 | Ongoing | 23490 | 21924 | 2025-08-28 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5580005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126582750 | Approved | 23490 | 0 | 2025-02-23 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/5620312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118382603 | Ongoing | 23490 | 12789 | 2025-08-23 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/863278 — Construction of IAY House -IAY REG. NO. MP1651466 | Completed | 15480 | 15588 | 2017-05-15 - 2019-03-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/870391 — Construction of IAY House -IAY REG. NO. MP1740348 | Completed | 15480 | 14520 | 2017-06-19 - 2019-03-28
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/924948 — Construction of IAY House -IAY REG. NO. MP2498744 | Completed | 15480 | 13512 | 2017-06-19 - 2019-03-28
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/944638 — Construction of IAY House -IAY REG. NO. MP2908368 | Approved | 23490 | 0 | 2017-04-04 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/944848 — Construction of IAY House -IAY REG. NO. MP2913173 | Completed | 15480 | 16704 | 2018-01-08 - 2018-08-29
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/945878 — Construction of IAY House -IAY REG. NO. MP2938800 | Completed | 15480 | 12528 | 2018-12-03 - 2019-04-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/957995 — Construction of IAY House -IAY REG. NO. MP3238445 | Completed | 15480 | 15516 | 2017-05-15 - 2019-03-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003015/IF/IAY/959596 — Construction of IAY House -IAY REG. NO. MP3277099 | Completed | 15480 | 2064 | 2017-05-15 - 2019-04-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1732003015/LD/22012034295806 — सोनासांवरी शांति धाम निर्माण | Completed | 180000 | 175564.54 | 2016-12-26 - 2019-09-08
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1732003015/LD/22012034295808 — सोनासांवरी स्‍कूल के पास खेल मैदान निर्माण | Deleted | 353000 | 0 | 2016-04-02 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1732003015/LD/54 — सोनांसावरी खेल मैदान निर्माण (स्‍कूल परिसर मे) | Completed | 452787 | 164326 | 2012-02-10 - 2013-03-31
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034154885 — सोनासांवरी पंच परमेश्‍वर ग्‍वालबाबा से विमल पटैल क | Completed | 146431 | 90419 | 2012-10-12 - 2013-04-20
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034195481 — सोनासांवरी रामनारायण के घर से देवकरण के घर तक दोनो | Completed | 101210 | 56020 | 2013-12-23 - 2014-11-03
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034201841 — सोनासांवरी खिडका से धान की चक्‍की तक एक ओर नाली नि | Completed | 43229 | 38084 | 2014-02-03 - 2014-11-03
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034218221 — सोनासांवरी सांसद निधि शंकर मंदिर से द्वारका सराठे के मकान की ओर सी.सी. रोड निर्माण | Completed | 38297 | 14801 | 2014-05-19 - 2018-08-01
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034298534 — सोनासांवरी रिन्‍युअल कोट मदन मालवीय से परसाई एवं गोविंद सेठ से बजरंग मंदिर तक | Deleted | 27324 | 0 | 2015-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034298535 — सोनासांवरी मदन मालवीय के घर से परसाई एवं गोविंद सेठ से बजरंग मंदिर तक नाली निर्माण | Deleted | 36901 | 0 | 2015-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034323233 — सोनासांवरी ग्‍वालबाबा के पास से कन्‍नी के घर तक सी सी रोड | Closed | 0 | 0 | 2017-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034334224 — rambharosh tilotiya ke ghar se jeevan lal mehra ke ghar tak cc road evam nali nirman | Completed | 5004 | 4988 | 2017-04-03 - 2017-12-20
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034334260 — MAIN ROAD SE GENIOUS PLATNET SCHOOL TAK CC RAOD EVAM NALI NIRMAN GRAM SONASAWARI | Completed | 21672 | 16512 | 2017-04-03 - 2017-12-20
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034337281 — MAHESH MALVIYA KE GHAR SE PRABHUDAYAL KE GHAR TAK CC NALI NIRMAN GRAM SONASAWRI | Completed | 1155 | 1032 | 2017-05-08 - 2017-12-20
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034375468 — SONASWARI JINIYAS SCHOOL KE SAMNE C.C. ROAD NIRMAN | Closed | 0 | 0 | 2017-10-02 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034390748 — RCC Nali nirman | Closed | 0 | 0 | 2018-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034397810 — HARIDAS KE GHAR SE PRAKASH MALVIYA KE GHAR TAK CC ROAD RENEVAL COAT NIRMAN | Completed | 7445 | 7308 | 2019-03-04 - 2019-04-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034397827 — Vinit yadav ke ghar se kailash patel ke ghar tak C.C. road renewal cort | Completed | 11585 | 11484 | 2019-03-11 - 2019-05-10
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003015/RC/22012034397837 — Babulal ke khale se men rodad tak C.C. road renewal cort | Completed | 37460 | 37236 | 2018-12-17 - 2019-03-28
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034398072 — Sardar patel ke ghar se Dhanraj patel ke ghar tak ek taraf naali nirman | Closed | 78400 | 0 | 2018-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034398074 — Parasram mehra ke ghar se Puranlal sagoriya ke ghar tak ek taraf naali nirman | Closed | 1650 | 0 | 2018-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034439891 — aanganwadi kendra 1 se nadi tak cc road nirmaan | Deleted | 0 | 0 | 2019-04-01 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034439894 — saala parisar boundary gate se MS tak cc road | Deleted | 0 | 0 | 2018-04-01 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034470114 — SONASWARI ANGANWADI KENDRA 01 SE NADI TAK C.C. ROAD NIRMAN | Completed | 28405 | 28368 | 2019-07-29 - 2020-03-24
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034470115 — SONASAWARI SHALA PARISAR ME BAUNDRI GATE SE M SHALA TAK C.C. ROAD NIRMAN | Completed | 33377 | 32580 | 2019-07-29 - 2020-03-24
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034478373 — SONASAWARI JINIYAS SCHOOL SE NADI TAK C.C. ROAD NIRMAN | Completed | 58622 | 58256 | 2019-09-23 - 2020-03-24
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034479052 — SONASAWARI PAWAN CHOUREY KE GHAR SE SHANKAR MANDIR TAK C.C. NALI NIRMAN | Completed | 1956 | 2112 | 2019-11-25 - 2020-11-17
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034479545 — SONASAWARI HANUMAN MANDIR KE PASS PULIYA NADI TAK C.C. ROAD NIRMAN | Closed | 4690 | 0 | 2019-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034506044 — C. C. ROAD MAIN ROAD SE SHANTIDHAM TAK | Deleted | 0 | 0 | 2019-10-02 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034506046 — C. C. Road Main Road Se Shantidham Tak | Completed | 19225 | 19008 | 2019-12-02 - 2020-03-24
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034506049 — Shree Pooranlal Prajapati Ke Ghar Se Shree Rahul Choudhary Ke Ghar Tak C. C. Road Renewal Cort | Completed | 18730 | 19008 | 2019-12-09 - 2020-06-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034506050 — Chandra Kumar Choudhary Ke Ghar Se Shree Balkrishna Choudhary Ke Ghar Tak | Completed | 13969 | 13728 | 2019-12-09 - 2020-06-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034508507 — C C ROAD PARMSUKH BADKUR KE GHAR SE VINAY BHARGAV KE GHAR TAK | Closed | 6310 | 0 | 2019-10-02 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034508583 — C C Road Rajkumar Mehra ke ghar se khedapati mandir tak | Completed | 9415 | 9504 | 2019-12-23 - 2020-03-24
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034510688 — गेंदालाल के घर से यशवंत के घर की ओर | Closed | 0 | 0 | 2019-10-02 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034510694 — सी सी रोड जस्सू परसाई के घर से श्री लाल के घर की ओर | Closed | 0 | 0 | 2019-10-02 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034514477 — SONASWARI RCC NALI NIRMAN ANIL GOUR SE MAKHAN MEENA KE GHAR TAK | Closed | 26250 | 0 | 2019-10-02 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034520114 — SONASWARI RCC NALI NIRMAN ANIL GOUR SE MAKHAN MEENA KE GHAR KI AUR | Completed | 46671 | 46236 | 2020-03-09 - 2020-10-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034553219 — SONASAWARI PCC NALI NIRMAN WARD NO 14 PRAMOD PATEL KE GHAR SE SARWAJANIK KOOP TAK | Completed | 5406 | 4940 | 2020-12-21 - 2021-02-14
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034658107 — Sonasanwari - Sonu mehra ke ghar se Nandkishor mehra ke ghar tak CCroad nirman | Completed | 4516 | 4507 | 2023-10-05 - 2025-01-23
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034665563 — Sonasanwari - prakash malviya ke ghar se dilip malaiya ke ghar tak cc road nirman | Completed | 8188 | 8186 | 2023-10-08 - 2024-12-06
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003015/RC/22012034670666 — Sonasanwari - Lalapatel ke ghar se Govind choure ke ghar ki or CCRoad nirman | Completed | 11470 | 11464 | 2023-12-14 - 2024-12-06
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003015/RS/22012034506547 — Nadep nirman Hanuman mandir ke pas Sonasawari | Ongoing | 23056.37 | 3717 | 2021-05-21 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003015/RS/22012034506548 — Nadep nirman Samudayik bhawan ke pas Sonasawari | Ongoing | 23056.37 | 3717 | 2021-05-21 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003015/RS/22012034647600 — Gwalbaba ke pas Nadep nirman | Closed | 4239 | 0 | 2021-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003015/RS/22012034647601 — Mangal Bhavan ke pas Nadep Nirman | Closed | 4239 | 0 | 2021-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732003015/RS/22012035127905 — Gbalbaba se Nandkishor Jothe ke ghar ki or RCC Nali nirman kary | Completed | 50652 | 50647 | 2024-06-27 - 2024-12-06
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732003015/RS/22012035127991 — Dinesh Sagoriya ke ghar ke samne RCC nali nirman kary | Approved | 0 | 0 | 2024-06-08 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732003015/RS/22012035127996 — Dinesh Sagoriya ke ghar ke samne RCC nali nirman kary | Approved | 5411 | 0 | 2024-06-08 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003015/RS/26599 — सोनासांवरी शौचालय निमाण रमेश रामरतन | Deleted | 5197 | 0 | 2013-06-03 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003015/RS/27696 — सोनासांवरी शौचालय रामगोपाल देवचंद | Completed | 5197 | 4627 | 2013-06-03 - 2015-05-20
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003015/RS/30426 — सोनासांवरी शौचालय नंदकिशोर मोहनलाल | Deleted | 5197 | 0 | 2013-06-10 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003015/RS/30429 — सोनासांवरी शौचालय निमाण सुंदरलाल रामपसाद | Completed | 5197 | 4627 | 2013-06-10 - 2015-05-20
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003015/RS/33987 — सोनासांवरी शौचालय निमाण रामदास कचरु | Completed | 5197 | 4627 | 2013-06-17 - 2015-05-20
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732003015/SK/1100 — Bharat Nirman Rajeev Gandhi Sewa Kendra,SONASAVARI | Completed | 1000000 | 544253 | 2013-09-30 - 2025-03-01
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732003015/WC/22012034612451 — Hodi Nirman Pashu ke liye shaskiy shala ke pas | Completed | 7795 | 7600 | 2021-03-05 - 2021-05-15
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732003015/WC/22012034612639 — Hodi Nirman Pashu ke liye Patel mohlla Sonasawari | Closed | 7795 | 0 | 2020-10-02 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732003015/WC/22012034612646 — Hodi Nirman Pashu ke liye Khedapati Mandir ke pas | Closed | 7795 | 0 | 2020-10-02 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732003015/WC/22012034612653 — Hodi Nirman Pashu ke liye Shaskiy Dukan ke pas Sonasawari | Deleted | 7795 | 0 | 2020-10-02 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732003015/WC/22012034612657 — Hodi Nirman Pashu ke liye Shaskiy Dukan ke pas Sonasawari | Closed | 7795 | 0 | 2020-10-02 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1732003015/WC/22012034617148 — check dam nirman panachayat bnawan ke pass sonasaveri nadi par | Completed | 303191.29 | 228780.03 | 2021-03-12 - 2023-05-20
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003015/WC/22012034691869 — CTR-recharge pit school me handpump ke pass sonasaveri | Completed | 14467.3 | 10379 | 2021-05-10 - 2026-04-01
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003015/WC/22012034693262 — CTR-Recharge pit mangal bhawan ke pass sonasaveri | Closed | 14467.3 | 0 | 2021-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003015/WC/22012034693266 — CTR-recharge pit primary school gandhiji ke murti ke pass sonasaveri | Completed | 14467.3 | 10136 | 2021-05-10 - 2026-04-01
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003015/WC/22012034693271 — CTR-recharge pit yatripartikshalya ke pass sonasaveri | Closed | 14467.3 | 0 | 2021-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003015/WC/22012034693275 — CTR-recharge pit shayam singh ke ghar ke pass handpump par sonasaveri | Closed | 14467.3 | 0 | 2021-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732003015/WC/22012034912432 — Sonasanwari - Talab Jirnodhdhar kary | Closed | 0 | 0 | 2021-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732003015/WC/22012035022500 — Sardar ji ki dery se nadi tak kachchi nali nirman | Completed | 55992.67 | 46384 | 2022-12-15 - 2026-04-27
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003015/WC/22012035124850 — Sonasanwari - Men road se bhojraj patel ke ghar ki or RCC nali nirman | Completed | 18639 | 18636 | 2023-10-05 - 2025-01-23
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003015/WC/22012035124866 — Sonasanwari - Harish malaiya ke ghar se badkur ke bade tak RCC nali road nirman | Completed | 11986 | 11797 | 2023-10-05 - 2024-12-06
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003015/WC/22012035124871 — Sonasanwari - Lalapatel ke ghar se Govind choure ke ghar ki or RCC nali nirman | Ongoing | 11470 | 1105 | 2023-10-05 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003015/WC/22012035124891 — Sonasanwari - Mahesh malviya ke ghar se prabhu malviya ke ghar tak RCC nali nirman | Completed | 7332 | 7309 | 2023-10-05 - 2025-01-23
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732003015/WC/22012035208943 — Roof top rain water harvesting Panchayat bhawan | Completed | 17675 | 14337 | 2024-09-04 - 2024-12-06
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003015/WC/22012035290892 — CTR Samudayik sokpit nirman shaskiy bhawan ke pas | Approved | 0 | 0 | 2025-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732003015/WC/22012035290964 — CTR ROOF RAIN WATER HARWESTING MS SCHOOL SONASAWARI | Approved | 17101 | 0 | 2025-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003015/WC/22012035290975 — CTR JGSA SAMUDAYIK SOCKPIT NIRMAN SAMUDAYIK BHAVAN KE PASS | Approved | 5274 | 0 | 2025-04-14 -
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732003015/WC/677 — सोनासांवरी सोक्‍ता गड्रडा स्‍कूल वाले हेण्‍डपंप के पास | Completed | 6815 | 6350 | 2011-06-18 - 2012-01-03
NARMADAPURAM / HOSHANGABAD / SONASAVARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732003015/WC/678 — सोनासांवरी हरिजन मोहल्‍ला के हेण्‍डपंप के पास | Completed | 6815 | 6350 | 2011-06-18 - 2012-01-03