## Work List
Exported on: 2026-10-14 19:43:07
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: VISARODA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1732003024/AV/22012034504511 — Shantidhaam nirmaan Ghughwasa | Ongoing | 192447.09 | 0 | 2020-05-15
NARMADAPURAM / HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1732003024/AV/22012034636623 — Bisaroda - Govt. M.S.School Bisaroda me Boundrywall Nirman kary | Ongoing | 103812 | 0 | 2023-10-02
NARMADAPURAM / HOSHANGABAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1732003024/DP/22012034595312 — Bisaroda - Vasudha Vandan - Amrit Vatika - Talab Kinare - Ghugwasa | Ongoing | 55847.4 | 0 | 2023-08-09
NARMADAPURAM / HOSHANGABAD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Shelter Belt Trees-Comm / Avenue Plantation for Community | Plantation | 1732003024/DP/22012034618112 — सोनासावरी रोड बीसारोड़ा से घुघवासा तक वन साईड रोड किनारे वृक्षारोपण | Ongoing | 453563.17 | 0 | 2024-06-27
NARMADAPURAM / HOSHANGABAD | 2025-2026 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1732003024/FP/22012034642099 — बीसारोड़ा एवं घुघवासा के बीच नदी पर पुलिया रपटा निर्माण | Approved | 75749 | 0 | 2025-04-14
NARMADAPURAM / HOSHANGABAD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individual | Goat Shelter | 1732003024/IF/22012034535727 — Bakri shed Kashi Bai / Chhotelal Bisaroda | Ongoing | 46140.53 | 0 | 2020-03-20
NARMADAPURAM / HOSHANGABAD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1732003024/IF/22012034535745 — Pashu Shed Sakunbai / Sabulal Bisaroda | Ongoing | 62950.96 | 0 | 2020-03-20
NARMADAPURAM / HOSHANGABAD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1732003024/IF/22012034535780 — Pashu shed Rajkumari / Shashikapur Bisaroda | Ongoing | 62950.96 | 0 | 2020-03-20
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1732003024/IF/22012035260055 — पशु शेड निर्माण नरबदी बाई /संतोष बीसारोड़ा | New | 0 | 0 | 2024-08-16
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1732003024/IF/22012035272049 — Pasu shed nirman Narabdibai patel/santosh bisaroda | Ongoing | 136121.6 | 0 | 2025-02-13
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732003024/IF/22012035614720 — Ek Bagiya Ma Ke Naam Uma Bai Patel Bisaroda | Ongoing | 160905.46 | 0 | 2025-09-16
NARMADAPURAM / HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/3816945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118104274 | Approved | 27000 | 0 | 2022-05-02
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/4559780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115283914 | Completed | 23490 | 0 | 2025-01-16 | 2026-08-12
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/4617454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125812220 | Ongoing | 27000 | 0 | 2025-09-09
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/4744935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114908287 | Ongoing | 27000 | 10500 | 2025-09-06
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/5285243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114908221 | Ongoing | 27000 | 0 | 2025-08-28
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/5302736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115921489 | Ongoing | 27000 | 0 | 2025-08-21
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/5313144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106483046 | Ongoing | 27000 | 0 | 2025-04-24
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/5313736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114908601 | Ongoing | 27000 | 0 | 2025-08-28
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/5334483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125869104 | Completed | 23490 | 0 | 2025-08-28 | 2026-08-12
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/5456726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118101077 | Completed | 23490 | 0 | 2025-05-22 | 2026-08-12
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/5458272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115935408 | Ongoing | 27000 | 0 | 2025-06-05
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/5461967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106503876 | Ongoing | 27000 | 0 | 2025-07-31
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/5465843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106529240 | Ongoing | 27000 | 0 | 2025-05-08
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/5620126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106486618 | Ongoing | 27000 | 10500 | 2025-09-09
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/5709365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148543304 | Ongoing | 27000 | 0 | 2025-08-28
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6069135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106525405 | Approved | 27000 | 0 | 2026-02-09
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6071733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114908439 | Approved | 27000 | 0 | 2026-03-02
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6071734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114908662 | Approved | 27000 | 0 | 2026-03-02
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6072522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115269221 | Approved | 27000 | 0 | 2026-02-09
NARMADAPURAM / HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6077366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118109118 | Ongoing | 27000 | 21000 | 2026-07-02
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6084624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124188537 | Approved | 27000 | 0 | 2026-02-09
NARMADAPURAM / HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6086376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125534623 | Ongoing | 27000 | 0 | 2026-05-28
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6086807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125828393 | Approved | 27000 | 0 | 2026-03-02
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6089721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127216926 | Approved | 27000 | 0 | 2026-03-02
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6090101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127472559 | Approved | 27000 | 0 | 2026-02-09
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6100433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150142667 | Approved | 27000 | 0 | 2026-03-02
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6128144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115938461 | Approved | 27000 | 0 | 2026-03-12
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6137002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147694192 | Approved | 27000 | 0 | 2026-02-09
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6153536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125867278 | Approved | 27000 | 0 | 2026-03-12
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6168439 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150141948 | Approved | 27000 | 0 | 2026-03-12
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6174291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118115737 | Approved | 27000 | 0 | 2026-03-12
NARMADAPURAM / HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003024/IF/IAY/6357988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151171471 | Ongoing | 27000 | 0 | 2026-10-08
NARMADAPURAM / HOSHANGABAD | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732003024/RC/22012034843210 — बीसारोड़ा एवं घुघवासा के बीच नदी पर सी.सी.रोड निर्माण | Approved | 48950 | 0 | 2025-04-14
NARMADAPURAM / HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1732003024/WC/22012035293190 — सामुदायिक सोख पिट भंगी बाबा के पास बीसारोडा | Approved | 5274 | 0 | 2025-04-14