## Work List
Exported on: 2026-09-05 15:00:45
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: PARRADEH
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1732003029/AV/22012034372882 — Shantidham Nirman Parradeh | Completed | 173773.05 | 162040 | 2020-02-27 | 2021-04-18
NARMADAPURAM / HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1732003029/AV/22012034399822 — Khel maidan nirman Parradeh | Closed | 0 | 0 | 2018-12-30
NARMADAPURAM / HOSHANGABAD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732003029/DP/22012034423584 — shaskiya bhoomi per block plantation gram parradeh (khasra no 27 | Completed | 543860 | 239835 | 2018-07-20 | 2023-08-17
NARMADAPURAM / HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Repair & Maint of water course Canal for Community / Repair and Maintenance of water course Canal for Community | Repair & Maint of Canal | 1732003029/DP/22012034548776 — PLANTATION ANGANBADI EVAM UPSWASTH KENDRA PARISAR HASALPUR | Deleted | 0 | 0 | 2022-01-26
NARMADAPURAM / HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Medicinal Plantation in Community land / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732003029/DP/22012034548777 — PLANTATION ANGANBADI EVAM UPSWASTH KENDRA PARISAR HASALPUR | Closed | 0 | 0 | 2022-01-26
NARMADAPURAM / HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1732003029/DP/22012034548780 — PLANTATION MADHYMIK SHALA PARRADEH | Closed | 0 | 0 | 2022-01-26
NARMADAPURAM / HOSHANGABAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1732003029/DP/22012034563739 — VRAKSHAROPAN PRABHU MEENA KE GHAR SE AAGE DONGARWADA ROAD KINARE MUKESH MEENA KE TAPPER TAK | Completed | 407719.19 | 178407.31 | 2022-08-23 | 2026-04-24
NARMADAPURAM / HOSHANGABAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732003029/DP/22012034595329 — Parradeh - Vasudha Vandan - Amrit Vatika - School Parisar me | Completed | 55847.4 | 27799 | 2023-08-17 | 2026-04-24
NARMADAPURAM / HOSHANGABAD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1732003029/DP/22012034620926 — Haslpur se randal road side plantation narmada path | Ongoing | 453563.17 | 110218 | 2024-07-16
NARMADAPURAM / HOSHANGABAD | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732003029/DP/63 — पर्रादेह शासकीय भूमि पर व़क्षारोपण एवं तार् फेसिंग | Completed | 486616 | 132021 | 2009-08-04 | 2013-03-15
NARMADAPURAM / HOSHANGABAD | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732003029/DP/69 — पर्रादेह नर्मदाजी किनारे बांसरोपण काय् | Completed | 284924.9 | 45439 | 2010-08-03 | 2013-03-15
NARMADAPURAM / HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732003029/FP/22012034365222 — nali nirman handpump ke pass se nale tak | Completed | 19607.25 | 10260 | 2020-05-28 | 2020-09-30
NARMADAPURAM / HOSHANGABAD | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732003029/IF/147 — पर्रादेह कपिलधारा रामबाई / भागचंद्र | Completed | 94000 | 88714 | 2009-05-02 | 2009-05-02
NARMADAPURAM / HOSHANGABAD | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732003029/IF/148 — पर्रादेह कपिलधारा हरिपाल / रामदयाल | Completed | 94000 | 74068.39 | 2009-05-02 | 2011-06-16
NARMADAPURAM / HOSHANGABAD | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732003029/IF/149 — पर्रादेह कपिलधारा हजारीलाल / रामदयाल | Completed | 94000 | 83720.6 | 2009-05-02 | 2009-05-02
NARMADAPURAM / HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003029/IF/22012034348217 — Parradeh Plantation of parradeh to hashallpur road kinare | Completed | 335000 | 124192 | 2017-06-15 | 2022-06-16
NARMADAPURAM / HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003029/IF/22012034351016 — HASALPUR PRADHANMANTRI SADAK KE KINARE PLANTATON | Completed | 335000 | 20784 | 2017-06-22 | 2019-12-12
NARMADAPURAM / HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003029/IF/22012034351025 — HASALPUR NARMDA NADI KINARE PLANTATION 1 | Completed | 335000 | 55225 | 2017-06-21 | 2021-01-23
NARMADAPURAM / HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003029/IF/22012034351551 — HASALPUR NARMDA NADI KINARE PLANTATION 2 | Completed | 335000 | 15172 | 2017-07-13 | 2019-12-12
NARMADAPURAM / HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003029/IF/22012034351554 — NARMDA NADI KE KINARE PLANTATION 3 | Completed | 335000 | 15344 | 2017-07-13 | 2019-12-12
NARMADAPURAM / HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003029/IF/22012034351558 — HASALPUR NARMDA NADI KINARE SHASKIYE BHOOMI PER R3&R4 KE LIYE PLANTATION 1 | Completed | 534460 | 124140 | 2017-06-21 | 2022-06-16
NARMADAPURAM / HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003029/IF/22012034351560 — HASALPUR NARMDA NADI KE KINARE SHASKIYE BHOOMI PER R3&R4KE LIYE PLANTATION 02 | Completed | 534460 | 32253 | 2017-06-21 | 2021-01-10
NARMADAPURAM / HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003029/IF/22012034377694 — PARRADEH KISHAN KI MED PER PALANTATION 01 | Physically Completed | 187600 | 7000 | 2017-11-11 | 2021-02-26
NARMADAPURAM / HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003029/IF/22012034377697 — PARRADEHKISHAN KI MED PER PLANTATION NO 2 | Physically Completed | 187600 | 7000 | 2017-11-11 | 2021-02-26
NARMADAPURAM / HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003029/IF/22012034377698 — PARRADEH KISHAN KI MED PER PLANTATION 03 | Physically Completed | 187600 | 7000 | 2017-11-11 | 2021-02-26
NARMADAPURAM / HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003029/IF/22012034377889 — PARRADEH KISHAN KI MED PER PLANTATION 04 | Physically Completed | 187600 | 7000 | 2017-11-11 | 2021-02-26
NARMADAPURAM / HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003029/IF/22012034377956 — PARRADEH KISHAN KI MED PER PLANTATION 05 | Physically Completed | 187600 | 7000 | 2017-11-11 | 2021-02-26
NARMADAPURAM / HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003029/IF/22012034377957 — PARRADEH KISHAN KI MED PER PLANTATION 06 | Physically Completed | 187600 | 7000 | 2017-11-11 | 2021-02-26
NARMADAPURAM / HOSHANGABAD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1732003029/IF/22012034528189 — bakrished dujiyabai/laxminarayan katare hasalpur | Deleted | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1732003029/IF/22012034528190 — bakrished vimlabai/vishram bamne hasalpur | Deleted | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1732003029/IF/22012034528191 — bakrished krishnabai/rameshwar bamne hasalpur | Deleted | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1732003029/IF/22012034528192 — bakrished pholwati/shobharam bamne hasalpur | Deleted | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1732003029/IF/22012034557304 — bakrished dujiyabai/laxminarayan katare hasalpur | Completed | 65467.98 | 50502 | 2020-05-21 | 2021-04-22
NARMADAPURAM / HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1732003029/IF/22012034557307 — bakrished krishnabai/rameshwar bamne hasalpur | Completed | 65467.98 | 47387 | 2020-05-21 | 2026-04-24
NARMADAPURAM / HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1732003029/IF/22012034557308 — bakrished vimlabai/vishram bamne hasalpur | Completed | 65467.98 | 55850 | 2020-05-28 | 2021-04-22
NARMADAPURAM / HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1732003029/IF/22012034557309 — bakrished pholwati/shobharam bamne hasalpur | Completed | 65467.98 | 51325 | 2020-06-11 | 2021-05-15
NARMADAPURAM / HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003029/IF/22012034557312 — khet talab nirman amaniyabai yadav | Ongoing | 332572.21 | 86663 | 2020-11-05
NARMADAPURAM / HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003029/IF/22012034570472 — pashused nirman bhagvati/imratlal | Closed | 140647.74 | 0 | 2020-05-14
NARMADAPURAM / HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003029/IF/22012034570474 — pashushed nirman maltibai/mahesh | Closed | 86093.76 | 0 | 2020-05-14
NARMADAPURAM / HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732003029/IF/22012035019731 — नंदन फलोद्द्यान -बालमुकुंद प्रजापति ग्राम पर्रादेह | Completed | 150727.05 | 129288.25 | 2022-12-06 | 2026-04-24
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732003029/IF/22012035557667 — Jgsa khet talab nirman narayan verma/ babulal verma | Completed | 55865.38 | 43952 | 2025-06-01 | 2026-03-25
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732003029/IF/22012035557680 — Jgsa khet talab nirman dorilal prajapati /balmukand prajapati | Closed | 55865.38 | 3915 | 2025-06-01
NARMADAPURAM / HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1732003029/IF/22012035557930 — CTR DUGWEL KOOP RECHARGE SHAFT BANVARILAL VERMA GRAM PARRADEH | New | 0 | 0 | 2025-04-14
NARMADAPURAM / HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1732003029/IF/22012035557943 — CTR DUGWEL KOOP RECHARGE SHAFT BANVARILAL VERMA GRAM PARRADEH | New | 0 | 0 | 2025-04-14
NARMADAPURAM / HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1732003029/IF/22012035557975 — CTR DUGWEL KOOP RECHARGE SHAFT CHAINSINGH YADAV HASALPUR | Completed | 17120 | 16965 | 2025-05-31 | 2026-04-25
NARMADAPURAM / HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1732003029/IF/22012035558039 — CTR DUGWEL KOOP RECHARGE SHAFT BANVARILAL VERMA GRAM PARRADEH | Completed | 17120 | 16965 | 2025-05-31 | 2026-04-24
NARMADAPURAM / HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1732003029/IF/22012035558061 — CTR DUGWEL KOOP RECHARGE SHAFT BANVARILAL VERMA GRAM PARRADEH | New | 0 | 0 | 2025-04-14
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1732003029/IF/22012035615838 — Cunstruction of PMAYG House for Individuals PMAY G REG NO MP4928704 | Completed | 23490 | 522 | 2025-09-14 | 2026-05-24
NARMADAPURAM / HOSHANGABAD | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732003029/IF/62 — पर्रादेह कूप निर्माण रामनाथ / रामप्रसाद | Completed | 75774 | 55551.78 | 2008-10-06 | 2011-06-16
NARMADAPURAM / HOSHANGABAD | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732003029/IF/63 — पर्रादेह 'हासलपुर' कूप निर्माण मनफूल / भागचंद | Completed | 75774 | 80240 | 2008-10-06 | 2008-10-06
NARMADAPURAM / HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003029/IF/9993666949 — पर्रादेह पशु शेड निर्माण कमलकिशोर/मनफूल | Completed | 123000 | 116485 | 2015-06-18 | 2016-08-08
NARMADAPURAM / HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003029/IF/9993666952 — पर्रादेह पशु शेड निर्माण रामनाथ/रामप्रसाद | Completed | 123000 | 115372 | 2015-06-18 | 2016-08-08
NARMADAPURAM / HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003029/IF/9993667268 — पर्रादेह मेढबंधान बनवारीलाल/मोरध्‍वज | Completed | 48931 | 39114 | 2015-06-20 | 2016-01-18
NARMADAPURAM / HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003029/IF/9993678676 — पर्रादेह मेढ बंधान राधेश्‍याम सुखराम | Deleted | 48888 | 0 | 2015-10-04
NARMADAPURAM / HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003029/IF/9993678678 — पर्रादेह मेढ बधान गुलाबबाई नर्मदाप्रसाद | Deleted | 48888 | 0 | 2015-10-04
NARMADAPURAM / HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003029/IF/9993678680 — पर्रादेह मेढ बंधान रामसिंग नंदलाल | Deleted | 48888 | 0 | 2015-10-04
NARMADAPURAM / HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003029/IF/9993678682 — पर्रादेह मेढ बंधान चंपालाल मूलचंद | Deleted | 48888 | 0 | 2015-10-04
NARMADAPURAM / HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003029/IF/9993678684 — पर्रादेह मेढ बंधान ओमप्रकाश रामरतन | Completed | 48888 | 29317 | 2015-10-08 | 2016-01-18
NARMADAPURAM / HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003029/IF/9993679259 — मेढ वंधान भागीरथ /दीनदयाल पर्रादेह | Completed | 48888 | 28205 | 2015-10-08 | 2016-01-18
NARMADAPURAM / HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003029/IF/9993679267 — पर्रादेह मेढबंधान शेरसिंह/घासीराम | Completed | 48888 | 33400 | 2015-10-08 | 2016-01-18
NARMADAPURAM / HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003029/IF/9993679272 — पर्रादेह मेढबंधान शेरसिंह/घासीराम | Deleted | 0 | 0 | 2015-04-14
NARMADAPURAM / HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003029/IF/9993679278 — पर्रादेह मेढबंधान ननिया /रामेश्‍वर | Completed | 48888 | 25697 | 2015-10-08 | 2016-01-18
NARMADAPURAM / HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003029/IF/9993679281 — मेढवंधान गंगा बाई /फूलचंद पर्रादेह | Completed | 48888 | 28826 | 2015-10-08 | 2016-01-18
NARMADAPURAM / HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/1001210 — Construction of IAY House -IAY REG. NO. MP3465558 | Completed | 15480 | 15486 | 2017-05-18 | 2018-06-22
NARMADAPURAM / HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/112289 — Construction of IAY House -IAY REG. NO. MP-32-003-029-001/57 | Completed | 14310 | 14614 | 2016-02-11 | 2016-08-16
NARMADAPURAM / HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/1910935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4601715 | Completed | 15660 | 15660 | 2018-09-13 | 2018-12-04
NARMADAPURAM / HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/236658 — Construction of IAY House -IAY REG. NO. MP1438845 | Completed | 15030 | 15192 | 2017-01-25 | 2018-05-20
NARMADAPURAM / HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/261126 — Construction of IAY House -IAY REG. NO. MP2528636 | Completed | 15030 | 15058 | 2017-01-26 | 2018-05-20
NARMADAPURAM / HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/271519 — Construction of IAY House -IAY REG. NO. MP2796680 | Completed | 15030 | 15030 | 2017-01-26 | 2018-01-10
NARMADAPURAM / HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/275845 — Construction of IAY House -IAY REG. NO. MP3374247 | Completed | 15030 | 14619 | 2017-01-26 | 2017-05-15
NARMADAPURAM / HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/3652701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116313895 | Completed | 18360 | 18156 | 2022-05-27 | 2022-11-10
NARMADAPURAM / HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/3671619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116323076 | Completed | 18360 | 18360 | 2022-05-27 | 2022-09-29
NARMADAPURAM / HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/3745131 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118178159 | Completed | 18360 | 18360 | 2022-05-27 | 2022-09-20
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/4570650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117474053 | Completed | 23490 | 22014 | 2024-11-05 | 2026-05-27
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/4993646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114689893 | Completed | 23490 | 23292 | 2025-03-20 | 2025-12-25
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/4993647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114689949 | Physically Completed | 23490 | 23157 | 2025-03-20 | 2026-08-04
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/4998044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116314063 | Completed | 23490 | 23040 | 2025-03-20 | 2025-12-25
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/4998345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115227477 | Completed | 23490 | 22914 | 2025-03-20 | 2025-12-03
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/4998694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116139666 | Completed | 23490 | 23040 | 2025-03-20 | 2025-12-25
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/4998696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116140632 | Completed | 23490 | 22968 | 2025-03-20 | 2026-05-27
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/5000594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117473868 | Completed | 23490 | 23040 | 2025-03-20 | 2025-12-03
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/5000595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117473946 | Completed | 23490 | 23166 | 2025-03-20 | 2025-12-25
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/5000596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117474146 | Completed | 23490 | 23103 | 2025-03-20 | 2025-12-25
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/5000597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117474438 | Completed | 23490 | 23166 | 2025-03-20 | 2025-12-25
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/5004880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118177896 | Completed | 23490 | 22968 | 2025-03-20 | 2026-05-27
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/5105735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149984830 | Completed | 23490 | 23103 | 2025-03-20 | 2025-12-25
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/5106077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150102192 | Completed | 23490 | 23166 | 2025-03-20 | 2025-12-25
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/5234071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116112698 | Completed | 23490 | 23229 | 2025-08-12 | 2026-05-27
NARMADAPURAM / HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/533106 — Construction of IAY House -IAY REG. NO. MP2879042 | Completed | 15030 | 15455 | 2017-02-02 | 2018-05-20
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/5331932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116141467 | Completed | 23490 | 23490 | 2025-04-22 | 2025-12-25
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/5778026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4928704 | Physically Completed | 23490 | 22968 | 2025-09-23 | 2026-05-03
NARMADAPURAM / HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003029/IF/IAY/976801 — Construction of IAY House -IAY REG. NO. MP3753544 | Completed | 15480 | 15486 | 2017-05-18 | 2018-05-20
NARMADAPURAM / HOSHANGABAD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1732003029/LD/22012034368636 — PARRADEH SHANTIDHAM NIRMAN | Deleted | 0 | 0 | 2018-04-14
NARMADAPURAM / HOSHANGABAD | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1732003029/LD/35 — पर्रादेह भूमिशिल्‍प मनफूल / भागचद्र | Completed | 23150 | 2658 | 2009-06-07 | 2009-06-14
NARMADAPURAM / HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1732003029/PG/22012034366060 — KHEL MAIDAN GRAM PARRADEH | Completed | 271926.35 | 120121.8 | 2019-07-18 | 2021-05-15
NARMADAPURAM / HOSHANGABAD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034154822 — पर्रादेह (पंच परमेश्‍वर) करण मीणा से रामनाथ के घर तक सी.सी. रोड व नाली निर्माण | Completed | 35012 | 29950 | 2012-11-16 | 2012-11-28
NARMADAPURAM / HOSHANGABAD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034154989 — पर्रादेह (पंच परमेश्‍वर) विजय के घर के पीछे नहर तक सी.सी. रोड व नाली निर्माण | Completed | 19619 | 20144 | 2012-10-29 | 2012-11-03
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034168559 — परादेह गंगाराम मेहरा के मकान से सवराज भवन तक सी०सी | Completed | 147415 | 128841.9 | 2013-05-31 | 2015-03-22
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034183997 — पर्रादेह पंच परमेश्‍वर धनपाल प्रजापति के घर से प्र | Completed | 10744 | 8970.98 | 2013-09-19 | 2015-03-22
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034196959 — पर्रादेह हासलपुर प्रा.शा. भवन से पवन मेहरा के घर त | Completed | 108830 | 107983 | 2014-01-02 | 2014-10-10
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034201372 — पर्रादेह प्रीतम मीना के घर से पवन मेहरा के घर तक स | Completed | 18050 | 18004 | 2014-01-30 | 2014-10-10
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034201375 — पर्रादेह हेंडपंप के पास पी.एम.जी.एस.वाय. रो से डों | Completed | 6419 | 6196 | 2014-01-30 | 2014-10-10
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034202855 — पर्रादेह सी.सी. रोड से उपस्‍वास्‍थ्‍य केन्‍द्र भवन | Completed | 103883 | 103742 | 2014-02-06 | 2014-10-10
NARMADAPURAM / HOSHANGABAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034294184 — पर्रादेह पंच.पर. सी.सी. रोड से रामप्रसाद वर्मा के घर तक सी.सी. रोड निर्माण | Completed | 25089 | 23850 | 2015-12-31 | 2016-05-30
NARMADAPURAM / HOSHANGABAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034294187 — पर्रादेह सी.सी. रोड से हरिचरण वर्मा के घर तक सी.सी. रोड निर्माण | Completed | 35125 | 33405 | 2015-12-24 | 2016-05-30
NARMADAPURAM / HOSHANGABAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034303156 — c.c. road rajendra verma ke makan se aage | Deleted | 0 | 0 | 2016-01-26
NARMADAPURAM / HOSHANGABAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034303157 — c.c.road se barjoribaba tak c.c.road | Deleted | 0 | 0 | 2016-01-26
NARMADAPURAM / HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034323296 — पर्रादेह मनोहर वर्मा के घर से पूर्व निर्मित रोड तक सी सी रोड निर्माण | Closed | 0 | 0 | 2017-04-14
NARMADAPURAM / HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034326307 — पर्रादेह नर्मदाप्रसाद के घर से मनमोहन चौधरी के घ्‍ार की ओर सी सी रोड ि‍निर्माण | Completed | 8355 | 7014 | 2017-02-16 | 2017-10-18
NARMADAPURAM / HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034329394 — PARRADEH RAMESH VERMA KE GHAR SE CHAGAN VERMA KE GHAR KI OR C.C.ROAD NIRMAN | Completed | 23812 | 23018 | 2017-03-16 | 2017-12-20
NARMADAPURAM / HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034329507 — PARRADEH BAINI PRASAD KE GHAR SE BHAGIRATH PRAJAPATI KE GHARTAK C.C.ROAD NIRMAN | Completed | 20888 | 20640 | 2017-06-08 | 2017-10-03
NARMADAPURAM / HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034329519 — PARRADEH MANMOHAN VERMA KE GHAR SE MANOHAR VERMA KE GHAR TAK C.C.ROAD NIRMAN | Completed | 1336800000 | 12900 | 2017-05-25 | 2017-10-25
NARMADAPURAM / HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034360910 — CC Road and nali nirman shree Ravishankar Varma ke ghar se Barjori Baba ki or | Completed | 65683 | 65316 | 2017-08-26 | 2017-11-20
NARMADAPURAM / HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034375403 — Mata mandir chouk se harprasad meena ke ghar ki or CC road avm nali nirman renuel code | Completed | 28593 | 28362 | 2018-10-04 | 2018-12-30
NARMADAPURAM / HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034375547 — PARRADEH ME ANTARIK MARG NIRMAN | Deleted | 0 | 0 | 2017-10-02
NARMADAPURAM / HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034438206 — Laljiram sen ke ghar se Karan meena ke ghar tk cc road & nali nirman | Closed | 0 | 0 | 2018-12-30
NARMADAPURAM / HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034438209 — Balkishan meena ke khalian se Maa Narmada ji ke ghat ki or cc road & nali nirman Hasalpur | Deleted | 0 | 0 | 2018-12-30
NARMADAPURAM / HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034447096 — LALJI RAM SEN KE GHAR SE VISHRAM MEHRA KE GHAR TAK C.C.ROAD EVAM NALI NIRMAN | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034447099 — SHASHKIYA PRATHMIK SHALA HASALPUR ME C.C.KARY | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034447102 — SARVAN MEENA KE KE KHALIYAN SE AAGE NALE TAK C.C ROAD & NALI NIRMAN | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034447103 — NALE SE MAA NARMDA GHAT KI OR C.C.ROAD &NALI NIRMAN | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034447688 — Lalji ram sen ke ghar se Vishram Mehra ke ghar ki or CC Road & nali nirman | Completed | 56640 | 36438 | 2019-03-01 | 2019-05-10
NARMADAPURAM / HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003029/RC/22012034447691 — Sarwan Meena ke Khalihan se aage nale tk CC road & nali nirman Hasalpur | Completed | 36375 | 33630 | 2019-03-01 | 2020-10-20
NARMADAPURAM / HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003029/RC/22012034448461 — Nale se Maa Narmada ji ki or CC road avm Nali Nirman Hasalpur | Completed | 59673 | 41536 | 2019-03-07 | 2019-12-12
NARMADAPURAM / HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034448466 — Shaskiy Prathmik Shala me CC Nirman Karya Hasalpur | Completed | 14918 | 10964 | 2019-03-07 | 2019-05-10
NARMADAPURAM / HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003029/RC/22012034510270 — pradhanmantri sadak jod se aage chirongilal meena ke ghar tak c.c.road &nali nirman gram hasalpur | Closed | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034510276 — shashkiy madhymik shala me c.c.kary gram parradeh | Closed | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003029/RC/22012034510277 — manphool mehra ke ghar se aage narmda nadi ki or c.c.road nirman gram hasalpur | Closed | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034510278 — gangaram mehra ke ghar se swaraj bhavan tak c.c.road with nali nirman gram parradeh | Closed | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034510279 — amarsingh verma ke ghar se aage c.c.road nirman gram parradeh | Closed | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034510280 — premnarayan verma ke ghar se aage chainsingh verma ke ghar tak c.c.road with nali nirman parradeh | Closed | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1732003029/RC/22012034510282 — khet sadak brajkishore yadav ke khet se keshrinandan ke khet tak | Closed | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034544232 — c.c.road nirman narmda ghat road se bhairab baba ki or | Closed | 0 | 0 | 2020-04-14
NARMADAPURAM / HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034544858 — सी सी रोड निर्माण नर्मदा घाट रोड से भैरब बाबा चबूतरा तक | Completed | 19275 | 18240 | 2020-10-22 | 2020-11-23
NARMADAPURAM / HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034547141 — c.c.road nirman barjori baba se hillalore nale ki or parradeh | Completed | 43629 | 43219.8 | 2020-11-19 | 2021-04-18
NARMADAPURAM / HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034550206 — सीमेंटीकरण कार्य बरजोरी बाबा चबूतरे के पास | Completed | 24603 | 22800 | 2020-12-10 | 2021-01-10
NARMADAPURAM / HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034577236 — hendpump tirahe hasalpur me puliya evam c.c. road nirman puliya | Completed | 28857 | 27792 | 2021-08-13 | 2021-09-13
NARMADAPURAM / HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034581636 — c.c.road nirman hasalpur tirahe per shesh kary | Completed | 21415 | 20844 | 2021-09-03 | 2021-12-15
NARMADAPURAM / HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1732003029/RC/22012034607352 — sudur sadak nirma shanti dham parisar tak gram parradeh | Closed | 0 | 0 | 2022-01-26
NARMADAPURAM / HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034650028 — GRAM HASALPUR NARMDAGHAT KA SHESH NIRMAN KARY | Completed | 36741 | 36471 | 2023-09-05 | 2024-01-07
NARMADAPURAM / HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034654273 — Vidhayak nidhi sadak se puliya tak c.c. Road v nali nirman hasalpur | Completed | 20135 | 20029 | 2023-09-26 | 2024-01-04
NARMADAPURAM / HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034654286 — Madhymik shala parradeh ka cementikaran kary | Completed | 41600 | 41439 | 2023-09-26 | 2024-01-19
NARMADAPURAM / HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034666275 — prabhudayal ke makan se prakash barkhane ke makan tak c,c,road vnali nirman | Completed | 40184 | 33592 | 2023-10-07 | 2024-02-10
NARMADAPURAM / HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034666365 — ajeet verma ke makan se sachin ke khet ki or c.c.road nirman | Closed | 15842 | 0 | 2023-08-16
NARMADAPURAM / HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003029/RC/22012034666382 — premnarayan verma ke makan se ekakshtak c.c.road nirman | Completed | 8090 | 7236 | 2023-10-07 | 2024-09-04
NARMADAPURAM / HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003029/RC/22012034684560 — c.c.road evam ek taraf nali nirman jagdish meena ke ghar se pritam meena ke ghar ki or | Closed | 0 | 0 | 2023-10-02
NARMADAPURAM / HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003029/RC/22012034684562 — c.c.road evam ek taraf nali nirman jagdish meena ke ghar se pritam meena ke ghar ki or | Closed | 15846 | 0 | 2023-10-02
NARMADAPURAM / HOSHANGABAD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of WBM Roads for Community / Construction of WBM Roads for Community | Construction of Road and Culvert | 1732003029/RC/22012034821388 — nehar se haricharnd ke khet ki aur wbm road | Approved | 20000 | 0 | 2024-04-14
NARMADAPURAM / HOSHANGABAD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034826415 — cc road renewal bhagwan singh meena ke ghar se vijay meena ke ghar ki aur | Completed | 47500 | 47385 | 2024-09-17 | 2026-04-24
NARMADAPURAM / HOSHANGABAD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034826881 — cc road evam nali nirman jagdiesh meena ke ghar se pritam meena ke ghar ki aur | Completed | 15900 | 15795 | 2024-10-01 | 2026-04-24
NARMADAPURAM / HOSHANGABAD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034826956 — cc road bhawan singh meena ke ghar se nehar ki aur | Completed | 9400 | 9234 | 2024-10-01 | 2026-04-24
NARMADAPURAM / HOSHANGABAD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003029/RC/22012034827491 — cc road raman meena ke ghar se bhurelal meena ke ghar ki aur | Completed | 11700 | 11421 | 2024-10-01 | 2026-04-24
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034185756 — पर्रादेह हासलपुर शौचालय रामेश्‍वर/मेंहगू | Completed | 4400 | 4390 | 2013-12-19 | 2014-10-30
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034185760 — पर्रादेह शौचालय सुनील/गुलदार | Completed | 4400 | 4390 | 2013-12-19 | 2014-10-30
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034194612 — Parradeh Toilat Prakash/Kaliram | Completed | 4400 | 4390 | 2014-01-16 | 2014-10-30
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034194710 — Parradeh Toilat Santosh Sabulal | Completed | 4400 | 4390 | 2014-01-16 | 2014-10-30
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034197199 — PARRADEH TOILET GULDHAR KUNJILAL | Completed | 4400 | 4390 | 2014-01-23 | 2014-10-30
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034197201 — PARRADEH TOILET RAMESVAR RAMDAS | Completed | 4400 | 4390 | 2014-01-23 | 2014-10-30
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034200205 — PARRADEH TOILET BISRAM HANNU | Completed | 4400 | 4390 | 2014-01-31 | 2014-10-30
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034202187 — PARADEH TOILET KAMAL MANGILAL | Completed | 4400 | 4390 | 2014-02-06 | 2014-10-30
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034202191 — PARADEH TOILET SANTOSH PHULCHAND | Completed | 4400 | 4400 | 2014-02-06 | 2015-03-15
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034205268 — PARRADEH TOILET RAMESH PRABHU | Completed | 4400 | 4390 | 2014-02-11 | 2014-10-30
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034205273 — PARRADEH TOILET AMARSHINGH RAMDAYAL | Completed | 4400 | 4390 | 2014-02-11 | 2014-10-30
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034207358 — PARRADEH TOILET RAMBHAROSH SHOBHARAM | Completed | 4400 | 4400 | 2014-02-20 | 2015-03-15
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034214339 — PARRADEH TOILET LAXMINARAYAN GOVIND | Completed | 5400 | 5080 | 2014-03-06 | 2015-03-15
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034214709 — PARRADEH TOILET RAMADHAR MEHGU | Completed | 5400 | 5080 | 2014-03-06 | 2015-03-15
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034216554 — PARRADEH TOILET RAJU SHOBHARAM | Completed | 5400 | 5278 | 2014-03-13 | 2015-03-15
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034216561 — PARRADEH TOILET SURESH KACHRU | Completed | 5400 | 5278 | 2014-03-13 | 2015-03-15
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034219062 — PARADEH TOILET PRAHLAD HANNU | Deleted | 5400 | 0 | 2014-01-26
NARMADAPURAM / HOSHANGABAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034228959 — पर्रादेह शौचालय रामप्रसाद/फूलचंद/राजाराम/बालकदास/बनवारीलाल | Completed | 27000 | 25872 | 2014-05-01 | 2015-03-15
NARMADAPURAM / HOSHANGABAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034235280 — PARADEH TOILET RAMESH LATABAI GEETABAI CHIRONJI RAJENDRA | Completed | 27000 | 26971 | 2014-05-24 | 2015-02-05
NARMADAPURAM / HOSHANGABAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034238859 — पर्रादेह 5 शौचायल सुनील, आसाराम संतोष मनीष, राम | Completed | 27000 | 25872 | 2014-06-05 | 2015-02-05
NARMADAPURAM / HOSHANGABAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034240736 — पर्रादेह शौचालय 5 पन्‍नालाल, नागेश, नन्‍हे, पन्‍ना, राममोहन | Completed | 27000 | 25872 | 2014-06-12 | 2015-02-05
NARMADAPURAM / HOSHANGABAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034245906 — PARRADEH TPILET 5 SUNDAR GEETA SHIVNARAYAN PREM MA | Completed | 27000 | 23360 | 2014-06-28 | 2015-03-15
NARMADAPURAM / HOSHANGABAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034248865 — पर्रादेह शौचालय 5 खूबचंद नर्मदा सुन्‍दरलाल कैलाश क | Completed | 27000 | 24930 | 2014-07-10 | 2015-03-15
NARMADAPURAM / HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003029/RS/22012034310212 — पर्रादेह सार्वजनिक नााडेप निर्माण इमली नाले रामसिंह चैनसिंह के घर केे पास | Deleted | 28155 | 0 | 2016-12-08
NARMADAPURAM / HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034369948 — HASALPUR TULSIRAM/SHANKERLAL MEENA SOCHALAY NIRMAN | Completed | 9800 | 9837 | 2017-09-07 | 2018-07-09
NARMADAPURAM / HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/22012034376603 — PARRADEH RAMSINGH/NANDLAL VERMA SOUCHALY NIRMAN | Deleted | 9800 | 0 | 2017-04-18
NARMADAPURAM / HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003029/RS/22012034478131 — nadef nirman madhymik shala puliya ke pass parradeh | Closed | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003029/RS/22012034478132 — nadef nirman randhal mod per hasalpur | Closed | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732003029/RS/22012034499297 — R CC Nali Nirmaan Dhannaa lal Ke Makan Se madhmik Shala Puliya tak | Completed | 68170 | 65550 | 2020-11-12 | 2021-02-21
NARMADAPURAM / HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732003029/RS/22012034585160 — R.c.c NALi NiRMAN SANTOSH MEHRA KE GHAR SE puLiYA Ki OR | Completed | 30370 | 29529 | 2021-10-29 | 2022-01-15
NARMADAPURAM / HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & Maint of NADEP Compost for Community / Repair and Maintenance of NADEP Compost structure for Community | Repaire and Maint of NADEP/Vermi Compost Pit | 1732003029/RS/22012034643247 — nadef nirman manohar erma ke ghar ke pass parradeh | Closed | 0 | 0 | 2022-01-26
NARMADAPURAM / HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003029/RS/22012034643936 — based nirman madhyamik shala puliya ke pass parradeh | Closed | 0 | 0 | 2022-01-26
NARMADAPURAM / HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003029/RS/22012034643939 — based nirman rakshak mod per hasalpur | Closed | 0 | 0 | 2022-02-26
NARMADAPURAM / HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003029/RS/22012034643943 — nadef nirman prathmik shala ke samne hasLpur | Closed | 0 | 0 | 2022-01-26
NARMADAPURAM / HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732003029/RS/22012034704631 — BAIJNATH MEENA KE MAKAN SE PULIYA TAK R. C. C.NALI NIRMAN | Completed | 12972 | 12376 | 2023-10-03 | 2023-12-07
NARMADAPURAM / HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732003029/RS/22012035122928 — GRAM HASALPUR ME RAMESH KE GHAR SE PRADHANMANTRI SADAK KEPASS PULIYAKI OR R.C.C.NALI NIRMAN | Closed | 37292 | 0 | 2024-02-05
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/79986 — पर्रादेह शौचालय निर्माण सुनील/विश्राम | Completed | 5197 | 4999 | 2013-11-07 | 2015-05-20
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/79988 — पर्रादेह शौचालय निर्माण शिवनारायण/खुबचंद | Deleted | 5197 | 0 | 2013-11-07
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/83887 — पर्रादेह शौचालय दौलतराम/रामरतन | Deleted | 5197 | 0 | 2013-04-14
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003029/RS/83890 — पर्रादेह शौचालय तुलसीराम/रामरतन | Deleted | 5197 | 0 | 2013-11-28
NARMADAPURAM / HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | Upgradation/extension of panchayat Bhawan / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1732003029/SK/1507 — Bharat Nirman Rajeev Gandhi Sewa Kendra,PARRADEH | Completed | 118101 | 121771 | 2013-12-12 | 2015-03-22
NARMADAPURAM / HOSHANGABAD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1732003029/WC/22012034393062 — Bakaliya nale me gabian nirman Hasalpur | Completed | 60419.02 | 50924.02 | 2018-07-05 | 2020-06-30
NARMADAPURAM / HOSHANGABAD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1732003029/WC/22012034446064 — Parradeh Check Dam Nirman Parradeh | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / HOSHANGABAD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1732003029/WC/22012034446068 — Parradeh Check Dam Nirman Hasalpur Piliya nala | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1732003029/WC/22012034463808 — Parradeh Check Dam Nirman | Closed | 596281.84 | 0 | 2019-05-25
NARMADAPURAM / HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732003029/WC/22012034521125 — rain water harvesting prathmik shala parradeh | Closed | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732003029/WC/22012034521126 — rain water harvesting madymik shala parradeh | Deleted | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732003029/WC/22012034521127 — rain water harvesting anganwadi bhavan parradeh | Deleted | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732003029/WC/22012034521131 — rain water harvesting e.panchayat bhavan parradeh | Completed | 31352.13 | 9578 | 2020-02-27 | 2021-06-12
NARMADAPURAM / HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732003029/WC/22012034521132 — rain water harvesting prathmik shala hasalpur | Deleted | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732003029/WC/22012034521133 — rain water harvesting anganwadi bhavanhasalpur | Deleted | 0 | 0 | 2019-10-02
NARMADAPURAM / HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1732003029/WC/22012034672978 — CTR-Check dam nriman kevalari nadi par parradeh | Closed | 0 | 0 | 2021-04-14
NARMADAPURAM / HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003029/WC/22012034698472 — CTR-rcc nali nirman mata mandir ke pass | Completed | 32491 | 32421 | 2021-06-11 | 2021-09-06
NARMADAPURAM / HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1732003029/WC/22012034914481 — check dem nirman kehlati nadi per badodiya ghat parradeh | Closed | 0 | 0 | 2022-01-26
NARMADAPURAM / HOSHANGABAD | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003029/WC/22012034944340 — पर्रादेह अम़त सरोवर अन्‍तर्गत केवलारी नदी पर बडोदिया घाट परस्‍टापडेम निर्माण | Closed | 0 | 0 | 2022-04-01
NARMADAPURAM / HOSHANGABAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1732003029/WC/22012034944343 — पर्रादेह अम़त सरोवर अन्‍तर्गत केवलारी नदी पर बडोदिया घाट परस्‍टापडेम निर्माण | Closed | 240000 | 2856 | 2022-04-19
NARMADAPURAM / HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1732003029/WC/22012035142720 — prabhu harijanke ghar se prakash ke ghar tak c.cnali nirman 160meter | Completed | 18069 | 17361 | 2023-10-07 | 2026-04-24
NARMADAPURAM / HOSHANGABAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1732003029/WC/22012035164441 — GRAM HASALPUR ME RAMESH KE GHAR SE PRADHANMANTRI SADAK KEPASS PULIYAKI OR R.C.C.NALI NIRMAN | Completed | 37292 | 36917 | 2024-03-05 | 2024-09-04
NARMADAPURAM / HOSHANGABAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1732003029/WC/22012035177618 — PRABHU HARIJAN KE GHAR SE PRAKASH BARKHANE KE GHAR TAK C.C.NALI NIRMAN | Closed | 18069 | 0 | 2023-10-02
NARMADAPURAM / HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1732003029/WC/22012035312281 — CTR SOCK PIT UPSWATH KENDRA HASALPUR | Approved | 5274 | 0 | 2025-04-14
NARMADAPURAM / HOSHANGABAD | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732003029/WC/663 — पर्रादेह शासकीय भूमि पर व़क्षारोपण पर निर्मलनीर | Completed | 91567 | 92847 | 2010-05-27 | 2012-07-03
NARMADAPURAM / HOSHANGABAD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732003029/WC/675 — पर्रादेह सोक्‍ता गड्रडा स्‍वराज भवन के सामने | Completed | 6815 | 6040 | 2011-06-05 | 2012-07-23
NARMADAPURAM / HOSHANGABAD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732003029/WC/676 — पर्रादेह सोक्‍ता गड्रडा प्रा.शाला भवन के हेण्‍डपंप पर | Completed | 6815 | 6667 | 2011-06-05 | 2012-07-23