## Work List
Exported on: 2026-10-08 02:58:30
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: ROJHDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1732003034/AV/22012034399245 — GRAM ROZDA ME KHEL MAIDAN NIRAMN | Ongoing | 149786.67 | 0 | 2019-03-08
NARMADAPURAM / HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Drought Proofing | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003034/DP/22012034444304 — Chek Dam Nirman - Rojhda - Hathed nadi per | Ongoing | 572035.52 | 0 | 2019-03-08
NARMADAPURAM / HOSHANGABAD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Avenue Plantation for Community | Plantation | 1732003034/DP/22012034625611 — Rojhada Talab kinare vriksharopan karya | Ongoing | 453563.17 | 0 | 2024-08-01
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732003034/IF/22012035555741 — CTR JGSA Brijlal / Chhannulal ke khet me Khet Talab Nirman | Approved | 55865.38 | 0 | 2025-04-14
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732003034/IF/22012035558722 — ROJHDA CTR JGSA BHOJRAJ / NARMADA PRASAD KE KET ME KHET TALAB NIRMAN | Ongoing | 55865.38 | 0 | 2025-06-01
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732003034/IF/22012035589550 — Ek Bagiya Ma Ke Naam Sandhya bai / Santosh Rajput Dudugaon Rojhada | Ongoing | 266577.25 | 0 | 2025-09-02
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732003034/IF/22012035589558 — Ek Bagiya Ma Ke Naam Basanti bai / Nandkishor Kushwaha Dudugaon Rojhda | Ongoing | 159501.07 | 0 | 2025-09-11
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/5004767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118142850 | Completed | 23490 | 0 | 2025-03-19 | 2026-08-12
NARMADAPURAM / HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/5005458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118743336 | Physically Completed | 23490 | 1692 | 2025-03-19 | 2026-08-02
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/5121017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117837125 | Completed | 23490 | 0 | 2025-08-27 | 2026-08-12
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/5125004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148894282 | Ongoing | 27000 | 0 | 2025-08-27
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/5589585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118143863 | Ongoing | 27000 | 261 | 2025-08-27
NARMADAPURAM / HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/5590501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117665308 | Ongoing | 27000 | 0 | 2026-04-01
NARMADAPURAM / HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/5620136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117659383 | Ongoing | 27000 | 0 | 2026-08-12
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/5620250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116378062 | Completed | 23490 | 0 | 2025-07-30 | 2026-08-12
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/5687761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116377022 | Ongoing | 27000 | 261 | 2025-08-27
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/5862486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122776851 | Approved | 27000 | 0 | 2025-09-09
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/5862512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118233305 | Completed | 23490 | 0 | 2026-02-11 | 2026-08-12
NARMADAPURAM / HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/6076376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117647405 | Ongoing | 27000 | 6300 | 2026-08-12
NARMADAPURAM / HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/6076395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117656395 | Ongoing | 27000 | 18900 | 2026-07-08
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/6076470 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117716125 | Approved | 27000 | 0 | 2026-01-15
NARMADAPURAM / HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/6077463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118140706 | Ongoing | 27000 | 8400 | 2026-08-19
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/6078546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118724931 | Approved | 27000 | 0 | 2026-01-15
NARMADAPURAM / HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/6082799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122811431 | Ongoing | 27000 | 18900 | 2026-06-24
NARMADAPURAM / HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/6097994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147154213 | Ongoing | 27000 | 21000 | 2026-06-24
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/6255076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118230324 | Approved | 27000 | 0 | 2026-01-15
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/6256724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118630703 | Approved | 27000 | 0 | 2026-01-15
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/6289910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119847182 | Approved | 27000 | 0 | 2026-01-15
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/6300555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118172174 | Approved | 27000 | 0 | 2026-03-17
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/6358086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117662114 | Approved | 27000 | 0 | 2025-07-16
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003034/IF/IAY/6400602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118401651 | Approved | 27000 | 0 | 2026-01-15
NARMADAPURAM / HOSHANGABAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732003034/WC/22012034554356 — Rojhada - Dudugaon - Ramkrishna Bakoriya ke ghar se Jalkundi nadi tak nali | Ongoing | 79375.17 | 0 | 2024-02-29
NARMADAPURAM / HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1732003034/WC/22012035282810 — Dudugav CTR JGSA प्रा शाला हेंडपंप सोकपिट | Approved | 52290 | 0 | 2025-04-14
NARMADAPURAM / HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1732003034/WC/22012035282851 — MOFADA CTR JGSA प्रा शाला हेंडपंप सोकपिट | Approved | 5229 | 0 | 2025-04-14
NARMADAPURAM / HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1732003034/WC/22012035282899 — KHARAR CTR JGSA प्रा शाला हेंडपंप सोकपिट | Approved | 52290 | 0 | 2025-04-14
NARMADAPURAM / HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1732003034/WC/22012035298443 — ROJHDA CTR JGSA RAIN WATER HARVESTING PANCHAYAT BHAVAN | Approved | 0 | 0 | 2025-04-14