## Work List
Exported on: 2026-10-01 05:31:05
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: LOHARIYAKALA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1732003039/AV/22012034548847 — shantidham nirmaan kary gram somalwada kalan | Ongoing | 195535.43 | 0 | 2021-04-06
NARMADAPURAM / HOSHANGABAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732003039/DP/22012034568449 — lohariya kalan se kandai pahuch marg tak plantation | Ongoing | 407825.29 | 0 | 2022-09-29
NARMADAPURAM / HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1732003039/FP/22012034369867 — LOHARIYAKALA MANGALSINGH KE BADE SE RAMESH MALVIYA KE GHAR KI AUR RCC NALI NIRMAN | Ongoing | 101226 | 0 | 2021-03-20
NARMADAPURAM / HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1732003039/IF/22012034573477 — Hitgrahi Damyanti bai/shivratan pashu shed kary somalwada kalan | Ongoing | 63531.21 | 0 | 2020-10-30
NARMADAPURAM / HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1732003039/IF/22012034573479 — Hitgrahi Parvati bai/ramphal bakri shed kary gwadi khurd | Ongoing | 46636.05 | 0 | 2020-11-27
NARMADAPURAM / HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1732003039/IF/22012034573480 — hitgrahi kubja bai/deviram bakri shed kary gwadi khurd | Ongoing | 46636.05 | 0 | 2020-11-27
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732003039/IF/22012035552468 — CTR JGSA Doulatsing/Munishvarsing ke khet me Khet Talab Nirman | Ongoing | 147621.16 | 0 | 2025-05-30
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732003039/IF/22012035552474 — CTR JGSA Gyansing/Wishvanath ke khet me Khet Talab Nirman | Ongoing | 55865.38 | 0 | 2025-05-30
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732003039/IF/22012035614827 — Ek Bagiya Ma Ke Naam SARIKA CHOUHAN Lohariyakala | Ongoing | 263510.03 | 0 | 2025-09-11
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732003039/IF/22012035614829 — Ek Bagiya Ma Ke Naam ANNU BAI RAJPUT Lohariyakala | Ongoing | 159501.07 | 0 | 2025-09-18
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5115004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116042160 | Ongoing | 27000 | 0 | 2025-04-03
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5118335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149826264 | Ongoing | 27000 | 0 | 2025-08-25
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5127910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131267800 | Completed | 23490 | 0 | 2025-05-22 | 2026-08-12
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5128306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144550148 | Ongoing | 27000 | 12600 | 2025-08-26
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5460227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148605907 | Ongoing | 27000 | 0 | 2025-08-25
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5461034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131268336 | Ongoing | 27000 | 0 | 2025-08-25
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5507066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150814173 | Ongoing | 27000 | 0 | 2025-08-25
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5511362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150974125 | Ongoing | 27000 | 6300 | 2025-08-25
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5579346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131267702 | Ongoing | 27000 | 0 | 2025-08-07
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5687575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116465022 | Completed | 23490 | 0 | 2025-08-25 | 2026-08-12
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5823613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128510623 | Ongoing | 27000 | 300 | 2026-02-12
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5824894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121683150 | Ongoing | 27000 | 0 | 2026-02-26
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5827893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124155035 | Ongoing | 27000 | 4500 | 2026-02-26
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5845562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124170277 | Ongoing | 27000 | 2400 | 2026-02-12
NARMADAPURAM / HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/585565 — Construction of IAY House -IAY REG. NO. MP1944150 | Ongoing | 27000 | 0 | 2017-02-24
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5862498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126857493 | Ongoing | 27000 | 8400 | 2026-01-29
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5907135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116465111 | Approved | 27000 | 0 | 2026-02-09
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5911041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131269442 | Approved | 27000 | 0 | 2026-02-09
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5926270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119543639 | Approved | 27000 | 0 | 2026-02-09
NARMADAPURAM / HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5927500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117780831 | Ongoing | 27000 | 8400 | 2026-08-13
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/5928327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150974608 | Approved | 27000 | 0 | 2026-02-09
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/6164834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120816332 | Approved | 27000 | 0 | 2026-02-09
NARMADAPURAM / HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003039/IF/IAY/6166110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151192444 | Approved | 27000 | 0 | 2026-02-09
NARMADAPURAM / HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003039/RC/22012034449824 — सदनलाल के घर से मनोज के खेत तक सी.सी.रोड व नाली निर्माण | Ongoing | 50950 | 0 | 2019-03-09
NARMADAPURAM / HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003039/RS/22012034478020 — पूनम सिंह के घर के पास नाडेप निर्माण | Ongoing | 12284.01 | 0 | 2020-11-27
NARMADAPURAM / HOSHANGABAD | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732003039/RS/22012034649338 — LOHARIYAKAL DHANSINGH KE GHAR SE HASAN BHAIJAN KE GHAR TAK RCC NALI NIRMAN | Ongoing | 47580 | 0 | 2022-04-28
NARMADAPURAM / HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003039/WC/22012035142484 — Lohariyakala - Somalwadakal- Kishan ke ghar se mata mandir tak rcc nali nirman | Ongoing | 25979 | 0 | 2023-10-06
NARMADAPURAM / HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003039/WC/22012035142529 — Lohariyakala - Kandaihimmat se horiyapipar road per paip puliya kary | Ongoing | 14995 | 0 | 2023-10-06
NARMADAPURAM / HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003039/WC/22012035142556 — Lohariyakala - somalwadakal - rahim ke ghar se lekr ajju ke ghar tak rcc nali nirman | Ongoing | 40318 | 0 | 2023-10-06
NARMADAPURAM / HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003039/WC/22012035284549 — Sokta gadda school ke pass lohariya kalan | New | 0 | 0 | 2025-04-20
NARMADAPURAM / HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003039/WC/22012035284575 — Sokta gadda school ke pass lohariya kalan | Approved | 0 | 0 | 2025-04-20
NARMADAPURAM / HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003039/WC/22012035284586 — CTR samudayik sok pit sashkiya school ke pass kandai himmat | Approved | 0 | 0 | 2025-04-20
NARMADAPURAM / HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1732003039/WC/22012035290124 — CTR JGSA LOHARIYA KALAN DUGWELL RICHARCH SHAFT SAMUDAYIK | Approved | 17120 | 0 | 2025-04-24