## Work List
Exported on: 2026-10-11 19:50:48
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: GURADIYAMOTI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Unskilled wage for Bio gas plant for community / Construction of Biogas Plant for Community | Bio-gas plant | 1732004004/AV/22012034658735 — verchharoupan puliya se guradiyamoti | Ongoing | 429602.82 | 0 | 2024-07-28
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Unskilled wage for Bio gas plant for community / Construction of Biogas Plant for Community | Bio-gas plant | 1732004004/AV/22012034658736 — verchharoupan guradiya se jhaksar ki our jhalsar | Ongoing | 452789.54 | 0 | 2024-07-28
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Line Plantation of Forestry Trees for Community | Plantation | 1732004004/DP/22012034562664 — virksharopan samudak jhalsarset | Ongoing | 411218.19 | 0 | 2022-10-12
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1732004004/IF/22012035341550 — JSGA Dug well Recharge pit Laxmibai/Ramesh GP Guradiamoti | Approved | 0 | 0 | 2025-04-01
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/4559196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114165511 | Completed | 23490 | 0 | 2025-03-17 | 2026-08-04
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/4995801 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114161832 | Ongoing | 27000 | 0 | 2025-10-02
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5095271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142221538 | Ongoing | 27000 | 0 | 2025-07-12
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5096731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145086485 | Ongoing | 27000 | 0 | 2025-08-10
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5096828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145174938 | Ongoing | 27000 | 0 | 2025-07-12
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5097303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145668190 | Ongoing | 27000 | 0 | 2025-07-12
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5097426 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145753987 | Ongoing | 27000 | 0 | 2025-04-02
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5115511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113708463 | Completed | 23490 | 0 | 2025-03-24 | 2026-08-04
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5132591 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145137426 | Ongoing | 27000 | 0 | 2026-03-01
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5687346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129524959 | Ongoing | 27000 | 0 | 2025-12-18
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5903165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141812403 | Ongoing | 27000 | 6300 | 2026-06-23
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5904020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114163273 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5904609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145715108 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5905142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145878771 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5906221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129509666 | Ongoing | 27000 | 0 | 2026-09-22
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5906540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145724425 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5909813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106467773 | Physically Completed | 27000 | 0 | 2026-01-27 | 2026-09-13
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5909820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145360791 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5912386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145671600 | Ongoing | 27000 | 0 | 2026-06-07
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5912484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114766678 | Ongoing | 27000 | 0 | 2026-10-07
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5912778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114165066 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5912910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146484856 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5912982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145178367 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5914012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145675216 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5914619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145665884 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5915296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145362254 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5915809 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131688798 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5916495 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145349490 | Ongoing | 27000 | 0 | 2026-04-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5916536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145669432 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5917463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145676669 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5917588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114163605 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5917946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145721532 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5918008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131689620 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5918134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131688919 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5918523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146417750 | Ongoing | 27000 | 4200 | 2026-04-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5918938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145673751 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5919229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145666751 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5920432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114162945 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5922527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114168995 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5923088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131689763 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5923173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146470590 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5925152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145118004 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5925330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113709246 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5925988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146050218 | Ongoing | 27000 | 0 | 2026-05-02
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5926139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145706723 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5926195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114162383 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5927261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142222858 | Physically Completed | 23490 | 4200 | 2026-05-02 | 2026-08-09
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5927307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145781676 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5927446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146432677 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5928170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141813835 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5928522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146255901 | Ongoing | 27000 | 6300 | 2026-06-07
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5929996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145704396 | Ongoing | 27000 | 0 | 2026-04-11
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5930739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145122627 | Ongoing | 27000 | 0 | 2026-04-11
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/5931281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131689526 | Ongoing | 27000 | 0 | 2026-04-11
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6125533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142218884 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6127124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145697046 | Approved | 27000 | 0 | 2026-02-28
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6127136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145732472 | Approved | 27000 | 0 | 2026-02-28
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6131531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145368668 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6132208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145750850 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6132214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145787677 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6138653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145761218 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6143877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148886633 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6143885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148898003 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6145119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145700916 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6147890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145095237 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6148065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113707943 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6148249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131689321 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6148645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148486638 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6148646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106467131 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6151098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145111560 | Approved | 27000 | 0 | 2026-02-28
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6153355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145142549 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6153400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106469018 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6153781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131687615 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6153782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131687717 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6154876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146484920 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6156338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106917202 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6156402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145361188 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6157200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146433449 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6162284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145349472 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6162285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145349640 | Ongoing | 27000 | 0 | 2026-10-07
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6162286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145349663 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6162331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145183806 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6162433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146407557 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6163183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142030201 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6163238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106467648 | Ongoing | 27000 | 4200 | 2026-08-10
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6163269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149944826 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6163931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146047073 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6166136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113918298 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6167502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129513863 | Physically Completed | 27000 | 0 | 2026-02-25 | 2026-10-04
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6172508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141816132 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6172613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145153306 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6174003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148481798 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6180086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129499639 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6185824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130092022 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6186483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131689394 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6196659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145709666 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6197379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131689044 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6198343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145243547 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6202055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131688752 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6203722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145712002 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6204281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145729172 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6206999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145349649 | Ongoing | 27000 | 0 | 2026-10-07
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6207929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145099388 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6249973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113581472 | Approved | 27000 | 0 | 2026-03-26
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6250494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114166990 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6274575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145151002 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6306983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106466651 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6321000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114161002 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6321238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145245280 | Approved | 27000 | 0 | 2026-05-06
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6334459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131689659 | Approved | 27000 | 0 | 2026-04-01
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6335282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145797803 | Approved | 27000 | 0 | 2026-07-04
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6377306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145659838 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6382191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145773454 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6382220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145804301 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6382515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145776749 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6382732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145147998 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6391155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145793918 | Approved | 27000 | 0 | 2026-02-25
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004004/IF/IAY/6397276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146484969 | Approved | 27000 | 0 | 2026-05-06
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732004004/RC/22012034839872 — CC ROAD NIRMAN KARYA ANTRAM K GHAR SE ANUPSINGH KEER K GHAR TAK GP GURADIYAMOTI | Approved | 0 | 0 | 2025-01-24
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732004004/RS/22012035128818 — CC Nali Nirman Pretam Ke Ghar Se Ashok Ge Ghar Tak 15 F TH | Approved | 7700 | 0 | 2024-07-05
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732004004/RS/22012035129859 — PCC Nali pritam ke ghar se ashok ke ghar tak | Approved | 0 | 0 | 2024-06-13
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732004004/RS/22012035129862 — PCC Nali pritam ke ghar se ashok ke ghar tak | New | 0 | 0 | 2024-06-13
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732004004/RS/22012035129863 — PCC Nali pritam ke ghar se ashok ke ghar tak | New | 0 | 0 | 2024-06-13
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732004004/RS/22012035129864 — PCC Nali pritam ke ghar se ashok ke ghar tak | Approved | 8361 | 0 | 2024-06-13
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732004004/RS/22012035130438 — CC nali nirman santosh ke ghar se komal ke ghar tak | Approved | 0 | 0 | 2024-07-14
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732004004/RS/22012035130439 — CC nali nirman santosh ke ghar se komal ke ghar tak | Ongoing | 12000 | 0 | 2024-11-24
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732004004/RS/22012035130440 — CC nali nirman pritam ke ghar se ashok ke ghar tak | Approved | 8000 | 0 | 2024-06-13
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732004004/RS/22012035133775 — Rcc nali nirman shrikisan k ghar s shaitan ke ghar ki or GP Guradiamoti | Approved | 0 | 0 | 2024-06-08
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732004004/RS/22012035133777 — Rcc nali nirman shrikisan k ghar s shaitan ke ghar ki or GP Guradiamoti | Approved | 68096 | 0 | 2024-06-08
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1732004004/RS/VB/YD/22012035140222 — Constr of NADEP Compost structure for 1 | Approved | 0 | 0 | 2026-04-01