## Work List
Exported on: 2026-10-13 01:49:26
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BAHARPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / MAKHAN NAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1732004028/DP/22012034603712 — Vashudh vandan Amrit vatika high school mai | Ongoing | 55847.4 | 0 | 2024-01-04
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Line Plantation of Forestry Trees for Community | Plantation | 1732004028/DP/22012034628042 — Plantation work for road site sankar mandir se tari mohhalla tak | Approved | 0 | 0 | 2024-08-17
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Avenue Plantation for Community | Plantation | 1732004028/DP/22012034628044 — plantation maru nadi pul se anand conony tak | Ongoing | 453563.17 | 0 | 2024-10-04
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of Storm Water Drain for Community | Works for Flood Control and Protection | 1732004028/FP/22012034626919 — Construction of culvert work gp Bharpur | Ongoing | 965628.06 | 0 | 2021-11-10
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of minor Canal for Community / Construction of Branch Canal for Community | Construction of Canal | 1732004028/IC/22012034885706 — kachci nali nirmaan dp se badi nahar tak 1km | New | 0 | 0 | 2024-08-17
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732004028/IF/22012035541341 — jgsa form pond rajkumar/dalchand | Approved | 450885.64 | 0 | 2025-04-14
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732004028/IF/22012035633008 — EK BAGIYA MAA KE NAME HEMVATI / HARGOVIND | Approved | 0 | 0 | 2025-04-14
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5142960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121604979 | Completed | 23490 | 0 | 2025-03-26 | 2026-08-04
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5903493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115805942 | Ongoing | 27000 | 0 | 2026-08-27
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5903872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121604657 | Ongoing | 27000 | 0 | 2026-05-22
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5904843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119924879 | Ongoing | 27000 | 0 | 2026-09-12
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5905045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127993416 | Ongoing | 27000 | 0 | 2026-09-13
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5905111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115410887 | Ongoing | 27000 | 0 | 2026-09-10
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5906328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147717925 | Completed | 23490 | 0 | 2026-05-15 | 2026-08-04
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5907460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119928326 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5909609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147725736 | Approved | 27000 | 0 | 2026-02-08
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5910457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116408742 | Ongoing | 27000 | 0 | 2026-09-02
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5912035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119924289 | Physically Completed | 27000 | 4200 | 2026-05-22 | 2026-10-11
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5912586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119650527 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5912784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145669311 | Ongoing | 27000 | 12600 | 2026-08-12
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5914418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115806081 | Ongoing | 27000 | 6300 | 2026-08-11
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5918874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119933667 | Ongoing | 27000 | 0 | 2026-10-11
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5923245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118362306 | Ongoing | 27000 | 16200 | 2026-06-21
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5925534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115806371 | Ongoing | 27000 | 8400 | 2026-08-11
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5926310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118562229 | Ongoing | 27000 | 12600 | 2026-08-12
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5927972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115806171 | Physically Completed | 23490 | 4200 | 2026-05-15 | 2026-08-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5929807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115410461 | Approved | 27000 | 0 | 2026-02-08
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5930040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120817085 | Ongoing | 27000 | 0 | 2026-09-10
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/5930817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145662095 | Physically Completed | 23490 | 1800 | 2026-03-15 | 2026-07-19
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6123119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119924757 | Ongoing | 27000 | 3900 | 2026-08-16
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6123120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119928264 | Ongoing | 27000 | 4200 | 2026-08-14
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6127326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145408380 | Ongoing | 27000 | 0 | 2026-09-19
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6127496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115806251 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6127497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115806272 | Ongoing | 27000 | 0 | 2026-08-26
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6127649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115879283 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6128142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121588299 | Ongoing | 27000 | 2100 | 2026-08-14
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6133257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116927670 | Physically Completed | 27000 | 0 | 2026-08-27 | 2026-10-11
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6140114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119931227 | Ongoing | 27000 | 8400 | 2026-08-13
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6144941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118361625 | Ongoing | 27000 | 16200 | 2026-06-21
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6156439 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116408766 | Ongoing | 27000 | 6300 | 2026-08-11
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6163184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118361800 | Approved | 27000 | 0 | 2026-03-07
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6168203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115410745 | Approved | 27000 | 0 | 2026-02-28
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6168807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115805376 | Physically Completed | 27000 | 18000 | 2026-08-02 | 2026-10-11
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6170137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119587106 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6171889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120234213 | Physically Completed | 27000 | 16200 | 2026-08-02 | 2026-10-11
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6172483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118562263 | Ongoing | 27000 | 12600 | 2026-08-13
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6251672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115780200 | Approved | 27000 | 0 | 2026-04-06
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6275082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145668521 | Ongoing | 27000 | 0 | 2026-10-11
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6277457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148891289 | Ongoing | 27000 | 0 | 2026-10-11
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6277459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148903720 | Ongoing | 27000 | 0 | 2026-10-11
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6306902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118364104 | Approved | 27000 | 0 | 2026-04-06
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6321253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118362127 | Ongoing | 27000 | 0 | 2026-10-08
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6321548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115410852 | Approved | 27000 | 0 | 2026-03-07
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6333558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115879220 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6367750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115410486 | Approved | 27000 | 0 | 2026-01-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6376806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115805422 | Approved | 27000 | 0 | 2026-02-08
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6376920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119933644 | Approved | 27000 | 0 | 2026-02-11
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6376999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145384991 | Approved | 27000 | 0 | 2026-02-28
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6377145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115779836 | Approved | 27000 | 0 | 2026-02-08
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004028/IF/IAY/6377299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119928060 | Approved | 27000 | 0 | 2026-02-11
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1732004028/WC/22012035283285 — Perculation tank nirmaan panchyat ke pass | Ongoing | 108330.19 | 0 | 2025-04-28
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1732004028/WC/22012035306044 — GUGWLL RICHARCHE PIT | Approved | 0 | 0 | 2025-04-14
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1732004028/WC/22012035306383 — JGSA Sarvjanik koop recharge bus stand ke pass Baharpur | Approved | 35808.58 | 0 | 2025-04-14