## Work List
Exported on: 2026-10-19 03:21:04
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: NayaDhai
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / MAKHAN NAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004059/IF/IAY/455749 — Construction of IAY House -IAY REG. NO. MP1636919 | Completed | 15030 | 15660 | 2017-02-06 | 2019-02-02
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1732004060/AV/22012034371847 — Shaitidham Kakdi | Completed | 180000 | 163095 | 2018-02-20 | 2019-10-10
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & maintenance of Bharat Nirman Seva Kendra / Repair and Maintenance of Bharat Nirman Seva Kendra Building for Community | Repair & Maint of Community infrastructure | 1732004060/AV/22012034373374 — Panchayat Bhawan Nayadhai | Completed | 579200 | 578401 | 2018-06-10 | 2020-09-30
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1732004060/AV/22012034462684 — khel medan naya kakadi | Deleted | 0 | 0 | 2019-01-26
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1732004060/AV/22012034462686 — khel medan naya kakadi | Completed | 129008.13 | 115348 | 2019-06-03 | 2021-12-06
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732004060/AV/22012034470833 — Khailmaidan Panchayat Bhawan ke Pass (40X40M) | Closed | 0 | 0 | 2019-10-02
NARMADAPURAM / MAKHAN NAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732004060/AV/22012034508761 — Sarjanik bhawan Nirmand Gram Naya jam | Physically Completed | 247000 | 233744 | 2020-05-25 | 2026-04-24
NARMADAPURAM / MAKHAN NAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732004060/AV/22012034508767 — Sawjanik bhawan Nirmand Prathmik sala ke pass kakdi | Completed | 247000 | 228540 | 2020-05-25 | 2026-04-25
NARMADAPURAM / MAKHAN NAGAR | 2020-2021 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1732004060/AV/22012034513565 — Banderiwall Prathamik Sala or Pachayat bhawan ke Pass | Completed | 142000 | 147120 | 2020-08-19 | 2021-07-06
NARMADAPURAM / MAKHAN NAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732004060/AV/22012034539847 — Boundriwall Nirman Forest Naka to Panchayat bhawan | Completed | 42000 | 45490 | 2020-10-22 | 2022-08-17
NARMADAPURAM / MAKHAN NAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732004060/AV/22012034540549 — Drinking Water Tank for Villagers | Completed | 5600 | 5510 | 2020-10-29 | 2024-01-25
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732004060/AV/22012034570783 — daynig tebal aregment work nayadhai | Completed | 16002.3 | 10658 | 2021-12-30 | 2024-11-17
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1732004060/AV/22012034570788 — CLF BHABAN NAYADHAI | Ongoing | 999721.6 | 663760 | 2021-07-11
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1732004060/AV/22012034572118 — shanti dham nirman naya jaam | Ongoing | 196981.11 | 1158 | 2021-12-06
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1732004060/AV/22012034572123 — shanti dham nirman naya jaam shivraj ke khet ke pass | Closed | 0 | 0 | 2021-04-14
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1732004060/AV/22012034572124 — shanti dham nirman naya jaam shivraj ke khet ke pass | Closed | 0 | 0 | 2021-04-14
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1732004060/AV/22012034617584 — GP Nayakheda Me Bajrang Mandir Ke Pass Sarwjani Chabutra par Chhat Nirman | Completed | 40700 | 35900 | 2022-06-03 | 2025-06-02
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1732004060/DP/22012034407478 — road side plantation nayabory to Dhamaniya NALA 1 km | Closed | 0 | 0 | 2018-04-14
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1732004060/DP/22012034407480 — Road side plantation Nayakheda 0 to 1 kmm | Closed | 0 | 0 | 2018-04-14
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1732004060/DP/22012034407481 — Road side Palantation Nayakheda 1km to 2km | Closed | 0 | 0 | 2018-04-14
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1732004060/DP/22012034541531 — maa ki bagiya GPS bori GP NAYADHAI | Completed | 16976.64 | 8568 | 2022-04-08 | 2022-12-16
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1732004060/DP/22012034545563 — maa ki bagiya GSM nayabori NAYADHAI | Closed | 0 | 0 | 2021-10-02
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1732004060/DP/22012034545597 — maa ki bagiya PSM NAYADHAI | Closed | 16976.64 | 0 | 2021-10-02
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732004060/DP/22012034569730 — Sarvjanik parisar prathmik shala kakadi vraksha ropad kary | Closed | 0 | 0 | 2022-08-18
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732004060/DP/22012034569731 — Sarvjanik parisar prathmik shala kakadi vraksha ropad kary | Closed | 0 | 0 | 2022-08-18
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732004060/DP/22012034569733 — Sarvjanik parisar prathmik shala kakadi vraksha ropad kary | Closed | 0 | 0 | 2022-08-18
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732004060/DP/22012034569734 — Sarvjanik parisar prathmik shala kakadi vraksha ropad kary | Closed | 0 | 0 | 2022-08-18
NARMADAPURAM / MAKHAN NAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1732004060/DP/22012034579409 — Plantation Prathmik Sala Parisad me Kakdi | Closed | 0 | 0 | 2023-04-01
NARMADAPURAM / MAKHAN NAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1732004060/DP/22012034601040 — vasudha vandan amrat vatika school parishar jaam | Completed | 55847.4 | 26715 | 2023-09-23 | 2026-05-20
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Plantation in Institutions for Community | Plantation | 1732004060/DP/22012034625765 — Block plantation PS School gram Kakdi GP NAYADHAI | Ongoing | 187783.09 | 45891.17 | 2024-08-20
NARMADAPURAM / MAKHAN NAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1732004060/IF/22012034306166 — Nadep Budhaman / Maglu | Completed | 9003 | 8606 | 2016-12-22 | 2018-06-08
NARMADAPURAM / MAKHAN NAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1732004060/IF/22012034306171 — Barmi Compost Pahalad / Udal | Deleted | 13196 | 0 | 2016-10-01
NARMADAPURAM / MAKHAN NAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1732004060/IF/22012034306174 — Nadep Mokal / Shaitu | Completed | 9003 | 8606 | 2016-12-24 | 2018-06-08
NARMADAPURAM / MAKHAN NAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1732004060/IF/22012034306301 — Barmi Compost Ghansayam / Raghunath | Deleted | 13196 | 0 | 2016-12-07
NARMADAPURAM / MAKHAN NAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1732004060/IF/22012034306302 — Barmi Compost Jhamsingh / Jugar | Deleted | 13196 | 0 | 2016-12-07
NARMADAPURAM / MAKHAN NAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732004060/IF/22012034306303 — Agriclture plantation nayadhai | Completed | 187600 | 8334 | 2016-12-24 | 2019-08-18
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732004060/IF/22012034339786 — Varchharopan Sadak Kinare Nayadhai se nayakakdi | Completed | 335000 | 21212 | 2017-05-17 | 2021-02-24
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732004060/IF/22012034339787 — Varchharopan Sadak kinare Naya bori Futan Se Virjikhapa | Completed | 335000 | 22768 | 2017-06-27 | 2021-02-24
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732004060/IF/22012034339788 — Varchharopan Sadak Kinare Nayabiri Kharda | Completed | 335000 | 11488 | 2017-06-28 | 2021-02-24
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1732004060/IF/22012034339790 — Virchharpan khailmaidan pe Nayabori | Completed | 335000 | 18348 | 2017-07-12 | 2021-12-06
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732004060/IF/22012034353447 — Bashropan Birjikhapa | Closed | 335000 | 0 | 2017-04-01
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732004060/IF/22012034353478 — Bashropan Nale Kinare | Closed | 335000 | 0 | 2017-04-01
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732004060/IF/22012034353480 — vraksha ropad mokal ke makan se dhamniya nale ki aur | Closed | 335000 | 0 | 2017-04-01
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Biodrainage-Individuals / Wasteland Block Plantation of Biodrainage Trees for Individuals | Plantation | 1732004060/IF/22012034406514 — SHIVPAL KHET TALAB NIRMAD | Closed | 43000 | 0 | 2018-01-26
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Sericulture-Individuals / Wastelands Block Plantation of Sericulture Trees for Individuals | Plantation | 1732004060/IF/22012034406529 — garjan singh Talab nirmad | Closed | 43000 | 0 | 2018-01-26
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Sericulture-Individuals / Wastelands Block Plantation of Sericulture Trees for Individuals | Plantation | 1732004060/IF/22012034406536 — prayag khet talab nirmad | Deleted | 43000 | 0 | 2018-01-26
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Wastelands Block Plantation of Farm Forestry Trees for Individuals | Plantation | 1732004060/IF/22012034406538 — prayag khet Talab | Deleted | 43000 | 0 | 2018-01-26
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plntation Forestry-Individuals / Wastelands Block Plantation of Forestry Trees for Individuals | Plantation | 1732004060/IF/22012034406539 — Batiya bai khet Talab | Completed | 72000 | 29292 | 2018-06-07 | 2021-09-12
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Sericulture-Individuals / Wastelands Block Plantation of Sericulture Trees for Individuals | Plantation | 1732004060/IF/22012034406542 — hariram talab nirmad kary | Closed | 43000 | 0 | 2018-01-26
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Sericulture-Individuals / Wastelands Block Plantation of Sericulture Trees for Individuals | Plantation | 1732004060/IF/22012034406544 — HIRALAL TALAB NIRMAD | Closed | 43000 | 0 | 2018-01-26
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Wastelands Block Plantation of Farm Forestry Trees for Individuals | Plantation | 1732004060/IF/22012034406545 — phul singh talab nirmad kary | Completed | 72000 | 65052 | 2018-05-30 | 2020-06-05
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Sericulture-Individuals / Block Plantation of Sericulture Trees in fields for Individual | Plantation | 1732004060/IF/22012034406546 — surak talab nirmad kary | Ongoing | 72000 | 4556 | 2018-05-31
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Sericulture-Individuals / Wastelands Block Plantation of Sericulture Trees for Individuals | Plantation | 1732004060/IF/22012034410949 — farm pond nirmad shivlal/juger | Closed | 74000 | 0 | 2018-04-14
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plntation Forestry-Individuals / Wastelands Block Plantation of Forestry Trees for Individuals | Plantation | 1732004060/IF/22012034411273 — farm pond nirmad kisor/doman | Closed | 72000 | 0 | 2018-04-14
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Sericulture-Individuals / Wastelands Block Plantation of Sericulture Trees for Individuals | Plantation | 1732004060/IF/22012034411285 — farm pond nirmad manohar/ajmer | Closed | 72000 | 0 | 2018-04-14
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Sericulture-Individuals / Wastelands Block Plantation of Sericulture Trees for Individuals | Plantation | 1732004060/IF/22012034411292 — farm pond nirmad Hiralal/basodi | Closed | 72000 | 0 | 2018-04-14
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1732004060/IF/22012034417726 — Ram singh khet Talab | Closed | 0 | 0 | 2018-04-01
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Sericulture-Individuals / Wastelands Block Plantation of Sericulture Trees for Individuals | Plantation | 1732004060/IF/22012034421874 — talab nirmad jhamsingh/juger | Completed | 78398.16 | 54044 | 2018-07-30 | 2021-07-06
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1732004060/IF/22012034455834 — nadep nirmad garjan singh/jaysingh | Completed | 10078.89 | 8698 | 2019-02-22 | 2019-11-13
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1732004060/IF/22012034455836 — nadep nirmad basodi /garjan | Closed | 10078.89 | 0 | 2019-01-26
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1732004060/IF/22012034455915 — nadep nirmad jhabbal/jhanak | Completed | 10102.6 | 8698 | 2019-03-16 | 2020-02-28
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1732004060/IF/22012034455917 — nadep nirmad sarvan/shiv ji | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Sericulture-Individuals / Wastelands Block Plantation of Sericulture Trees for Individuals | Plantation | 1732004060/IF/22012034458235 — form pond nirmad ram sing | Closed | 89884.12 | 0 | 2019-01-26
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1732004060/IF/22012034469112 — form pond nirmad babulal/magilal naya bori | Completed | 100283.19 | 75362 | 2019-12-07 | 2021-08-11
NARMADAPURAM / MAKHAN NAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1732004060/IF/22012034479680 — talab nirmad Raju/najar aadibasi naya dhai | Completed | 138262.86 | 59820 | 2020-05-17 | 2021-08-16
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1732004060/IF/22012034480567 — medbandhan vishor/doman naya kakadi | Completed | 23970.43 | 8448 | 2019-06-27 | 2020-05-15
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1732004060/IF/22012034480569 — medbandhan basod/doman | Closed | 23999.02 | 0 | 2019-04-14
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1732004060/IF/22012034480570 — medbandhan aadharsingh/babulal | Closed | 0 | 0 | 2019-04-14
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1732004060/IF/22012034480571 — medbandhan gopal/aadhar singh | Closed | 0 | 0 | 2019-04-14
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1732004060/IF/22012034480573 — medbandhan ramesh/aadhar singh kakadi | Closed | 0 | 0 | 2019-04-14
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1732004060/IF/22012034483819 — medbandhan jhamsingh/juger nayadhai | Closed | 0 | 0 | 2019-04-14
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1732004060/IF/22012034483821 — form pond nirmad jhabbal/jhanak nayadhai | Closed | 0 | 0 | 2019-04-14
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1732004060/IF/22012034484827 — khet talab garjansingh/jaysingh nayakakadi | Completed | 92954.68 | 58070 | 2019-06-27 | 2021-07-06
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individual | Goat Shelter | 1732004060/IF/22012034506432 — bakri shed ramlal/bagda bori | Ongoing | 46140.58 | 6336 | 2019-11-11
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1732004060/IF/22012034506435 — bakri shed atal/bhaddal bori | Closed | 0 | 0 | 2019-08-15
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone graded Bund for Individuals / Construction of Stone graded Bund for Individuals | Construction of Bund | 1732004060/IF/22012034529437 — Talab nirmad jhabbl/jhanak | Closed | 0 | 0 | 2019-10-02
NARMADAPURAM / MAKHAN NAGAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1732004060/IF/22012034552829 — Minakshi talab murakh/suka naya bori | Completed | 412783.19 | 186865 | 2020-05-13 | 2024-12-27
NARMADAPURAM / MAKHAN NAGAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1732004060/IF/22012034552832 — Minakshi talab kailash/mehtab naya bori | Closed | 412783.19 | 0 | 2020-04-01
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1732004060/IF/22012034759969 — minakshi talab muniyabai/raghuveer | Closed | 0 | 0 | 2021-04-14
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Brushwood Check Dam for Individuals / Construction of Brushwood Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1732004060/IF/22012034801745 — nanadan phaludyan garjan/jaysingh | Completed | 117912.51 | 76290 | 2021-08-17 | 2024-07-21
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1732004060/IF/22012034801754 — nandan phaludyan dhannalal/kishor kakadi | Completed | 117912.51 | 75314 | 2021-09-08 | 2024-07-21
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1732004060/IF/22012034801765 — nandan phaludyan dhannalal/kishor kakadi | Closed | 0 | 0 | 2021-04-14
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1732004060/IF/22012034801779 — nandan phaludyan shivlal/parvatsingh kakadi | Closed | 117912.51 | 0 | 2021-04-14
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Brushwood Check Dam for Individuals / Construction of Brushwood Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1732004060/IF/22012034801795 — nandan phaludyan basodi/ganjan kakadi | Closed | 117912.51 | 0 | 2021-04-14
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1732004060/IF/22012034801813 — nandan phaludyan lavar/doman kakadi | Closed | 117912.51 | 0 | 2021-04-14
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1732004060/IF/22012034824426 — nandan phaludyan jaysingh/gyansingh kakadi | Closed | 0 | 0 | 2021-04-14
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1732004060/IF/22012034824427 — nandan phaludyan jaysingh/gyansingh kakadi | Closed | 0 | 0 | 2021-04-14
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1732004060/IF/22012034824428 — nandan phaludyan jaysingh/gyansingh kakadi | Closed | 0 | 0 | 2021-04-14
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1732004060/IF/22012034824429 — nandan phaludyan jaysingh/gyansingh kakadi | Closed | 0 | 0 | 2021-04-14
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1732004060/IF/22012034824431 — nandan phaludyan lakhanlal/gyansingh kakadi | Completed | 117912.51 | 78354 | 2021-08-17 | 2024-07-21
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1732004060/IF/22012034824436 — nandan phaludyan manohar/amarsingh kakadi | Closed | 117912.51 | 0 | 2021-04-14
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1732004060/IF/22012034825859 — nandan phaludyan Chhotelal/gyansingh kakadi | Completed | 117912.51 | 76098.6 | 2021-09-08 | 2024-07-21
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1732004060/IF/22012034862039 — nadep nirman amita/siyaram naya bori | Completed | 13875.22 | 11987 | 2022-01-25 | 2022-10-26
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1732004060/IF/22012034942356 — nandanfal udhan nayadhai | Closed | 0 | 0 | 2022-01-25
NARMADAPURAM / MAKHAN NAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Block Plantation of Forestry Trees in fields for Individual | Other Works | 1732004060/IF/22012035171158 — Nandan phaloudyan Aadhar/babulal kakadi | Ongoing | 132985.6 | 1560 | 2023-10-10
NARMADAPURAM / MAKHAN NAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1732004060/IF/22012035171183 — Nandan phaloudyan shivpal/parvat | Closed | 132985.6 | 0 | 2023-10-02
NARMADAPURAM / MAKHAN NAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Line Plantation of Forestry Trees for Individual | Plantation | 1732004060/IF/22012035171193 — Nandan phaloudyan jaysingh/gyansingh | Ongoing | 132985.6 | 1560 | 2023-10-10
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732004060/IF/22012035534765 — JGSA form pond nirman karya Jagdish / Ramdas GP NAYADHAI | Closed | 147621.16 | 1044 | 2025-05-22
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732004060/IF/22012035534787 — JGSA Form pond nirman Budhman / Manglu GP NAYADHAI | Physically Completed | 394558.55 | 122301 | 2025-05-22 | 2026-06-28
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732004060/IF/22012035534800 — JGSA Form pond Vishram / Manarsha GP NAYADHAI | Ongoing | 147621.16 | 8091 | 2025-05-26
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732004060/IF/22012035534806 — JGSA Form pond nirman Parvati bai / Shivji GP NAYADHAI | Physically Completed | 147621.16 | 46079 | 2025-05-22 | 2026-05-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732004060/IF/22012035534810 — JGSA Form pond Nirman Harvan / Shivji GP NAYADHAI | Physically Completed | 147621.16 | 45432.33 | 2025-05-22 | 2026-05-27
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732004060/IF/22012035534816 — JGSA Form pond nirman Radhey shyam / Munshi GP NAYADHAI | New | 0 | 0 | 2025-04-14
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732004060/IF/22012035534817 — JGSA Form pond nirman Radhey shyam / Munshi GP NAYADHAI | New | 0 | 0 | 2025-04-14
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732004060/IF/22012035534834 — JGSA Form pond nirman Radhey shyam / Munshi GP NAYADHAI | Physically Completed | 147621.16 | 49127.87 | 2025-05-23 | 2026-05-29
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732004060/IF/22012035534838 — JGSA Form pond nirman Sakaltaal / Munshi GP NAYADHAI | Physically Completed | 147621.16 | 48701.94 | 2025-06-05 | 2026-05-21
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732004060/IF/22012035534848 — JGSA Form pond nirman Sukkan / Sambhu GP NAYADHAI | Ongoing | 147621.16 | 1827 | 2025-05-23
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732004060/IF/22012035534859 — JGSA Form pond nirman Deepak / Shankar GP NAYADHAI | Physically Completed | 147621.16 | 86391 | 2025-05-22 | 2026-05-12
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732004060/IF/22012035534880 — JGSA Form pond Patiram/sitalli GP SATWASA | Approved | 0 | 0 | 2025-04-14
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004060/IF/IAY/1846688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4379026 | Closed | 17100 | 0 | 2018-06-13
NARMADAPURAM / MAKHAN NAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/LD/22012034294567 — Khel Maidan TS NO 63 | Completed | 242482 | 121022 | 2017-01-17 | 2019-04-23
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair and maintenance of WBM Roads for Community / Repair & Maintenance of WBM Road for Community | Repair & Maint of Community infrastructure | 1732004060/LD/22012034294569 — Saintidham TS NO 62 | Ongoing | 180000 | 167498 | 2017-05-08
NARMADAPURAM / MAKHAN NAGAR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1732004060/LD/22012034299601 — Khailmadan | Closed | 0 | 0 | 2017-01-26
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1732004060/LD/22012034309081 — Shaintidham virjikhapa | Completed | 209000 | 183524 | 2017-04-04 | 2018-07-08
NARMADAPURAM / MAKHAN NAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034317371 — CC Road Or Nali Nirmand Main Road se P Shcool | Completed | 41224 | 39579 | 2016-12-24 | 2018-06-08
NARMADAPURAM / MAKHAN NAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034322575 — CC Road | Closed | 0 | 0 | 2017-01-26
NARMADAPURAM / MAKHAN NAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034325862 — CC Road Or nali nirmand Ektar singh se sukhadev | Deleted | 18564 | 0 | 2017-01-29
NARMADAPURAM / MAKHAN NAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034329646 — CC Road or Nali niramnd Raju Aadiwasi ke Makan se Aganwadi tak | Completed | 62043 | 53604 | 2017-03-15 | 2018-06-08
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034368446 — CC Road | Closed | 0 | 0 | 2017-10-02
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034398119 — CC Road Ramchrn Adiwashi ke Makan ki or | Completed | 71820 | 66433 | 2018-12-27 | 2019-11-13
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034398342 — CC Road Ward 01 Se Makan No 22 Tak | Completed | 71820 | 60849 | 2018-12-27 | 2020-06-15
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034433709 — CC Road Nali Nirmand Mohan singh Se Sabulal Tak | Completed | 42300 | 29280 | 2019-01-07 | 2019-11-13
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034434401 — CC Road or Nali Nrmand Mokal ke Makan se Mata mandi | Completed | 64000 | 54672 | 2019-01-07 | 2022-01-02
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034439107 — सीसी रोड निर्माण कार्य | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034448761 — CC Road or Nali Madan ke Ghar Se Bhagilal | Completed | 17000 | 15828 | 2019-03-08 | 2020-12-09
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034448763 — CC Road or Nali Main Road Se Aganwadi Bhawan | Completed | 26000 | 24452 | 2019-03-08 | 2020-02-28
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034448764 — CC Road or Nali Radhesayam Ke Makan Se Jaiypal | Completed | 8000 | 7556 | 2019-03-08 | 2019-12-17
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034481659 — CC Road or nali nirmand Main road se Najar singh ke khet tak | Completed | 72000 | 79194 | 2019-11-07 | 2021-02-23
NARMADAPURAM / MAKHAN NAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034481662 — CC Road or Najar singh ke khet se Naya tendukheta tak | Completed | 63500 | 66880 | 2019-10-14 | 2020-01-04
NARMADAPURAM / MAKHAN NAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034548161 — CC Road Nirman Banti bai ke ghar se Nale ki or | Completed | 21000 | 18384 | 2020-11-19 | 2022-02-28
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034576393 — CC Road Nirmand Mata Mandir se Ekbal Ke Makan Tak | Completed | 33000 | 31652 | 2021-08-10 | 2021-11-24
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034576396 — CC Road Nirmand Mukh Marg Se Swasth kendr Tak | Ongoing | 11100 | 965 | 2021-08-29
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034592273 — CC Road Nirman Kamal Ke Makan Se Kichan Sed Tak | Closed | 0 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034592274 — CC Road Nirman Kamal Ke Makan Se Kichan Sed Tak | Closed | 21800 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034628595 — RCC Nali Nirman Hanuman ke Mandir Se Sarwan ke ghar tak | Completed | 27600 | 26741 | 2023-09-30 | 2024-07-03
NARMADAPURAM / MAKHAN NAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732004060/RC/22012034658707 — CC Road Nirman Samudaik Bhawan Se Sadak Ke ghar tak ( 15 TH F) | Completed | 16400 | 14586 | 2023-10-06 | 2025-06-02
NARMADAPURAM / MAKHAN NAGAR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732004060/RC/VB/22012034854264 — CC Road nirman main road se shanti dham ki or gram Kakdi GP NAYADHAI | New | 0 | 0 | 2026-04-01
NARMADAPURAM / MAKHAN NAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034496655 — samudaik swachchhta parisar gram dobh | Completed | 43700 | 43320 | 2020-09-29 | 2020-12-09
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034603869 — Construction of Community Nadep | Deleted | 0 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034603870 — Construction of Community Nadep | Deleted | 0 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034603873 — Construction of Community Nadep | Closed | 4800 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034603877 — Construction of Community Nadep | Deleted | 0 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034603879 — Construction of Community Nadep | Closed | 4800 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034603896 — Construction of Community Nadep | Closed | 4800 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034603897 — Construction of Community Nadep | Closed | 0 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034603898 — Construction of Community Nadep | Closed | 0 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034603900 — Construction of Community Nadep | Closed | 0 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034603901 — Construction of Community Nadep | Deleted | 0 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034603902 — Construction of Community Nadep | Deleted | 0 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034603903 — Construction of Community Nadep | Deleted | 0 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034608156 — Construction Of Community Nadep | Closed | 4800 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034608161 — Construction Of Community Nadep | Closed | 0 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034608163 — Construction Of Community Nadep | Closed | 4800 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Groups / Construction of Berkeley Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034608167 — Construction Of Community Nadep | Closed | 4800 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034608177 — Construction Of Community Nadep | Closed | 4800 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Groups / Construction of Berkeley Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034630131 — Samudayik Sochalay Saski prathmik sala naya bori | Physically Completed | 103000 | 44466 | 2021-12-19 | 2026-04-25
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034650838 — Communty Nadep Shantidham Ke Pass Virjikhapa | Completed | 4800 | 4692 | 2022-06-02 | 2022-10-02
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Groups / Construction of Berkeley Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034650840 — Communty Nadep Jhamsingh ke ghar Ka pass | Completed | 4800 | 3672 | 2022-04-27 | 2023-12-13
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034650843 — Communty Nadep School Ke Pass Virjikhapa | Completed | 4800 | 4692 | 2022-06-02 | 2022-10-02
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034651555 — Communty Nadep Mata Mandir Ke Pass Nayadhai Kakdi | Closed | 4800 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034651558 — Communty Nadep Mata Mandir Ke Pass Nayadhai Dob | Completed | 4800 | 1224 | 2022-05-04 | 2023-12-13
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034651563 — Communty Nadep Panchayat Bhawan ke Baju me Nayadhai | Completed | 4800 | 2448 | 2022-05-04 | 2023-12-13
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034651564 — Communty Nadep D P Ke Pass Nayadhai Dob | Completed | 4800 | 1224 | 2022-05-04 | 2023-12-13
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034651569 — Communty Nadep Chhanulala Ke Samen Nayadhai D P Ke Pass | Completed | 4800 | 3672 | 2022-05-04 | 2022-10-02
NARMADAPURAM / MAKHAN NAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732004060/RS/22012034704897 — Samudaik Swachhta Parisar Hatbajjar Ke pass | Completed | 50800 | 50069 | 2023-10-06 | 2024-11-14
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732004060/WC/22012034325331 — Check Dam nayadhai | Completed | 75372 | 29928 | 2017-05-23 | 2018-06-14
NARMADAPURAM / MAKHAN NAGAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1732004060/WC/22012034326937 — Talab Gaherikar Nayabori | Completed | 74000 | 65016 | 2017-05-25 | 2018-06-14
NARMADAPURAM / MAKHAN NAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732004060/WC/22012034438824 — stop dam nayabori | Closed | 0 | 0 | 2019-01-26
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732004060/WC/22012034443629 — talab nirmad naya kakadi | Completed | 100283.19 | 51492 | 2021-05-13 | 2024-01-17
NARMADAPURAM / MAKHAN NAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1732004060/WC/22012034616360 — Pani ka Taka School ke Pass Bori | Completed | 359723.09 | 316464.6 | 2021-03-10 | 2021-11-24
NARMADAPURAM / MAKHAN NAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1732004060/WC/22012034623741 — chek dem nirmad khel medan ke pas kakadi | Completed | 303321.84 | 176140 | 2021-03-20 | 2022-03-17
NARMADAPURAM / MAKHAN NAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1732004060/WC/22012034623743 — chek dem nirmad naya bori school ke pass | Completed | 320543.27 | 211400 | 2021-03-24 | 2025-06-02
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732004060/WC/22012034717835 — CTR FORM POND MUNIYABAI/RAGHUVEER NAYA BORI | Completed | 337715.44 | 199931 | 2021-05-28 | 2024-01-17
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1732004060/WC/22012034911313 — Checkdam nirman | Closed | 0 | 0 | 2022-01-25
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1732004060/WC/22012034944667 — Amrit sarover gram kaakdi school k pichey GP Nayadhai | Completed | 197000 | 149952 | 2022-04-12 | 2024-01-17
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1732004060/WC/22012034967569 — Under ground dyke nirman gram kakadi gp Nayadhai school k pichey | Closed | 36075.82 | 0 | 2022-04-14
NARMADAPURAM / MAKHAN NAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1732004060/WC/22012035132610 — Boulder Check dam nirman kary Shanti dham k khet ke pas NAYA JAAM GP-NAYADHAI | Completed | 412321.5 | 406876.62 | 2023-10-07 | 2024-08-22
NARMADAPURAM / MAKHAN NAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1732004060/WC/22012035135561 — Check Dam Nayajam Shantidha ke aag Nale par | Closed | 0 | 0 | 2023-04-01
NARMADAPURAM / MAKHAN NAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Pebble graded Bund for Community / Construction of Pebble graded Bund for Community | Construction of Bund | 1732004060/WC/22012035135591 — Wadniyataran Work Nayadhai ME Awadi kshatr me Vivek ke khat se Ashok ki or | Completed | 45287.8 | 35581 | 2024-01-12 | 2025-05-25
NARMADAPURAM / MAKHAN NAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1732004060/WC/22012035185092 — Boulder check dem gram kakdi | Physically Completed | 492923.18 | 411837.33 | 2024-06-17 | 2026-03-29
NARMADAPURAM / MAKHAN NAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1732004060/WC/22012035185094 — Boulder check dem gram kakdi | Closed | 0 | 0 | 2024-03-04
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1732004060/WC/22012035270469 — JGSA comunity rechagre pit santosh k ghar k pass GP nayadhai | Completed | 24759.91 | 19405.3 | 2025-04-28 | 2026-01-23
NARMADAPURAM / MAKHAN NAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732004060/WC/22012035270504 — JGSA Roof water harwesting work gram panchayat bavan GP Nayadhai | Closed | 27853.08 | 0 | 2025-04-28
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732004060/WH/22012034457338 — Talab jinudhhar kary GRAM Nayabori | Closed | 14700 | 0 | 2021-10-22
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732004060/WH/22012034457365 — check dam desilting check dam se nayabori tak NAYADHAI | Closed | 12000 | 0 | 2021-10-02
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732004060/WH/22012034930652 — checkdam desilting work kakadi Nayadhai | Closed | 12000 | 0 | 2021-05-05
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732004060/WH/22012034930662 — check dem desliting check dem s nayabori | Completed | 12027 | 2448 | 2022-04-17 | 2022-12-23
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732004060/WH/22012034930678 — Talab jinudhhar kary GRAM Nayabori | Closed | 0 | 0 | 2022-04-01
NARMADAPURAM / MAKHAN NAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732004060/WH/22012034930687 — Talab jinudhhar kary GRAM Nayabori | Completed | 14758 | 2448 | 2022-04-17 | 2022-12-12
NARMADAPURAM / MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732004061/WH/22012034457368 — checkdam desilting work kakadi Nayadhai | Closed | 12000 | 0 | 2021-10-01