## Work List
Exported on: 2026-10-10 10:26:22
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: CHANDON
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / BANKHEDI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1732007004/AV/22012034568108 — कचरा उपचार /भंडार केंद्र शेड निर्माण चांदौन | Ongoing | 133783 | 0 | 2021-08-18
NARMADAPURAM / BANKHEDI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1732007004/AV/22012034593132 — daining hall middle school chandon | Ongoing | 26826.27 | 0 | 2021-09-22
NARMADAPURAM / BANKHEDI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Avenue Plantation for Community | Plantation | 1732007004/DP/22012034626476 — plantation road site petrol pump se seetaram mandir ki or chandon | Approved | 0 | 0 | 2024-04-14
NARMADAPURAM / BANKHEDI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individual | Plantation | 1732007004/IF/22012035025959 — शह्तूत बृक्षारोपण हरिशंकर / मूरत सिंह | Ongoing | 120000 | 0 | 2022-12-30
NARMADAPURAM / BANKHEDI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individual | Plantation | 1732007004/IF/22012035025964 — शह्तूत बृक्षारोपण रामस्वरूप/गर्वसिंह | Ongoing | 120000 | 0 | 2022-12-30
NARMADAPURAM / BANKHEDI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individual | Plantation | 1732007004/IF/22012035025965 — शह्तूत बृक्षारोपण राजेश/वीरन | Ongoing | 120000 | 0 | 2022-12-30
NARMADAPURAM / BANKHEDI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individual | Plantation | 1732007004/IF/22012035026053 — शह्तूत बृक्षारोपण सक्कूलाल/अजबसिंह | Ongoing | 120000 | 0 | 2022-12-30
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732007004/IF/22012035594226 — Ekbagiya maa ke naam chandrakala /chandan | Ongoing | 179867.97 | 0 | 2025-09-12
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732007004/IF/22012035594249 — Ek bagiya maa ke naam rekha /rajesh | Ongoing | 179867.97 | 0 | 2025-09-12
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732007004/IF/22012035594267 — Ekbagiya maa ke naam sarswati bai / gangaram | Ongoing | 179867.97 | 0 | 2025-09-12
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732007004/IF/22012035594273 — Ekbagiya maa ke naam maya bai/chensingh | Ongoing | 179867.97 | 0 | 2025-09-17
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732007004/IF/22012035594281 — Ekbagiya maa ke naam lalita bai /dharmendra vishwkarma | Ongoing | 179867.97 | 0 | 2025-09-12
NARMADAPURAM / BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4014393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119832337 | Ongoing | 27000 | 0 | 2025-01-24
NARMADAPURAM / BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4029250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148009958 | Ongoing | 27000 | 0 | 2025-01-24
NARMADAPURAM / BANKHEDI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4029255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148011230 | Approved | 27000 | 0 | 2022-05-09
NARMADAPURAM / BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4029259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148013295 | Ongoing | 27000 | 0 | 2025-01-24
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4029261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148014452 | Ongoing | 27000 | 0 | 2025-08-29
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4029284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148023024 | Ongoing | 27000 | 12327 | 2026-04-24
NARMADAPURAM / BANKHEDI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4029295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148032738 | Approved | 27000 | 0 | 2022-05-07
NARMADAPURAM / BANKHEDI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4086447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124736267 | Approved | 27000 | 0 | 2022-05-14
NARMADAPURAM / BANKHEDI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4131714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119833059 | Approved | 27000 | 0 | 2022-05-20
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4343913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119821809 | Ongoing | 27000 | 2100 | 2026-08-14
NARMADAPURAM / BANKHEDI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4346959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119832327 | Approved | 27000 | 0 | 2022-07-27
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4357997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148010198 | Ongoing | 27000 | 0 | 2026-01-09
NARMADAPURAM / BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4874226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148013241 | Approved | 27000 | 0 | 2024-11-19
NARMADAPURAM / BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4874228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148021637 | Ongoing | 27000 | 0 | 2025-01-10
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4880353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119825559 | Physically Completed | 27000 | 0 | 2025-09-05 | 2026-09-06
NARMADAPURAM / BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4881337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121942693 | Ongoing | 27000 | 0 | 2025-01-17
NARMADAPURAM / BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/4881575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148011052 | Physically Completed | 27000 | 0 | 2025-01-24 | 2026-09-06
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5344024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147993682 | Completed | 23490 | 0 | 2025-05-02 | 2026-08-06
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5344113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118505350 | Ongoing | 27000 | 0 | 2025-09-19
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5344366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119822059 | Physically Completed | 27000 | 300 | 2025-09-05 | 2026-09-06
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5345666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148023099 | Ongoing | 27000 | 0 | 2025-05-09
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5346690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148032371 | Completed | 23490 | 0 | 2025-05-02 | 2026-08-06
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5347370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119825572 | Ongoing | 27000 | 0 | 2025-09-19
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5347371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119825671 | Ongoing | 27000 | 0 | 2025-12-19
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5347570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126437376 | Ongoing | 27000 | 0 | 2025-09-19
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5348073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121947241 | Ongoing | 27000 | 0 | 2025-05-02
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5349472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119833160 | Ongoing | 27000 | 0 | 2025-12-19
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5350495 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148004100 | Completed | 23490 | 0 | 2025-04-25 | 2026-08-06
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5350504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148001854 | Ongoing | 27000 | 0 | 2025-09-19
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5351162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119819391 | Completed | 23490 | 0 | 2025-05-02 | 2026-08-06
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5351416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147997340 | Ongoing | 27000 | 0 | 2025-11-07
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5351419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147997717 | Completed | 23490 | 0 | 2025-05-02 | 2026-08-06
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5352521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121947081 | Ongoing | 27000 | 0 | 2025-12-19
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5352855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121944838 | Ongoing | 27000 | 0 | 2025-07-04
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5353094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119821327 | Ongoing | 27000 | 0 | 2025-05-23
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5353133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148030562 | Ongoing | 27000 | 0 | 2026-01-09
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5354059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148026363 | Ongoing | 27000 | 0 | 2025-08-29
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5356187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119832291 | Completed | 23490 | 0 | 2025-05-23 | 2026-08-06
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5601995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120249158 | Ongoing | 27000 | 2100 | 2025-09-19
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5602111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119818466 | Ongoing | 27000 | 0 | 2025-09-26
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5684227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148001080 | Ongoing | 27000 | 0 | 2026-08-21
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5684228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148027254 | Ongoing | 27000 | 0 | 2026-05-01
NARMADAPURAM / BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5684347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120805141 | Approved | 27000 | 0 | 2025-03-26
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5684570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148021819 | Ongoing | 27000 | 0 | 2025-09-26
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5684602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116996622 | Ongoing | 27000 | 0 | 2025-12-19
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5684641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119821620 | Physically Completed | 27000 | 2100 | 2025-09-19 | 2026-09-06
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5684805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121944993 | Ongoing | 27000 | 0 | 2026-09-11
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5684870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148008820 | Ongoing | 27000 | 8400 | 2025-10-24
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5685043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148033919 | Ongoing | 27000 | 0 | 2026-01-09
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5685064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120976753 | Ongoing | 27000 | 0 | 2025-08-22
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5685072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148013350 | Ongoing | 27000 | 0 | 2026-02-20
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5803481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148002698 | Ongoing | 27000 | 0 | 2026-01-09
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5972435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118454151 | Ongoing | 27000 | 0 | 2026-08-14
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5972459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118505468 | Approved | 27000 | 0 | 2026-02-10
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5972601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119825638 | Approved | 27000 | 0 | 2026-02-10
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5972718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148005308 | Ongoing | 27000 | 0 | 2026-10-09
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5972793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120976269 | Approved | 27000 | 0 | 2026-02-10
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5972794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120976362 | Ongoing | 27000 | 0 | 2026-09-04
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5972924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121942794 | Ongoing | 27000 | 0 | 2026-10-09
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5973117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120457860 | Ongoing | 27000 | 0 | 2026-08-21
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5973329 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148032604 | Ongoing | 27000 | 0 | 2026-07-20
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5973330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148032875 | Ongoing | 27000 | 0 | 2026-08-21
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5973331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148033963 | Approved | 27000 | 0 | 2026-02-10
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5973334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148070976 | Approved | 27000 | 0 | 2026-02-10
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5973352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119819353 | Ongoing | 27000 | 0 | 2026-07-18
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5973476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116996643 | Approved | 27000 | 0 | 2026-02-10
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5973477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116996650 | Ongoing | 27000 | 0 | 2026-08-14
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5973664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148033776 | Approved | 27000 | 0 | 2026-02-10
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5973837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120805099 | Approved | 27000 | 0 | 2026-02-10
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5973895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148023352 | Approved | 27000 | 0 | 2026-02-10
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5973896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148023423 | Approved | 27000 | 0 | 2026-02-10
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/5973901 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119818367 | Approved | 27000 | 0 | 2026-02-10
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/6151356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148033083 | Ongoing | 27000 | 2100 | 2026-09-25
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/6157622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148021468 | Ongoing | 27000 | 8400 | 2026-08-21
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/6157624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148021567 | Ongoing | 27000 | 10227 | 2026-08-21
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/6158114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148018155 | Approved | 27000 | 0 | 2026-03-05
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/6218036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121942913 | Ongoing | 27000 | 1827 | 2026-09-04
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/6218542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148004799 | Ongoing | 27000 | 0 | 2026-10-02
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/6219135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147991418 | Ongoing | 27000 | 0 | 2026-09-04
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/6305872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119821341 | Approved | 27000 | 0 | 2026-03-12
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/6325250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148019486 | Approved | 27000 | 0 | 2026-06-10
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/6376802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119818650 | Approved | 27000 | 0 | 2026-06-10
NARMADAPURAM / BANKHEDI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732007004/IF/IAY/835021 — Construction of IAY House -IAY REG. NO. MP1278383 | Approved | 27000 | 0 | 2017-04-01