## Work List
Exported on: 2026-09-27 21:42:01
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PIPARPANI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARMADAPURAM / BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Unskilled wage for Bio gas plant for community / Unskilled wage component towards the construction of Bio-gas plant for community | Bio-gas plant | 1732007042/AV/22012034657753 — प्लांटेशन अमृत सरोवर श्रीलाल नागवंशी के खेत के पास पीपरपानी | New | 0 | 0 | 2024-04-14
NARMADAPURAM / BANKHEDI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1732007042/DP/22012034621481 — Brakskaropan amrit sarovar talab ke pas piparpani | New | 0 | 0 | 2024-04-14
NARMADAPURAM / BANKHEDI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1732007042/DP/22012034621496 — Brakskaropan amrit sarovar talab ke pas piparpani | Ongoing | 198459.53 | 0 | 2024-07-23
NARMADAPURAM / BANKHEDI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1732007042/DP/22012034630279 — vraksharopan kary khasra no 176 van vibhag gram piparpani | Approved | 0 | 0 | 2025-04-14
NARMADAPURAM / BANKHEDI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1732007042/IF/22012034864077 — वृक्षारोपण कार्य ट्रेंच के पास ग्राम पंचायत पीपर पानी | Ongoing | 117912.51 | 0 | 2021-10-22
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732007042/IF/22012035383639 — khet talab nirman kundan / vijay thakur | New | 0 | 0 | 2025-04-14
NARMADAPURAM / BANKHEDI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/1493047 — Construction of IAY House -IAY REG. NO. MP3299814 | Approved | 27000 | 0 | 2018-03-12
NARMADAPURAM / BANKHEDI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/1908576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3299734 | Approved | 27000 | 0 | 2018-07-17
NARMADAPURAM / BANKHEDI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/4409425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147280484 | Ongoing | 27000 | 0 | 2023-09-20
NARMADAPURAM / BANKHEDI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/46035 — Construction of IAY House -IAY REG. NO. MP-32-007-042-001/61 | Approved | 27000 | 0 | 2015-11-30
NARMADAPURAM / BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/4657995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148069873 | Ongoing | 27000 | 0 | 2024-10-01
NARMADAPURAM / BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/4660297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146977333 | Ongoing | 27000 | 0 | 2024-11-12
NARMADAPURAM / BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/4661632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148948973 | Ongoing | 27000 | 0 | 2024-11-05
NARMADAPURAM / BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/4663059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149229487 | Ongoing | 27000 | 0 | 2024-11-12
NARMADAPURAM / BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/4868833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146548327 | Ongoing | 27000 | 0 | 2025-01-14
NARMADAPURAM / BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/5798839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146977557 | Ongoing | 27000 | 0 | 2025-09-09
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/5882503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146977305 | Ongoing | 27000 | 0 | 2026-05-19
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/6218221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147350228 | Ongoing | 27000 | 8400 | 2026-08-14
NARMADAPURAM / BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/6219265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149453672 | Ongoing | 27000 | 0 | 2026-04-16
NARMADAPURAM / BANKHEDI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/661665 — Construction of IAY House -IAY REG. NO. MP1565155 | Approved | 27000 | 0 | 2017-03-15
NARMADAPURAM / BANKHEDI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/663444 — Construction of IAY House -IAY REG. NO. MP1799640 | Approved | 27000 | 0 | 2017-03-15
NARMADAPURAM / BANKHEDI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/951191 — Construction of IAY House -IAY REG. NO. MP3073659 | Approved | 27000 | 0 | 2017-04-01
NARMADAPURAM / BANKHEDI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007042/IF/IAY/952029 — Construction of IAY House -IAY REG. NO. MP3096051 | Approved | 27000 | 0 | 2017-04-01
NARMADAPURAM / BANKHEDI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1732007042/WC/22012034936149 — CTR-amrit sarobar shashkeey talab nirman piparpani | Ongoing | 1377000 | 0 | 2022-04-20
NARMADAPURAM / BANKHEDI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732007042/WC/22012035306783 — हनुमान मंदिर के पास कुआं रिचार्ज फिट पीपर पानी | New | 0 | 0 | 2025-04-14