## Work List
Exported on: 2026-10-25 02:40:55
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: DHAKERWAH
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR / SIHORA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1733001049/AV/22012034393352 — agwanwadee bhawan nirman Dhakarwah | Completed | 180000 | 184798 | 2018-12-28 | 2020-06-24
JABALPUR / SIHORA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733001049/AV/22012034401897 — shantidham nirman dhakarwah | Completed | 180000 | 179993.94 | 2019-07-03 | 2020-06-19
JABALPUR / SIHORA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Repair & Maint of distributary Canal for Community / Repair and Maintenance of distributary Canal for Community | Repair & Maint of Canal | 1733001049/IC/22012034388294 — Repair and maintenance of khagamau vitran naharand minor canals | Completed | 69202.51 | 66520 | 2021-01-21 | 2021-03-14
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1733001049/IF/22012034343181 — vraksharopan - shantidham/khel maidan bhanpura mai | Completed | 335000 | 40180 | 2017-06-15 | 2021-06-23
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1733001049/IF/22012034350028 — VRACHHAROPAN shanti dham dhakarwah | Completed | 335000 | 23020 | 2017-06-15 | 2018-08-10
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1733001049/IF/22012034358555 — vraksharopan - shantidham park dhakarwah | Completed | 335000 | 23192 | 2017-10-07 | 2022-11-11
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1733001049/IF/22012034358563 — vraksharopan- shantidham park dhakarwah | Completed | 535000 | 36264 | 2017-06-29 | 2021-06-23
JABALPUR / SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/1212752 — Construction of IAY House -IAY REG. NO. MP2725931 | Completed | 15480 | 16704 | 2018-07-23 | 2019-01-08
JABALPUR / SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/1212880 — Construction of IAY House -IAY REG. NO. MP2800908 | Completed | 17100 | 16116 | 2018-07-23 | 2022-02-05
JABALPUR / SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/1213499 — Construction of IAY House -IAY REG. NO. MP3192603 | Completed | 15480 | 15472 | 2018-07-30 | 2019-04-01
JABALPUR / SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/1346036 — Construction of IAY House -IAY REG. NO. MP3667763 | Completed | 15480 | 15660 | 2018-07-23 | 2018-12-14
JABALPUR / SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/1349663 — Construction of IAY House -IAY REG. NO. MP3812044 | Completed | 15480 | 15312 | 2018-07-23 | 2019-06-06
JABALPUR / SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/1350084 — Construction of IAY House -IAY REG. NO. MP3830766 | Completed | 15480 | 17748 | 2018-06-28 | 2018-12-05
JABALPUR / SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/1350141 — Construction of IAY House -IAY REG. NO. MP3832923 | Completed | 15480 | 15510 | 2018-07-30 | 2019-05-01
JABALPUR / SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/1350531 — Construction of IAY House -IAY REG. NO. MP3850198 | Completed | 15480 | 16530 | 2018-07-23 | 2018-12-30
JABALPUR / SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/1683240 — Construction of IAY House -IAY REG. NO. MP3811289 | Completed | 15660 | 15660 | 2018-07-23 | 2019-07-09
JABALPUR / SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/1829082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3087249 | Completed | 17100 | 14982 | 2018-07-23 | 2023-07-10
JABALPUR / SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/1830671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3306483 | Completed | 15660 | 15046 | 2018-06-28 | 2020-06-26
JABALPUR / SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/1868565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3111344 | Completed | 15660 | 15486 | 2018-07-23 | 2019-02-01
JABALPUR / SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/1870214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3707484 | Completed | 15660 | 15582 | 2018-07-23 | 2020-05-25
JABALPUR / SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/1870850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3936564 | Completed | 15660 | 15486 | 2018-07-23 | 2019-02-02
JABALPUR / SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/1886776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3096638 | Completed | 15660 | 15138 | 2018-07-23 | 2019-07-30
JABALPUR / SIHORA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2324787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5381235 | Completed | 17100 | 16430 | 2019-11-09 | 2021-05-28
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2616945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3171866 | Completed | 17100 | 17130 | 2021-04-26 | 2021-12-06
JABALPUR / SIHORA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2617319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1647050 | Completed | 17100 | 16982 | 2021-03-14 | 2023-08-19
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2617699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1621884 | Completed | 17100 | 15696 | 2021-04-26 | 2024-02-14
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2618863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3162080 | Completed | 17100 | 17166 | 2021-04-26 | 2021-11-25
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2619111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3683083 | Completed | 17100 | 17166 | 2021-04-26 | 2021-11-25
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2619268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3213767 | Completed | 17100 | 17166 | 2021-04-26 | 2021-11-25
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2620375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3694806 | Completed | 17100 | 17208 | 2021-04-26 | 2021-12-09
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2621006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2860259 | Completed | 17100 | 16856 | 2021-04-26 | 2024-05-21
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2621920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3162069 | Completed | 17100 | 17748 | 2021-04-26 | 2022-09-20
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2623257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3668267 | Completed | 17100 | 17798 | 2021-04-26 | 2022-09-20
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2623316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3722803 | Completed | 17100 | 17079 | 2022-09-12 | 2024-07-04
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2663185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3938887 | Completed | 17100 | 17145 | 2021-04-26 | 2021-11-12
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2800371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3706678 | Completed | 17100 | 16994 | 2021-05-20 | 2022-08-05
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2801144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3832905 | Completed | 17100 | 16714 | 2021-04-26 | 2023-07-10
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2803492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3895814 | Completed | 17100 | 17130 | 2021-04-26 | 2021-11-16
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2854406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3683050 | Completed | 17100 | 15580 | 2021-04-26 | 2022-07-19
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/2858828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3707411 | Completed | 17100 | 17160 | 2021-04-26 | 2021-12-13
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3061809 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4615034 | Completed | 17370 | 17112 | 2021-04-26 | 2021-11-19
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3062169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3707126 | Completed | 17370 | 17112 | 2021-04-26 | 2021-11-19
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3063462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5493038 | Completed | 17370 | 18756 | 2021-04-26 | 2022-10-10
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3064346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5472549 | Completed | 17370 | 17172 | 2021-04-26 | 2022-02-05
JABALPUR / SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3064347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5472626 | Completed | 17370 | 17168 | 2021-04-26 | 2023-07-10
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/335068 — Construction of IAY House -IAY REG. NO. MP1102248 | Completed | 15030 | 18347.6 | 2017-10-27 | 2018-11-30
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3787869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130785063 | Completed | 18360 | 17800 | 2022-06-29 | 2024-02-14
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3787891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130796585 | Completed | 18360 | 17928 | 2022-06-29 | 2024-02-14
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3814688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115637096 | Completed | 18360 | 18342 | 2022-06-13 | 2023-07-08
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3814694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115637850 | Completed | 18360 | 17962 | 2022-06-29 | 2023-08-10
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3832711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124853168 | Completed | 18360 | 17216 | 2022-06-29 | 2024-02-14
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3858900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130794197 | Completed | 18360 | 18275 | 2022-06-29 | 2024-02-14
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3910561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130181336 | Completed | 18360 | 17712 | 2022-06-13 | 2024-02-14
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3946038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130181629 | Completed | 18360 | 18232 | 2022-11-03 | 2024-02-14
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3952481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130788761 | Completed | 18360 | 17632 | 2022-06-29 | 2024-02-20
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3952484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130790314 | Completed | 18360 | 13726 | 2022-11-19 | 2024-11-05
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3952488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130792950 | Completed | 18360 | 17712 | 2022-11-03 | 2024-02-14
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/3956451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125079047 | Completed | 18360 | 17712 | 2022-11-19 | 2024-02-14
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4049631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130787078 | Completed | 18360 | 17928 | 2022-06-29 | 2024-02-14
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4049632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130795032 | Completed | 18360 | 17712 | 2022-09-05 | 2024-02-14
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4049634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130795285 | Completed | 18360 | 17658 | 2022-08-06 | 2024-02-14
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4063022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115660531 | Completed | 18360 | 18082 | 2022-11-03 | 2024-08-01
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4101695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130793752 | Completed | 18360 | 17731 | 2022-10-29 | 2024-02-14
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4101696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130795408 | Completed | 18360 | 18241 | 2022-06-29 | 2024-02-14
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4103914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130181515 | Completed | 18360 | 17820 | 2022-07-15 | 2024-02-20
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4116636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115636781 | Completed | 18360 | 18360 | 2022-07-15 | 2023-03-31
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4125270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130786908 | Completed | 18360 | 15291 | 2022-11-16 | 2024-07-04
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4125271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130789663 | Completed | 18360 | 18072 | 2022-11-16 | 2024-02-14
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4256105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130182742 | Completed | 18360 | 18123 | 2023-02-06 | 2024-02-14
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4258253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130789896 | Completed | 23490 | 20097 | 2022-12-05 | 2026-05-09
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4258255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130791827 | Completed | 18360 | 18356 | 2022-12-16 | 2024-07-04
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4258256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130794694 | Completed | 18360 | 18190 | 2022-08-25 | 2023-08-10
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4287765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128173484 | Completed | 18360 | 17880 | 2022-12-24 | 2024-05-21
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4287894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130793893 | Completed | 18360 | 17698 | 2022-12-06 | 2024-07-04
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4294061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128786560 | Completed | 18360 | 18360 | 2023-01-31 | 2023-03-31
JABALPUR / SIHORA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4294297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130182610 | Completed | 18360 | 18321 | 2024-03-01 | 2024-07-04
JABALPUR / SIHORA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4294298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130182775 | Completed | 18360 | 13677 | 2024-03-01 | 2024-11-05
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4294915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130788649 | Completed | 18360 | 17544 | 2022-10-29 | 2023-07-08
JABALPUR / SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4294916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130792335 | Completed | 18360 | 17663 | 2022-12-24 | 2024-02-20
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/429837 — Construction of IAY House -IAY REG. NO. MP1393216 | Completed | 15030 | 15136 | 2017-10-26 | 2018-05-22
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/432862 — Construction of IAY House -IAY REG. NO. MP1414981 | Completed | 15030 | 14620 | 2017-10-26 | 2019-05-28
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/435349 — Construction of IAY House -IAY REG. NO. MP1432293 | Completed | 15030 | 14981 | 2017-04-18 | 2018-08-04
JABALPUR / SIHORA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4402776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123474809 | Completed | 19890 | 19096 | 2024-02-23 | 2024-07-04
JABALPUR / SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4600576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123477519 | Completed | 23490 | 22824 | 2025-02-20 | 2026-01-02
JABALPUR / SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4630855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128178832 | Completed | 23490 | 23112 | 2025-02-28 | 2026-01-02
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/467394 — Construction of IAY House -IAY REG. NO. MP1789268 | Completed | 15030 | 15159 | 2017-04-18 | 2018-08-04
JABALPUR / SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4692722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115661823 | Completed | 23490 | 22842 | 2025-02-20 | 2026-02-11
JABALPUR / SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4717519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130181473 | Completed | 23490 | 22968 | 2025-02-20 | 2026-02-03
JABALPUR / SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4718282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130795769 | Completed | 23490 | 23364 | 2025-03-21 | 2025-12-30
JABALPUR / SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4718283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130795783 | Completed | 21870 | 21774 | 2024-11-12 | 2025-03-11
JABALPUR / SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4756098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117636820 | Completed | 23490 | 21141 | 2025-04-22 | 2026-04-01
JABALPUR / SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4781362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128203245 | Completed | 21870 | 21822 | 2024-11-12 | 2025-04-01
JABALPUR / SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4784553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130181285 | Completed | 21870 | 21774 | 2024-11-12 | 2025-01-31
JABALPUR / SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4785186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130790476 | Completed | 23490 | 21840 | 2024-11-12 | 2026-01-02
JABALPUR / SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4785188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130793140 | Completed | 23490 | 23112 | 2025-02-20 | 2026-02-06
JABALPUR / SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4785194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130796567 | Completed | 21870 | 21774 | 2024-11-12 | 2025-02-10
JABALPUR / SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4785201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130799152 | Completed | 23490 | 22986 | 2025-02-20 | 2026-01-02
JABALPUR / SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4785211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130802558 | Completed | 23490 | 21645 | 2024-11-30 | 2026-01-02
JABALPUR / SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4850813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130792158 | Completed | 23490 | 22626 | 2024-12-16 | 2026-01-02
JABALPUR / SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4850814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130792279 | Completed | 23490 | 22860 | 2025-02-20 | 2026-01-02
JABALPUR / SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/4953655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118177560 | Completed | 23490 | 23490 | 2025-08-01 | 2025-12-30
JABALPUR / SIHORA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/51387 — Construction of IAY House -IAY REG. NO. MP-33-001-049-002/07 | Completed | 14310 | 15425 | 2016-12-20 | 2021-09-29
JABALPUR / SIHORA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/51388 — Construction of IAY House -IAY REG. NO. MP-33-001-049-002/26 | Completed | 14310 | 4773 | 2016-12-20 | 2017-10-12
JABALPUR / SIHORA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/51389 — Construction of IAY House -IAY REG. NO. MP-33-001-049-002/75 | Completed | 14310 | 15081 | 2016-12-20 | 2018-11-30
JABALPUR / SIHORA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/51726 — Construction of IAY House -IAY REG. NO. MP-33-001-049-001/13a | Completed | 14310 | 15436 | 2016-12-20 | 2021-09-08
JABALPUR / SIHORA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/51727 — Construction of IAY House -IAY REG. NO. MP-33-001-049-002/87 | Completed | 14310 | 1910 | 2016-12-13 | 2017-10-12
JABALPUR / SIHORA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/538528 — Construction of IAY House -IAY REG. NO. MP3032139 | Completed | 15030 | 14981 | 2017-03-08 | 2018-08-04
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/542799 — Construction of IAY House -IAY REG. NO. MP3147811 | Completed | 15030 | 14964 | 2017-08-08 | 2018-08-04
JABALPUR / SIHORA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/543018 — Construction of IAY House -IAY REG. NO. MP3153941 | Completed | 15030 | 15005 | 2017-03-08 | 2018-08-04
JABALPUR / SIHORA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/560932 — Construction of IAY House -IAY REG. NO. MP3695442 | Completed | 15030 | 15005 | 2017-03-08 | 2018-08-04
JABALPUR / SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/5788018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130788401 | Completed | 23490 | 23490 | 2026-02-05 | 2026-05-09
JABALPUR / SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/5788019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130788513 | Completed | 23490 | 23490 | 2026-02-10 | 2026-05-09
JABALPUR / SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/5788020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130789012 | Completed | 23490 | 23490 | 2025-09-20 | 2026-03-26
JABALPUR / SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/5788021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130789090 | Completed | 23490 | 22968 | 2025-09-04 | 2026-03-26
JABALPUR / SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/5788022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130789205 | Completed | 23490 | 23490 | 2025-12-04 | 2026-05-09
JABALPUR / SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/5788023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130789456 | Completed | 23490 | 23229 | 2025-11-10 | 2026-03-26
JABALPUR / SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/5789589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132554060 | Completed | 23490 | 23490 | 2025-09-24 | 2026-02-03
JABALPUR / SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/5789590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132554278 | Completed | 23490 | 23490 | 2025-09-24 | 2025-12-30
JABALPUR / SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/5789591 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132554569 | Completed | 23490 | 23490 | 2025-09-13 | 2026-06-03
JABALPUR / SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/5789805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130182707 | Completed | 23490 | 23490 | 2025-09-20 | 2026-04-01
JABALPUR / SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/5790191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130784900 | Completed | 23490 | 23490 | 2025-11-10 | 2026-04-01
JABALPUR / SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/5790380 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115638430 | Completed | 23490 | 23229 | 2025-09-13 | 2026-01-02
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/593657 — Construction of IAY House -IAY REG. NO. MP1647288 | Completed | 15030 | 14545 | 2017-05-16 | 2019-07-30
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/593892 — Construction of IAY House -IAY REG. NO. MP1804456 | Completed | 15030 | 15136 | 2017-08-01 | 2018-08-04
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/593920 — Construction of IAY House -IAY REG. NO. MP1822394 | Completed | 15030 | 15233 | 2017-05-16 | 2018-09-01
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/598150 — Construction of IAY House -IAY REG. NO. MP1226830 | Completed | 15030 | 15061 | 2017-05-16 | 2018-08-04
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/634983 — Construction of IAY House -IAY REG. NO. MP1338670 | Completed | 15030 | 15480 | 2017-08-08 | 2018-06-22
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/636279 — Construction of IAY House -IAY REG. NO. MP1646728 | Completed | 15030 | 15308 | 2017-10-27 | 2018-08-04
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/651652 — Construction of IAY House -IAY REG. NO. MP3819184 | Completed | 15030 | 15308 | 2017-09-11 | 2018-09-01
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/710540 — Construction of IAY House -IAY REG. NO. MP1567634 | Completed | 15030 | 15480 | 2017-10-27 | 2018-06-22
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/756440 — Construction of IAY House -IAY REG. NO. MP2795629 | Completed | 15030 | 15480 | 2017-10-27 | 2018-06-22
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/756442 — Construction of IAY House -IAY REG. NO. MP2795694 | Completed | 15030 | 14448 | 2017-10-27 | 2019-07-30
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/756503 — Construction of IAY House -IAY REG. NO. MP2797689 | Completed | 15030 | 16576 | 2017-10-27 | 2018-08-03
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/762270 — Construction of IAY House -IAY REG. NO. MP3066821 | Completed | 15030 | 14824 | 2017-08-08 | 2019-05-28
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/764242 — Construction of IAY House -IAY REG. NO. MP3156420 | Completed | 15030 | 15308 | 2017-08-08 | 2018-08-04
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/764251 — Construction of IAY House -IAY REG. NO. MP3157101 | Completed | 15030 | 15480 | 2017-08-08 | 2018-06-30
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/775570 — Construction of IAY House -IAY REG. NO. MP3706698 | Completed | 15030 | 16340 | 2017-08-08 | 2018-05-17
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/777682 — Construction of IAY House -IAY REG. NO. MP3842132 | Completed | 15030 | 15480 | 2017-10-26 | 2018-06-30
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/787425 — Construction of IAY House -IAY REG. NO. MP1622399 | Completed | 15480 | 15336 | 2017-10-26 | 2019-06-06
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/790787 — Construction of IAY House -IAY REG. NO. MP1852834 | Completed | 15480 | 15512 | 2017-10-31 | 2018-09-01
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/801069 — Construction of IAY House -IAY REG. NO. MP2769685 | Completed | 15480 | 15468 | 2017-10-26 | 2018-06-30
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/801070 — Construction of IAY House -IAY REG. NO. MP2769768 | Completed | 15480 | 15476 | 2017-10-26 | 2018-06-30
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/801294 — Construction of IAY House -IAY REG. NO. MP2795561 | Completed | 15480 | 14624 | 2017-10-26 | 2019-07-30
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/801346 — Construction of IAY House -IAY REG. NO. MP2801405 | Completed | 15480 | 15480 | 2017-10-26 | 2018-06-30
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/801382 — Construction of IAY House -IAY REG. NO. MP2805419 | Completed | 15480 | 15668 | 2017-10-27 | 2018-08-03
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/802953 — Construction of IAY House -IAY REG. NO. MP3042420 | Completed | 15480 | 15348 | 2017-10-27 | 2019-06-06
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/803728 — Construction of IAY House -IAY REG. NO. MP3159715 | Completed | 15480 | 16256 | 2017-10-26 | 2018-11-30
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/804017 — Construction of IAY House -IAY REG. NO. MP3204547 | Completed | 15480 | 15598 | 2017-08-08 | 2018-08-04
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/951694 — Construction of IAY House -IAY REG. NO. MP3087271 | Completed | 15480 | 15380 | 2017-08-08 | 2019-06-06
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/954920 — Construction of IAY House -IAY REG. NO. MP3170898 | Completed | 15480 | 15824 | 2017-10-26 | 2018-09-01
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/958282 — Construction of IAY House -IAY REG. NO. MP3245230 | Completed | 15480 | 15480 | 2017-10-26 | 2018-06-30
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/959344 — Construction of IAY House -IAY REG. NO. MP3271041 | Completed | 15480 | 15168 | 2017-12-18 | 2019-05-28
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/960378 — Construction of IAY House -IAY REG. NO. MP3298338 | Completed | 15480 | 15824 | 2017-10-26 | 2018-09-01
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/960420 — Construction of IAY House -IAY REG. NO. MP3299228 | Completed | 15480 | 15824 | 2017-08-08 | 2018-05-17
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/960654 — Construction of IAY House -IAY REG. NO. MP3305668 | Completed | 15480 | 15480 | 2017-10-26 | 2018-08-04
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/960711 — Construction of IAY House -IAY REG. NO. MP3306848 | Completed | 17100 | 16251 | 2017-10-27 | 2021-06-07
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/974586 — Construction of IAY House -IAY REG. NO. MP3669654 | Completed | 15480 | 15716 | 2018-03-08 | 2018-11-18
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/975093 — Construction of IAY House -IAY REG. NO. MP3687981 | Completed | 15480 | 14730 | 2018-03-08 | 2019-05-28
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/975556 — Construction of IAY House -IAY REG. NO. MP3706685 | Completed | 15480 | 15480 | 2017-08-08 | 2018-08-04
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/975940 — Construction of IAY House -IAY REG. NO. MP3722440 | Completed | 15480 | 14972 | 2017-08-08 | 2019-07-30
JABALPUR / SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733001049/IF/IAY/978752 — Construction of IAY House -IAY REG. NO. MP3830755 | Completed | 15480 | 15158 | 2017-10-26 | 2019-05-28
JABALPUR / SIHORA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/139 — दुर्गाबाई पिता/पति कोडीलाल के खेत में मेड बंधान का | Completed | 12000 | 17836 | 2009-06-13 | 2010-07-06
JABALPUR / SIHORA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/140 — गंगाराम पिता/पति विश्राम के खेत में मेड बंधान कार् | Completed | 12100 | 3731 | 2009-06-26 | 2010-07-06
JABALPUR / SIHORA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/141 — पुरूषोत्‍तम पिता/पति रामदयाल के खेत में मेड बंधान | Completed | 12100 | 5369 | 2009-06-23 | 2010-07-06
JABALPUR / SIHORA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/142 — कैलाश पिता/पति गयाप्रसाद के खेत में मेड बंधान कार् | Completed | 12100 | 19292 | 2009-06-06 | 2010-07-06
JABALPUR / SIHORA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/143 — चंद्रभान पिता/पति विष्‍णु के खेत में मेड बंधान कार | Completed | 12100 | 9191 | 2009-06-22 | 2010-07-06
JABALPUR / SIHORA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/144 — समनीबाई पिता/पति रामदयाल के खेत में मेड बंधान कार् | Completed | 12000 | 2093 | 2009-06-22 | 2010-07-06
JABALPUR / SIHORA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/145 — रामकेश पिता/पति रामप्रकाश के खेत में मेड बंधान कार्य | Completed | 0 | 1729 | 2009-06-25 | 2010-07-09
JABALPUR / SIHORA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/146 — तुलसीबाई पिता/पति विश्राम के खेत में मेड बंधान कार | Completed | 12000 | 13650 | 2009-06-15 | 2010-07-06
JABALPUR / SIHORA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/147 — रामकिशोर पिता/पति विषम्‍भर के खेत में मेड बंधान का | Completed | 12000 | 18291 | 2009-06-13 | 2010-07-06
JABALPUR / SIHORA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/148 — सुमरतीबाई पिता/पति जयसिंग के खेत में मेड बंधान कार | Completed | 12000 | 5005 | 2009-06-06 | 2010-07-06
JABALPUR / SIHORA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/22012034241076 — mad.b.canga bahi/mamesh | Completed | 42200000 | 35881 | 2015-12-02 | 2016-07-21
JABALPUR / SIHORA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/22012034241080 — mad.b rajendr/harilal | Completed | 42200 | 1 | 2015-12-02 | 2016-07-21
JABALPUR / SIHORA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/22012034241086 — mad b.manik lal/babu lal | Completed | 13000000 | 11997 | 2015-12-02 | 2016-07-21
JABALPUR / SIHORA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/22012034241094 — mad b/milan/lasgar | Completed | 31200 | 1 | 2015-12-02 | 2016-07-21
JABALPUR / SIHORA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/22012034241099 — mad b.sumant bai/mangee lal | Completed | 25700000 | 1 | 2015-12-02 | 2016-05-21
JABALPUR / SIHORA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/22012034241101 — mad b/bhakoli/besakhu | Completed | 42200 | 8110 | 2015-12-07 | 2016-07-21
JABALPUR / SIHORA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/22012034242427 — mad b gaynshi/pardeshi | Completed | 10400 | 1 | 2015-12-07 | 2026-02-03
JABALPUR / SIHORA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/22012034242538 — Med-ramkishan/mitthu 15-16 | Completed | 42000 | 1 | 2015-12-07 | 2016-07-21
JABALPUR / SIHORA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/22012034242541 — Med-Shankar/bhukkd dahiya 14-15 | Completed | 21000 | 1 | 2015-12-07 | 2016-07-21
JABALPUR / SIHORA | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1733001049/LD/22012034244722 — shantidham-Bhanpura 15-16 | Completed | 286000 | 166 | 2015-12-08 | 2017-08-22
JABALPUR / SIHORA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733001049/LD/22012034302287 — shanti dham nirman bhanpura/2016-17 | Completed | 180000 | 174580.84 | 2017-02-18 | 2019-03-15
JABALPUR / SIHORA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/415 — खेल मैदान समतलीकरण गोरैया बाबा | Completed | 494000 | 311989 | 2011-02-02 | 2014-07-31
JABALPUR / SIHORA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/425 — खेल मैदान समतलीकरण भनपुरा | Completed | 494000 | 293704 | 2012-07-07 | 2015-08-28
JABALPUR / SIHORA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733001049/LD/428 — शांति धाम निर्माण ढकरवाह | Completed | 500000 | 433262 | 2011-03-07 | 2014-07-31
JABALPUR / SIHORA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1733001049/RC/127 — भनपुरा से नहर रोड | Completed | 227000 | 381379 | 2009-02-08 | 2010-07-09
JABALPUR / SIHORA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1733001049/RC/144 — भनपुरा से खमरिया पहुच मार्ग | Completed | 0 | 355610 | 2009-02-27 | 2010-04-24
JABALPUR / SIHORA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733001049/RC/22012034193261 — CC Road-Shashi Patel ls Makoli Dumar ke ghar ds be | Completed | 42000 | 40260 | 2013-12-11 | 2015-07-06
JABALPUR / SIHORA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733001049/RC/22012034193265 — CC Road-Narmada Patel ke ghar se Makoli Dumar ke g | Completed | 131000 | 129668.84 | 2013-12-11 | 2015-07-06
JABALPUR / SIHORA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733001049/RC/22012034224309 — .c.c.road wa nali nirmaan hend punp seganesh edahi | Completed | 68000 | 40947.8 | 2014-07-09 | 2015-04-01
JABALPUR / SIHORA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733001049/RC/22012034228548 — c.c.road - deepchand ke ghar se MS School 6face 14 | Completed | 62500 | 37288 | 2014-09-17 | 2015-07-06
JABALPUR / SIHORA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733001049/RC/22012034284879 — CC Road-Naresh ke ghar se vishnu & Raghuveer se Bhagwat 7th 15-16 | Completed | 30000 | 3461 | 2015-09-16 | 2016-04-01
JABALPUR / SIHORA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733001049/RC/22012034294838 — CC Road-Handpump se deepchand patel ke ghar tak | Completed | 280000 | 22790.7 | 2014-07-03 | 2016-04-01
JABALPUR / SIHORA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733001049/RC/22012034294995 — cc road-deepchand ke ghar se ps school tak | Completed | 50000 | 24473 | 2014-09-19 | 2016-04-01
JABALPUR / SIHORA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1733001049/RC/357 — सी सी रोड से हनुमान मंदिर तक मुरमी करण | Completed | 96000 | 91200 | 2010-10-22 | 2011-06-09
JABALPUR / SIHORA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1733001049/RC/454 — Ajay singh ke khet she naher tak marg | Completed | 500000 | 110356 | 2011-06-04 | 2014-07-31
JABALPUR / SIHORA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1733001049/RC/458 — pr. shala bhanpura se ajay ke khet tak marg | Completed | 500000 | 408893.76 | 2011-05-28 | 2014-07-31
JABALPUR / SIHORA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733001049/RC/561 — सीसी रोड पंचपरमेश्‍वर मंदिर से प्राथमिक शाला तक | Completed | 82000 | 60822 | 2012-03-16 | 2014-07-31
JABALPUR / SIHORA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1733001049/RS/22012034511586 — Community sanitary complex_ dhakharwah | Completed | 75000 | 40580 | 2021-03-25 | 2023-07-28
JABALPUR / SIHORA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1733001049/WC/103 — बड़े तालाब बाबा से तिघरा नाला गहरी करण | Completed | 280000 | 239070 | 2010-04-10 | 2010-06-27
JABALPUR / SIHORA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1733001049/WC/154 — हगनी नाला विस्‍तारी करण कार्य | Completed | 431000 | 68686 | 2012-03-12 | 2014-07-31
JABALPUR / SIHORA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1733001049/WC/22012034483291 — pond nirman dhakarwah | Completed | 499493.66 | 428211.8 | 2020-02-02 | 2020-11-12
JABALPUR / SIHORA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1733001049/WC/22012034546450 — Pond nirman Bada k pass | Completed | 481780.64 | 353622 | 2020-05-24 | 2020-11-06
JABALPUR / SIHORA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1733001049/WC/22012034593230 — community pond- dhakarwah | Completed | 567996.81 | 513570 | 2020-11-19 | 2021-07-10
JABALPUR / SIHORA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1733001049/WC/22012034609007 — Check dam_ dakharwah | Completed | 820431.92 | 811042.46 | 2021-03-25 | 2021-09-29
JABALPUR / SIHORA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1733001049/WC/22012034620401 — Community pond _ guraiya baba ke pas | Completed | 380313.48 | 331652 | 2021-03-11 | 2021-07-10
JABALPUR / SIHORA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1733001049/WC/22012034654800 — CAT COMMUNITY POND- DHAKARWAH | Completed | 369513.99 | 223944 | 2021-06-03 | 2025-05-22
JABALPUR / SIHORA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1733001049/WC/89 — पिपरिया नाला से तिघरा नाला गहरीकरण | Completed | 280000 | 275283 | 2010-03-14 | 2010-04-24
JABALPUR / SIHORA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1733001049/WH/22012034909215 — talab jiddodhar karya gram bhanpura | Completed | 238000 | 174990 | 2022-03-08 | 2022-11-11
JABALPUR / SIHORA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1733/RC/4500303 — Grevel Road Phanwani kumhi to Bhanpura, Sihora | Completed | 3039000 | 927157.9 | 2010-07-23 | 2013-01-11