## Work List
Exported on: 2026-10-11 04:28:45
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BANKHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR / MAJHOULI | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1733002045/AV/22012034624502 — Boundary wall Convergence - PS School Bankhedi- panchayat bhawan 22-23 | Ongoing | 31000 | 0 | 2022-11-19
JABALPUR / MAJHOULI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1733002045/DP/22012034622074 — Plantation - Mandir Ke paas 24-25 | Approved | 812728.34 | 0 | 2024-06-08
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733002045/IF/22012035603649 — Ek Bagiya Maa Ke naam - Seema Bai Gram Gurda | Ongoing | 270536.27 | 0 | 2025-09-04
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733002045/IF/22012035642100 — Ek Bagiya Maa Ke naam - Choti Bai Gram-Gurda | Approved | 151167 | 0 | 2025-08-01
JABALPUR / MAJHOULI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/4559505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114971833 | Approved | 27000 | 0 | 2024-09-12
JABALPUR / MAJHOULI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/4559551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114976969 | Approved | 27000 | 0 | 2024-09-11
JABALPUR / MAJHOULI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/4562157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115150215 | Ongoing | 27000 | 0 | 2026-05-14
JABALPUR / MAJHOULI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/4582026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119579877 | Ongoing | 27000 | 0 | 2026-05-14
JABALPUR / MAJHOULI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/4582027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119579928 | Ongoing | 27000 | 0 | 2026-05-14
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/4593136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121864625 | Ongoing | 27000 | 0 | 2026-02-12
JABALPUR / MAJHOULI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/4599695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122667910 | Ongoing | 27000 | 0 | 2026-06-02
JABALPUR / MAJHOULI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/4600115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122933868 | Approved | 27000 | 0 | 2024-09-10
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/4944877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114971852 | Completed | 27000 | 0 | 2026-01-14 | 2026-09-15
JABALPUR / MAJHOULI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/4951073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119580056 | Approved | 27000 | 0 | 2025-02-17
JABALPUR / MAJHOULI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/4958047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122934190 | Ongoing | 27000 | 0 | 2025-03-20
JABALPUR / MAJHOULI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5138212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121864938 | Approved | 27000 | 0 | 2025-03-12
JABALPUR / MAJHOULI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/52659 — Construction of IAY House -IAY REG. NO. MP-33-002-045-001/1 | Approved | 27000 | 0 | 2015-10-23
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5520208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114964645 | Ongoing | 27000 | 0 | 2026-02-24
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5623361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115150384 | Ongoing | 27000 | 0 | 2026-01-14
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5779691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121668868 | Physically Completed | 27000 | 10440 | 2026-02-24 | 2026-10-09
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5779906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123147916 | Physically Completed | 27000 | 10440 | 2026-02-10 | 2026-10-09
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5779908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123149467 | Ongoing | 27000 | 0 | 2026-02-12
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5779948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123704886 | Physically Completed | 27000 | 10440 | 2026-02-10 | 2026-10-09
JABALPUR / MAJHOULI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5780047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114963212 | Approved | 27000 | 0 | 2025-03-12
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5780058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115150260 | Ongoing | 27000 | 9396 | 2026-02-19
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5780067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121650480 | Approved | 27000 | 0 | 2025-04-08
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5780090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122933120 | Completed | 27000 | 5220 | 2026-01-14 | 2026-09-15
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5780093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121864319 | Ongoing | 27000 | 14877 | 2026-02-12
JABALPUR / MAJHOULI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5780777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114955141 | Ongoing | 27000 | 0 | 2026-06-02
JABALPUR / MAJHOULI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5780926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123705164 | Ongoing | 27000 | 9135 | 2026-08-14
JABALPUR / MAJHOULI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5781194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119594350 | Approved | 27000 | 0 | 2025-03-12
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5781825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114973416 | Ongoing | 27000 | 10179 | 2026-02-12
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5781944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114975447 | Ongoing | 27000 | 9657 | 2026-02-10
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5781984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115026895 | Ongoing | 27000 | 0 | 2025-12-22
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5782134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123150373 | Physically Completed | 27000 | 10440 | 2026-02-12 | 2026-10-09
JABALPUR / MAJHOULI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5782143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115164171 | Approved | 27000 | 0 | 2025-03-13
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5782578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122667705 | Ongoing | 27000 | 0 | 2025-09-12
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002045/IF/IAY/5782749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122934843 | Ongoing | 27000 | 5220 | 2025-09-10
JABALPUR / MAJHOULI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1733002045/RC/22012034827266 — Construction of gravel road Asharaam se bhatiya mohalla | Approved | 0 | 0 | 2024-04-26
JABALPUR / MAJHOULI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1733002045/RS/22012034692218 — CC Nali Convergence - Ramdev ke ghar se jadeesh ke ghar Bankhedi 22-23 | Ongoing | 7000 | 0 | 2023-09-20
JABALPUR / MAJHOULI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1733002045/RS/22012035129843 — CC Nali Convergence - Ramlal ke ghar se Rajjan Khangar Gurda 24-25 | Approved | 36000 | 0 | 2024-06-08
JABALPUR / MAJHOULI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1733002045/RS/22012035129845 — CC Nali Convergence - Ashish ke ghar se Kallu Bai ke ghar tak Gurda 24-25 | Approved | 29000 | 0 | 2024-06-08
JABALPUR / MAJHOULI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733002045/WC/22012035014846 — cantoor tranch bankheri 02 | Ongoing | 657536.28 | 0 | 2024-01-20
JABALPUR / MAJHOULI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1733002045/WC/22012035208669 — Talab nirman karya bankheri koni road me | Approved | 0 | 0 | 2024-04-26
JABALPUR / MAJHOULI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1733002045/WC/22012035208670 — Ckeck dem talab danwahi me | Approved | 0 | 0 | 2024-04-26