## Work List
Exported on: 2026-10-21 17:14:56
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PADWAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR / MAJHOULI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & Maintenance of Play field for Community / Repair & Maintenance of Play Ground for Government School for Community | Repair & Maint of Community infrastructure | 1733002056/AV/22012034563599 — khel medan aganwadi parisar me | Ongoing | 133216.67 | 0 | 2021-04-10
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1733002056/IF/22012035412884 — Khet Talab - Santosh/Jagdeesh Prasad | Ongoing | 147621.16 | 0 | 2025-05-10
JABALPUR / MAJHOULI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733002056/IF/IAY/1729504 — Construction of IAY House -IAY REG. NO. MP2428174 | Ongoing | 27000 | 0 | 2018-05-22
JABALPUR / MAJHOULI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002056/IF/IAY/2219534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2513382 | Ongoing | 27000 | 0 | 2019-10-16
JABALPUR / MAJHOULI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002056/IF/IAY/2473442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3765599 | Ongoing | 27000 | 0 | 2020-06-06
JABALPUR / MAJHOULI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002056/IF/IAY/2568059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3983267 | Ongoing | 27000 | 0 | 2020-06-14
JABALPUR / MAJHOULI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002056/IF/IAY/3287747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1449861 | Approved | 27000 | 0 | 2021-10-26
JABALPUR / MAJHOULI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002056/IF/IAY/3288487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2484916 | Ongoing | 27000 | 0 | 2022-02-04
JABALPUR / MAJHOULI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002056/IF/IAY/3292806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4761547 | Ongoing | 27000 | 0 | 2022-02-04
JABALPUR / MAJHOULI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002056/IF/IAY/3353327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5659815 | Approved | 27000 | 0 | 2021-11-12
JABALPUR / MAJHOULI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002056/IF/IAY/3709596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114822231 | Approved | 27000 | 0 | 2022-05-02
JABALPUR / MAJHOULI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002056/IF/IAY/4649506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145476583 | Ongoing | 27000 | 0 | 2024-12-08
JABALPUR / MAJHOULI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733002056/IF/IAY/4748413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114808459 | Approved | 27000 | 0 | 2024-10-06
JABALPUR / MAJHOULI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733002056/IF/IAY/59435 — Construction of IAY House -IAY REG. NO. MP-33-002-056-001/117 | Approved | 27000 | 0 | 2015-12-17
JABALPUR / MAJHOULI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733002056/IF/IAY/59436 — Construction of IAY House -IAY REG. NO. MP-33-002-056-001/201 | Approved | 27000 | 0 | 2015-12-17
JABALPUR / MAJHOULI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1733002056/RS/22012034677947 — Community Sanitary Complex - School Prangan Padwar 22-23 | Ongoing | 47000 | 0 | 2023-01-15
JABALPUR / MAJHOULI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1733002056/RS/22012035121738 — CC Nali Convergence - Bharwa Tola me Raghuveer kachhi ke ghar se Marhi mata ki or 23-24 | Ongoing | 18000 | 0 | 2024-06-22
JABALPUR / MAJHOULI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1733002056/WC/22012035205135 — Talab Renovation - Bhatwa Padwaar 24-25 | Approved | 0 | 0 | 2024-06-12