## Work List
Exported on: 2026-09-06 10:18:55
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MUDIYA BHARAUD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR / MAJHOULI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1733002070/AV/22012034658860 — Puliya Convergence - PS School Mahagwa ke paas 24-25 | Ongoing | 27000 | 0 | 2024-10-26
JABALPUR / MAJHOULI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1733002070/DP/22012034588989 — Amrit Vatica - Mudiya Madod 23-24 | Ongoing | 55847.4 | 0 | 2023-08-10
JABALPUR / MAJHOULI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/1020764 — Construction of IAY House -IAY REG. NO. MP1972206 | Ongoing | 27000 | 0 | 2017-08-25
JABALPUR / MAJHOULI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/2017331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3011384 | Ongoing | 27000 | 0 | 2020-06-11
JABALPUR / MAJHOULI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/3668912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115678941 | Approved | 27000 | 0 | 2022-04-29
JABALPUR / MAJHOULI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/3672097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114140713 | Approved | 27000 | 0 | 2022-04-30
JABALPUR / MAJHOULI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/3679746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115098150 | Approved | 27000 | 0 | 2022-05-01
JABALPUR / MAJHOULI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/3684154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106554113 | Ongoing | 27000 | 0 | 2022-10-15
JABALPUR / MAJHOULI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/3697004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115253364 | Approved | 27000 | 0 | 2022-05-01
JABALPUR / MAJHOULI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/3697005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115253655 | Approved | 27000 | 0 | 2022-05-01
JABALPUR / MAJHOULI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/3716247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114934606 | Approved | 27000 | 0 | 2022-04-29
JABALPUR / MAJHOULI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/3802564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115253888 | Approved | 27000 | 0 | 2022-05-03
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/5163177 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116013650 | Ongoing | 27000 | 0 | 2025-05-26
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/52672 — Construction of IAY House -IAY REG. NO. MP-33-002-070-002/99 | Ongoing | 27000 | 0 | 2025-06-06
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/5308531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115097915 | Ongoing | 27000 | 0 | 2025-05-26
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/5466040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115252575 | Ongoing | 27000 | 0 | 2025-06-13
JABALPUR / MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/5718822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113999207 | Ongoing | 27000 | 0 | 2025-08-27
JABALPUR / MAJHOULI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/5881614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115097567 | Ongoing | 27000 | 0 | 2026-05-19
JABALPUR / MAJHOULI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/6141597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106464264 | Ongoing | 27000 | 10500 | 2026-06-17
JABALPUR / MAJHOULI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/6146246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113567035 | Ongoing | 27000 | 6300 | 2026-06-17
JABALPUR / MAJHOULI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002070/IF/IAY/652166 — Construction of IAY House -IAY REG. NO. MP1029770 | Ongoing | 27000 | 0 | 2017-04-07
JABALPUR / MAJHOULI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1733002070/LD/22012034470615 — charagah amoda | Ongoing | 1592469.08 | 0 | 2020-07-14
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035329778 — cuntoor tranch - abhimannu ke ghar k paas | Deleted | 201335.8 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035329783 — cantoor trench ramphal k ghar k paas mahgawan | Deleted | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035329785 — cantoor trench basant k ghar k paas | Deleted | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035329789 — cantoor trench kodu barman k ghar k paas | Deleted | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035329804 — cantoor trench pashu oushghalaya k piche | Deleted | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035329806 — cantoor trench high shcool ke paas | Deleted | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035329807 — cantoor trench kodu k khet k paas | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035330023 — CANTOOR Trenches RAMPHAL PARDHANKE GHAR KE PEECHHE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035330025 — CANTOOR Trenches PASUOUSDHALY KE PEECHHE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035330027 — CANTOOR Trenches KODU KE GHAR KE PICHHE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035330028 — CANTOOR Trenches CHETRAM KE GHAR PICHEE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035330030 — CANTOOR Trenches SUSEEL YADAV KE GHAR KE PEECHE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035330031 — CANTOOR Trenches BASANT KE GHAR KE PEECHE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035330036 — CANTOOR Trenches bindee ke ghsr peeche | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035332593 — CANTOOR Trenches JOGAN TALAB KE AGE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035332594 — CANTOOR Trenches RAMAN BARMAN KE GHAR KE PICHE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035332595 — CANTOOR Trenches SAMUDAYAK BHAVAN KE PICHHE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035332596 — CANTOOR Trenches HARDYAL KE GHAR KE PICHHE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035332597 — CANTOOR Trenches BISRAM KE GHAR KE PEECHE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035332599 — CANTOOR Trenches SURESH THATU KE GHAR KE PEECHE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035332602 — CANTOOR Trenches KISHAN KE GHAR KE PEECHE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035332603 — CANTOOR Trenches CHHATRA BAS KE GHAR KE PEECHE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035332605 — CANTOOR Trenches PREM YADAV KE GHAR KE PEECHE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035332606 — CANTOOR Trenches DILLI VALE KE GHAR KE PEECHE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035332607 — CANTOOR Trenches PAKKU KE GHAR KE PEECHE | Approved | 0 | 0 | 2026-06-30
JABALPUR / MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002070/WC/VB/22012035332608 — CANTOOR Trenches SONE LAL YADAV KE GHAR KE PEECHE | Approved | 0 | 0 | 2026-06-30