## Work List
Exported on: 2026-10-10 02:42:38
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: BOURIYA
Status: Physically Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR / PATAN | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003010/AV/22012034399554 — CC Road & Naali - Sanju barman(Hendpump) se lakhan & matru ke ghar ki or (18-19) 14vitt | Physically Completed | 49000 | 40020 | 2019-02-12 | 2021-06-17
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003010/IF/IAY/5197791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116793451 | Physically Completed | 23490 | 23490 | 2026-01-26 | 2026-06-18
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003010/IF/IAY/5306991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116793894 | Physically Completed | 23490 | 23490 | 2026-01-26 | 2026-06-11
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003010/IF/IAY/5684765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118169722 | Physically Completed | 23490 | 23490 | 2025-09-15 | 2026-02-08