## Work List
Exported on: 2026-09-05 21:30:08
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SEHSAN (PADARIYA)
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR / PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1733003010/RS/22012034651805 — JAM SOAK PIT NIRMAN KARY MANGUDIYA HAND PUMP | Ongoing | 2200 | 0 | 2023-10-08
JABALPUR / PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & maintenance of Kitchen shed / Repair and Maintenance of Kitchen shed Building for Community | Repair & Maint of Community infrastructure | 1733003025/AV/22012034647379 — Kirchen Shed me nayi chhat height badhana flooring plaster putai kary gram sigantalai | Ongoing | 8000 | 0 | 2023-10-08
JABALPUR / PATAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1733003025/DP/22012034582909 — Podharopan karya Hasua sab miner narbad ke khet se karari ki or gram shasan | Ongoing | 435815.48 | 0 | 2023-08-17
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003025/IF/22012035483227 — Khet talab nirman karya Rakesh chadar /Biran Sigantalai | Approved | 55865.38 | 0 | 2025-04-14
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003025/IF/22012035483480 — Khet talab nirman karya Gulab sing/Babulal shasan | New | 0 | 0 | 2025-04-14
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003025/IF/22012035484173 — Khet talab nirman karya Gulab sing/Babulal shasan | Approved | 55865.38 | 0 | 2025-04-14
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733003025/IF/22012035633125 — एक बगिया माँ के नाम रजनी पटेल सहसन पड़रिया | Ongoing | 266578.64 | 261 | 2025-11-09
JABALPUR / PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003025/IF/IAY/5098348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146557243 | Ongoing | 27000 | 0 | 2025-03-24
JABALPUR / PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003025/IF/IAY/5102366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148573370 | Ongoing | 27000 | 1827 | 2025-03-20
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003025/IF/IAY/5151878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147711991 | Ongoing | 27000 | 7308 | 2025-07-23
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003025/IF/IAY/5153806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117887445 | Ongoing | 27000 | 3654 | 2025-10-24
JABALPUR / PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003025/IF/IAY/5223934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147797128 | Approved | 27000 | 0 | 2025-02-17
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003025/IF/IAY/5226972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147711967 | Ongoing | 27000 | 7308 | 2025-10-04
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003025/IF/IAY/5656224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148575127 | Ongoing | 27000 | 0 | 2026-08-21
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003025/IF/IAY/5671240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146562185 | Approved | 27000 | 0 | 2025-05-30
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003025/IF/IAY/5675416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113633768 | Ongoing | 27000 | 12030 | 2026-06-12
JABALPUR / PATAN | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003025/IF/IAY/935221 — Construction of IAY House -IAY REG. NO. MP2723312 | Approved | 27000 | 0 | 2017-04-12
JABALPUR / PATAN | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1733003025/RC/22012034840311 — एप्रोच रोड निर्माण कार्य पड़रिया मुख्य मार्ग से शांति धाम तक ग्राम सहसन | Ongoing | 1196402.35 | 0 | 2025-03-28
JABALPUR / PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1733003025/RS/22012034651837 — JAM SOAK PIT NIRMAN KARY P.S.SCHOOL SIGANTALI HAND PUMP KE PASS | Ongoing | 2200 | 0 | 2023-10-07
JABALPUR / PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1733003025/RS/22012034651893 — JAM SOAK PIT NIRMAN KARY PIPARIYA KE HAND PUMP KE PASS | Ongoing | 2200 | 0 | 2023-10-05
JABALPUR / PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1733003025/RS/22012034651904 — JAM SOAK PIT NIRMAN KARY CHODHARI MOHALLE KE HAND PUMP KE PASS | Ongoing | 2200 | 0 | 2023-10-03
JABALPUR / PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733003025/RS/22012035117248 — R C C Nali Nirman Nitin Patel ke ghar se Heera Lal ke ghar ki or nali nirman kary | Ongoing | 17000 | 0 | 2023-10-08
JABALPUR / PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Multi Unit Toilets for School / Construction of Multi Unit Toilets for School | Construction of Toilets | 1733003025/RS/22012035125882 — Shouchalaya Nirman Kary Sha. Prath. Shala Gram Sehsan | Ongoing | 21000 | 0 | 2024-03-14
JABALPUR / PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733003025/RS/22012035127207 — R.C.C NALI NIRMAN KARY PARASRAM CHODHARI KE GHAR SE TALAB TAK SHASAN | Ongoing | 17000 | 0 | 2024-03-16