## Work List
Exported on: 2026-10-21 16:35:39
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: HARDUA (MADWA)
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR / PATAN | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733003041/AV/22012034658760 — Shanti dham nirman karya pipariya | New | 0 | 0 | 2024-05-21
JABALPUR / PATAN | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733003041/AV/22012034658820 — shanti dam nirman karya hardua | New | 0 | 0 | 2024-05-26
JABALPUR / PATAN | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733003041/AV/22012034658821 — shanti dam nirman karya hardua | New | 222300 | 0 | 2024-05-26
JABALPUR / PATAN | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733003041/AV/22012034658822 — Shanti dham nirman karya pipariya | New | 197000 | 0 | 2024-06-23
JABALPUR / PATAN | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Village/Rural Haat for community / Construction of Rural Haat Building for Community | Construction of Village Haats | 1733003041/AV/22012034661596 — Water Proofing awam annya karya PS School hardua | New | 0 | 0 | 2024-06-12
JABALPUR / PATAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation-Horticulture - Community / Canal Line Plantation for Community | Plantation | 1733003041/DP/22012034580873 — samudayak vrasharopan karya panchyat bhavan se nadi ki or | Ongoing | 846516.97 | 0 | 2023-09-05
JABALPUR / PATAN | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1733003041/IF/22012034992559 — Khet talab nirman karya Kalu Singh/ran | Ongoing | 188342.05 | 0 | 2023-06-15
JABALPUR / PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Block Plantation of Forestry Trees in fields for Individual | Other Works | 1733003041/IF/22012035131977 — Hket ki med par vrakchharopan karya in groups,ramsingh,ramdas,umesh harduwa | Ongoing | 130836.89 | 0 | 2024-08-13
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733003041/IF/22012035600492 — Ek bagiya ma ke naam Laxmi bai gram hardua GP hardua madwa | Ongoing | 238731.49 | 0 | 2025-09-04
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733003041/IF/22012035602288 — Ek bagiya ma ke naam VIMLA BAI gram Harduwa gp Harduwa Madwa | Ongoing | 238731.49 | 10696 | 2025-09-03
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733003041/IF/22012035627221 — Ek bagiya Maa ke Naam MUNDO BAI gram Harduwa GP Harduwa Madwa | New | 0 | 0 | 2025-04-14
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733003041/IF/22012035635727 — Ek bagiya Maa ke naam SUHAG RANI gram Harduwa GP Harduwa Madwa | Ongoing | 241541.63 | 13510 | 2026-04-22
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733003041/IF/22012035635732 — Ek bagiya Maa ke naam BATTO BAI gram Harduwa Harduwa Madwa | Ongoing | 241541.63 | 13216 | 2025-12-11
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733003041/IF/22012035639078 — Ek bagiya maa ke naam VIMLA GOUND gram Harduwa GP Harduwa Madwa | Approved | 241541.63 | 0 | 2025-04-14
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733003041/IF/22012035643517 — Ek bagiya Maa ke naam Mundo bai Gram Hardua Gram Panchayat Hardua Madwa | New | 0 | 0 | 2025-04-14
JABALPUR / PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/3288808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2774856 | Approved | 27000 | 0 | 2021-10-26
JABALPUR / PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/4561005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114997299 | Ongoing | 27000 | 0 | 2025-03-22
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/5199744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114756155 | Ongoing | 27000 | 0 | 2025-05-29
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/5277819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113836503 | Ongoing | 27000 | 15660 | 2026-07-18
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/5330326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106722385 | Ongoing | 27000 | 0 | 2026-06-02
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/5344303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113570796 | Approved | 27000 | 0 | 2025-04-01
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/5429270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114007383 | Ongoing | 27000 | 0 | 2025-07-04
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6004375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113570561 | Ongoing | 27000 | 0 | 2026-06-09
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6004376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113570732 | Ongoing | 27000 | 0 | 2026-07-18
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6004377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113570743 | Ongoing | 27000 | 19515 | 2026-07-18
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6005391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114007249 | Approved | 27000 | 0 | 2026-03-06
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6009190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113836427 | Approved | 27000 | 0 | 2026-03-02
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6009191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113836464 | Approved | 27000 | 0 | 2026-03-06
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6009204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113782749 | Ongoing | 27000 | 23460 | 2026-08-05
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6009205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113782857 | Approved | 27000 | 0 | 2026-03-02
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6009206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113782884 | Ongoing | 27000 | 3915 | 2026-07-18
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6009281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113525684 | Ongoing | 27000 | 23460 | 2026-08-05
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6009925 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107011962 | Approved | 27000 | 0 | 2026-02-12
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6010845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113570841 | Approved | 27000 | 0 | 2026-03-06
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6010846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113570892 | Ongoing | 27000 | 15630 | 2026-07-02
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6010847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113570958 | Approved | 27000 | 0 | 2026-03-02
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6122855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114996835 | Ongoing | 27000 | 7830 | 2026-07-08
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6122924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113782448 | Approved | 27000 | 0 | 2026-03-08
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6128808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114756517 | Physically Completed | 27000 | 11730 | 2026-06-09 | 2026-09-17
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6140992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114930955 | Physically Completed | 27000 | 23490 | 2026-07-28 | 2026-10-11
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6140993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114930980 | Approved | 27000 | 0 | 2026-03-11
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6142325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106702774 | Approved | 27000 | 0 | 2026-03-08
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6142793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106903427 | Approved | 27000 | 0 | 2026-03-11
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6146604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113782796 | Approved | 27000 | 0 | 2026-03-06
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6149448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114901096 | Approved | 27000 | 0 | 2026-03-08
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6156037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113836390 | Ongoing | 27000 | 0 | 2026-07-04
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6156038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113836406 | Approved | 27000 | 0 | 2026-03-08
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6171337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114007336 | Approved | 27000 | 0 | 2026-03-08
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6171340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114007836 | Approved | 27000 | 0 | 2026-03-06
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6171341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114007855 | Approved | 27000 | 0 | 2026-03-06
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6171943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113570545 | Ongoing | 27000 | 15600 | 2026-07-18
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6171944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113570608 | Approved | 27000 | 0 | 2026-03-08
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6171945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113570623 | Ongoing | 27000 | 0 | 2026-07-18
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6172304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114007375 | Approved | 27000 | 0 | 2026-03-06
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6175412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106694864 | Ongoing | 27000 | 7815 | 2026-08-05
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6176257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114007117 | Approved | 27000 | 0 | 2026-03-11
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6176363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106726924 | Approved | 27000 | 0 | 2026-03-11
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6181154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113570637 | Approved | 27000 | 0 | 2026-03-11
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6181637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107011952 | Approved | 27000 | 0 | 2026-03-08
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6181782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106709682 | Approved | 27000 | 0 | 2026-03-17
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6187611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114007316 | Approved | 27000 | 0 | 2026-03-08
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6188083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114007033 | Approved | 27000 | 0 | 2026-03-11
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6191628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114006952 | Approved | 27000 | 0 | 2026-03-17
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6191803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113836489 | Ongoing | 27000 | 15660 | 2026-07-21
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6192106 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106715363 | Approved | 27000 | 0 | 2026-03-11
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6197227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113570652 | Approved | 27000 | 0 | 2026-03-10
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6208610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106903446 | Approved | 27000 | 0 | 2026-03-10
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6213388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114006869 | Approved | 27000 | 0 | 2026-03-17
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6248152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106903388 | Ongoing | 27000 | 0 | 2026-10-13
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6250039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114007285 | Approved | 27000 | 0 | 2026-05-05
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6250155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114762102 | Approved | 27000 | 0 | 2026-05-04
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6250388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114930948 | Approved | 27000 | 0 | 2026-04-13
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6250389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114930959 | Approved | 27000 | 0 | 2026-05-04
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6250390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114930976 | Approved | 27000 | 0 | 2026-05-04
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6279982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106724781 | Approved | 27000 | 0 | 2026-04-01
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6293039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107011938 | Approved | 27000 | 0 | 2026-05-01
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6295917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114007972 | Approved | 27000 | 0 | 2026-04-01
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6302675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106709704 | Approved | 27000 | 0 | 2026-05-04
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6306450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113782717 | Approved | 27000 | 0 | 2026-05-05
JABALPUR / PATAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6318759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114930963 | Approved | 27000 | 0 | 2026-06-02
JABALPUR / PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/6319766 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107011907 | Approved | 27000 | 0 | 2026-03-08
JABALPUR / PATAN | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733003041/IF/IAY/938185 — Construction of IAY House -IAY REG. NO. MP2788255 | Approved | 27000 | 0 | 2017-04-08
JABALPUR / PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1733003041/RC/22012034650273 — Approach sadak nirman karya chanditola se rashan dukan tak | Ongoing | 2399919.37 | 0 | 2023-10-10
JABALPUR / PATAN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1733003041/WC/22012035213438 — soack pit nirman karya Madhyamik shala ke pass Hardua Madwa | Approved | 2000 | 0 | 2024-06-12
JABALPUR / PATAN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1733003041/WC/22012035213439 — soack pit nirman karya Ramlal ke Ghar ke pass Hardua Madwa | Approved | 2000 | 0 | 2024-06-12
JABALPUR / PATAN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1733003041/WC/22012035213716 — Roof water Harvesting Panchayat bhawan me hardua | Approved | 3000 | 0 | 2024-06-12