## Work List
Exported on: 2026-09-27 20:38:57
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: IMALIA (TIKARI)
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR / PANAGAR | 2020-2021 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1733005004/AV/22012034470846 — गौशाला हेतु चरागाह निर्माण-इमलिया | Ongoing | 1499091.23 | 0 | 2020-05-16
JABALPUR / PANAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1733005004/DP/22012034587057 — PLANTATION BASUDHA VANDAN 75 PLANT TALAB KI MED PAR TIKARI | Ongoing | 55847.4 | 0 | 2023-09-11
JABALPUR / PANAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/3809700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117923771 | Approved | 27000 | 0 | 2022-05-02
JABALPUR / PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/4574060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117923354 | Approved | 27000 | 0 | 2024-12-23
JABALPUR / PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/4750236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117190539 | Ongoing | 27000 | 0 | 2024-12-24
JABALPUR / PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/4753503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117923544 | Approved | 27000 | 0 | 2024-12-25
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/5297313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118144512 | Completed | 23490 | 0 | 2025-05-20 | 2026-08-03
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/5318024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117347355 | Completed | 23490 | 0 | 2025-04-15 | 2026-08-03
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/5329434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118144734 | Completed | 23490 | 0 | 2025-04-20 | 2026-08-03
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/5335040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117924320 | Completed | 23490 | 0 | 2025-04-15 | 2026-08-03
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/5335631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150574382 | Ongoing | 27000 | 0 | 2025-06-13
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/5486299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117344826 | Completed | 23490 | 0 | 2025-08-21 | 2026-08-03
JABALPUR / PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/5754506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117190664 | Approved | 27000 | 0 | 2025-02-19
JABALPUR / PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/5754912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116968516 | Approved | 27000 | 0 | 2025-03-27
JABALPUR / PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/5755730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118567656 | Approved | 27000 | 0 | 2025-03-27
JABALPUR / PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6127624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116968435 | Ongoing | 27000 | 0 | 2026-08-01
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6134074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125843169 | Approved | 27000 | 0 | 2026-02-19
JABALPUR / PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6135296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117347388 | Ongoing | 27000 | 0 | 2026-08-01
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6136969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125869005 | Approved | 27000 | 0 | 2026-02-14
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6137636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117190725 | Approved | 27000 | 0 | 2026-02-19
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6142899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117923665 | Approved | 27000 | 0 | 2026-02-21
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6142900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117923699 | Approved | 27000 | 0 | 2026-02-19
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6142901 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117924136 | Approved | 27000 | 0 | 2026-02-19
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6142902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117924364 | Approved | 27000 | 0 | 2026-02-17
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6143131 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118144025 | Approved | 27000 | 0 | 2026-02-17
JABALPUR / PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6143132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118144101 | Ongoing | 27000 | 0 | 2026-08-01
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6143134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118144812 | Approved | 27000 | 0 | 2026-02-21
JABALPUR / PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6146954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120023235 | Ongoing | 27000 | 0 | 2026-08-01
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6149186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120022914 | Approved | 27000 | 0 | 2026-02-14
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6149187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120022924 | Approved | 27000 | 0 | 2026-02-14
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6151120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125854753 | Approved | 27000 | 0 | 2026-02-28
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6152315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117924176 | Approved | 27000 | 0 | 2026-02-28
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6152316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117924227 | Approved | 27000 | 0 | 2026-02-28
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6158080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118567346 | Approved | 27000 | 0 | 2026-02-19
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6161234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125841804 | Approved | 27000 | 0 | 2026-02-06
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6161263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117923517 | Approved | 27000 | 0 | 2026-02-14
JABALPUR / PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6171899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117332155 | Ongoing | 27000 | 0 | 2026-08-01
JABALPUR / PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6175470 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116968173 | Ongoing | 27000 | 0 | 2026-08-01
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6215532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117923444 | Approved | 27000 | 0 | 2026-03-17
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005004/IF/IAY/6217250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118567911 | Approved | 27000 | 0 | 2026-03-10
JABALPUR / PANAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733005004/RS/22012035128923 — RCC HUME PIPE NALI NIRMAN KAILESH SINGH KE GHAR SE SADAK PAR TAK | Ongoing | 30000 | 0 | 2024-07-05
JABALPUR / PANAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733005004/RS/22012035130790 — RCC HUME PIPE NALI NIRMAN-NEERAJ CHOUBEY SE DHARMENDRA JHARIYA KI OR 15FC AND NREGA IMALIYA TIKARI | Approved | 28500 | 0 | 2024-06-15