## Work List
Exported on: 2026-10-06 23:42:04
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: RAIPURA
Status: Physically Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR / PANAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1733005018/AV/22012034401757 — BHARAT NIRMAN SEVA KENDRA (PANCHAYAT BHAVAN), RAIPURA | Physically Completed | 579200 | 576457.39 | 2019-04-01 | 2026-05-31
JABALPUR / PANAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Repair & Maint of distributary Canal for Community / Repair and Maintenance of distributary Canal for Community | Repair & Maint of Canal | 1733005018/IC/22012034387175 — नहर की सर्विस बेंको में ग्रेवल मार्ग एवं नहर की गाद निकालना, BILAGWA VITRAN-RAIPURA | Physically Completed | 957127.66 | 143124 | 2020-11-23 | 2021-07-18
JABALPUR / PANAGAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1733005018/IF/22012034564000 — MEDH BANDHAN-TINSI/RAMVILAS, RAIPURA | Physically Completed | 28768.6 | 9272 | 2020-06-09 | 2021-07-08
JABALPUR / PANAGAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1733005018/IF/22012034770983 — CTR मेड बंधन कार्य राजकुमार के खेत में | Physically Completed | 56681.21 | 4632 | 2021-06-14 | 2021-07-15
JABALPUR / PANAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005018/IF/IAY/3457071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5506562 | Physically Completed | 17370 | 17144 | 2022-04-18 | 2024-11-21
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005018/IF/IAY/5767705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116714606 | Physically Completed | 23490 | 19575 | 2025-09-11 | 2026-01-12
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005018/IF/IAY/5769116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116071989 | Physically Completed | 23490 | 3915 | 2025-09-11 | 2025-12-23
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005018/IF/IAY/5769162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116255251 | Physically Completed | 23490 | 19575 | 2025-09-11 | 2026-03-22