## Work List
Exported on: 2026-08-18 17:33:01
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: GHANA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR / PANAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/1053842 — Construction of IAY House -IAY REG. NO. MP1289994 | Approved | 23490 | 0 | 2017-05-05
JABALPUR / PANAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/132298 — Construction of IAY House -IAY REG. NO. MP-33-005-035-001/109 | Approved | 23490 | 0 | 2016-02-05
JABALPUR / PANAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/132299 — Construction of IAY House -IAY REG. NO. MP-33-005-035-001/157 | Approved | 23490 | 0 | 2016-02-05
JABALPUR / PANAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/132300 — Construction of IAY House -IAY REG. NO. MP-33-005-035-001/30 | Approved | 23490 | 0 | 2016-02-05
JABALPUR / PANAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/132301 — Construction of IAY House -IAY REG. NO. MP-33-005-035-001/378 | Approved | 23490 | 0 | 2016-02-05
JABALPUR / PANAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/132302 — Construction of IAY House -IAY REG. NO. MP-33-005-035-001/70 | Approved | 23490 | 0 | 2016-02-05
JABALPUR / PANAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/3862902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146499962 | Approved | 23490 | 0 | 2022-05-02
JABALPUR / PANAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/4024764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146499860 | Approved | 23490 | 0 | 2022-05-06
JABALPUR / PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/4855677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114879024 | Ongoing | 23490 | 0 | 2025-03-15
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/5347313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121641024 | Completed | 23490 | 0 | 2025-09-13 | 2026-08-03
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/5348865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114202472 | Ongoing | 23490 | 0 | 2025-09-13
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/5360237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146499364 | Completed | 23490 | 0 | 2025-04-25 | 2026-08-03
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/5374161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146499632 | Approved | 23490 | 0 | 2025-04-03
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/5378386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122888167 | Ongoing | 23490 | 0 | 2025-09-03
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/5381399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146499509 | Ongoing | 23490 | 0 | 2025-04-25
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/5574567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121089263 | Ongoing | 23490 | 0 | 2025-05-11
JABALPUR / PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/5611351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121089223 | Approved | 23490 | 0 | 2025-03-01
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/5972437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114181948 | Approved | 23490 | 0 | 2026-02-06
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/5972642 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146528273 | Approved | 23490 | 0 | 2026-02-24
JABALPUR / PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005035/IF/IAY/6189077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122137821 | Ongoing | 23490 | 0 | 2026-07-11
JABALPUR / PANAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733005035/RC/22012034607420 — CC ROAD SAH NALI NIRMAN-MAIN ROAD SE SUMAN KOL KE GHAR TAK, GHANA | Ongoing | 8820 | 0 | 2022-02-16
JABALPUR / PANAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733005035/RC/22012034607421 — CC ROAD SAH NALI NIRMAN-SUMAN KOL KE GHAR SE JITENDRA RAJAK KE GHAR TAK, GHANA | Ongoing | 9113 | 0 | 2022-02-16
JABALPUR / PANAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733005035/RC/22012034650780 — CC ROAD NIRMAN-VINEET YADAV KE GHAR SE MAMTA JHA KE GHAR TAK, GHANA | Ongoing | 14388 | 0 | 2023-10-13
JABALPUR / PANAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733005035/RC/22012034650781 — CC ROAD NIRMAN-AJAY CHOUTHMAL KE GHAR SE BALRAM MISHRA KE GHAR TAK, GHANA | Ongoing | 13877 | 0 | 2023-10-13
JABALPUR / PANAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733005035/RC/22012034650782 — CC ROAD NIRMAN-SONU PASI KE GHAR SE NAYAR JI KE GHAR TAK, GHANA | Ongoing | 14260 | 0 | 2023-08-29
JABALPUR / PANAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733005035/RC/22012034650783 — CC ROAD NIRMAN-NAYAR JI KE GHAR SE AMIT MAHOBIYA KE GHAR TAK, GHANA | Ongoing | 8771 | 0 | 2023-10-20
JABALPUR / PANAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733005035/RC/22012034668203 — CC ROAD NIRMAN-ASHWINI GOTIYA KE GHAR SE VARUN SHRIVASTAV, GHANA | Ongoing | 10879 | 0 | 2023-11-29
JABALPUR / PANAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733005035/RS/22012035118940 — NALI NIRMAN-ADVIN KE GHAR SE KADIR BHAIJAN, GHANA | Ongoing | 23318 | 0 | 2024-06-11
JABALPUR / PANAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733005035/RS/22012035126502 — NALI NIRMAN-BAPI DADA KE GHAR SE RAJESH VERMA KE GHAR TAK, GHANA | Ongoing | 52600 | 0 | 2024-03-15
JABALPUR / PANAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733005035/RS/22012035126510 — NALI NIRMAN-BHENSASUR MANDIR SE BINDU GOSWAMI KE GHAR TAK, GHANA | Ongoing | 7851 | 0 | 2024-03-15
JABALPUR / PANAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733005035/RS/22012035126517 — NALI NIRMAN-NIRANJAN KE GHAR SE KADIR BHAIJAN KE GHAR TAK, GHANA | Ongoing | 41870 | 0 | 2024-03-15
JABALPUR / PANAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733005035/RS/22012035127230 — madina ke ghar se shankar ji ke mandir tak hume pipe nali | Ongoing | 33920 | 0 | 2024-03-16