## Work List
Exported on: 2026-10-01 21:34:36
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MATAMAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR / PANAGAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1733005044/AV/22012034534333 — गौ-शाला निर्माण कार्य ग्राम मटामर (ग्राम पंचायत मटामर) | Ongoing | 3804449.17 | 0 | 2020-12-16
JABALPUR / PANAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1733005044/AV/22012034639047 — BOUDNARY BALL NIRMAN-SHIKSHA GAURANTEE SHALA PARISAR, MATAMAR | Ongoing | 60963 | 0 | 2023-08-09
JABALPUR / PANAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1733005044/DP/22012034581096 — COMMUNITY PLANTATION FRONT OF GAUSHALA GRAM MATAMAR | Ongoing | 427106.07 | 0 | 2023-07-25
JABALPUR / PANAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Repair & Maint of distributary Canal for Community / Repair and Maintenance of distributary Canal for Community | Repair & Maint of Canal | 1733005044/IC/22012034387053 — नहर की सर्विस बेंको में ग्रेवल मार्ग एवं नहर की गाद निकालना, MATAMAR MINER-MATAMAR | Ongoing | 999223.51 | 0 | 2021-05-21
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733005044/IF/22012035568342 — JGSA KHET TALAB NIRMAN KARYA DEVKARAN BALD JALDHARI KE KHET ME GRAM MATAMAR GP MATAMAR | Approved | 0 | 0 | 2025-04-14
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733005044/IF/22012035601737 — EK BAGIYA MAA KE NAAM SONA BAI/JAGANNATH GP MATAMAR | Approved | 158133.16 | 0 | 2025-08-19
JABALPUR / PANAGAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005044/IF/IAY/3182739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3018169 | Approved | 27000 | 0 | 2020-10-22
JABALPUR / PANAGAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005044/IF/IAY/3291373 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4442092 | Ongoing | 27000 | 0 | 2022-02-01
JABALPUR / PANAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005044/IF/IAY/3292845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4768283 | Ongoing | 27000 | 0 | 2023-07-24
JABALPUR / PANAGAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005044/IF/IAY/3292914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4783425 | Ongoing | 27000 | 0 | 2022-02-01
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005044/IF/IAY/5198844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106767552 | Ongoing | 27000 | 0 | 2025-05-24
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005044/IF/IAY/5205434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106767569 | Ongoing | 27000 | 0 | 2025-04-24
JABALPUR / PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005044/IF/IAY/5212445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114849753 | Approved | 27000 | 0 | 2025-02-19
JABALPUR / PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005044/IF/IAY/5466425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115028321 | Ongoing | 27000 | 0 | 2026-06-09
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005044/IF/IAY/5467666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106879455 | Ongoing | 27000 | 0 | 2025-04-24
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005044/IF/IAY/5574230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114103925 | Ongoing | 27000 | 0 | 2025-08-09
JABALPUR / PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005044/IF/IAY/5608969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106521373 | Approved | 27000 | 0 | 2025-02-14
JABALPUR / PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005044/IF/IAY/5659980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106767151 | Ongoing | 27000 | 0 | 2026-08-18
JABALPUR / PANAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005044/IF/IAY/66298 — Construction of IAY House -IAY REG. NO. MP-33-005-044-001/146 | Approved | 27000 | 0 | 2015-12-31
JABALPUR / PANAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Food Grain | Food Grain / Repair and Maintenance of Food grain Storage Building for Community | Constr of Food Grain storage | 1733005044/OP/9425885522 — 100 mt godown nirmn kary | Ongoing | 908000 | 0 | 2014-05-01
JABALPUR / PANAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733005044/RC/22012034645424 — CC ROAD NIRMAN-SHIV MANDIR, MATAMAR | Ongoing | 37000 | 0 | 2023-10-08
JABALPUR / PANAGAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733005044/RC/22012034843525 — CC ROAD NIRMAN NANDI SHREEPAL K GHAR SE PARASRAMKUND KI OR | Approved | 0 | 0 | 2025-04-14
JABALPUR / PANAGAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733005044/RC/22012034843526 — CC ROAD NIRMAN NANDI SHRIPAL K GHAR SE PARASRAMKUND KI OR GRAM MATAMAR | Approved | 0 | 0 | 2025-04-14
JABALPUR / PANAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733005044/RS/22012035136576 — RCC HUME PIPE NALI NIRMAN SHANKAR VISVAKARMA KE GHAR SE JITTU YADAV K GHAR KI OR | Approved | 21000 | 0 | 2025-01-25