## Work List
Exported on: 2026-10-02 08:58:29
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: TINDANI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733005047/IF/22012035599892 — EK BAGIYA MAA KE NAAM SUMMO SINGH/SUNIL SINGH GOND GP TINDANI | Ongoing | 157024.52 | 0 | 2025-09-01
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733005047/IF/22012035599903 — EK BAGIYA MAA KE NAAM MAYA GOND/NARAYAN SINGH GOND GP TINDANI | Ongoing | 159492.11 | 0 | 2025-09-01
JABALPUR / PANAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733005047/IF/IAY/1034725 — Construction of IAY House -IAY REG. NO. MP2603611 | Approved | 27000 | 0 | 2017-04-30
JABALPUR / PANAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733005047/IF/IAY/1035767 — Construction of IAY House -IAY REG. NO. MP2679078 | Approved | 27000 | 0 | 2017-04-30
JABALPUR / PANAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733005047/IF/IAY/1173566 — Construction of IAY House -IAY REG. NO. MP1421764 | Approved | 27000 | 0 | 2017-06-18
JABALPUR / PANAGAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733005047/IF/IAY/3182649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4215910 | Ongoing | 27000 | 0 | 2021-09-19
JABALPUR / PANAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733005047/IF/IAY/3847083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131149544 | Ongoing | 27000 | 0 | 2022-05-27
JABALPUR / PANAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733005047/IF/IAY/4288152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3260232 | Approved | 27000 | 0 | 2022-07-04
JABALPUR / PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733005047/IF/IAY/4638146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131698957 | Ongoing | 27000 | 0 | 2025-01-31
JABALPUR / PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733005047/IF/IAY/4790377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127121565 | Ongoing | 27000 | 0 | 2025-03-04
JABALPUR / PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733005047/IF/IAY/4849222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127120744 | Ongoing | 27000 | 0 | 2024-11-15
JABALPUR / PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733005047/IF/IAY/5363366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143881875 | Approved | 27000 | 0 | 2025-03-21
JABALPUR / PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733005047/IF/IAY/5763133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131149409 | Ongoing | 27000 | 3915 | 2026-09-03
JABALPUR / PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733005047/IF/IAY/5782867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129267889 | Ongoing | 27000 | 0 | 2025-09-16
JABALPUR / PANAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1733005047/RC/22012034827913 — CC ROAD NIRMAN GANESH GOND SE MAIN ROAD 15FC AND NREGA KASHI GP TINDNI | Ongoing | 7400 | 0 | 2025-03-21
JABALPUR / PANAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1733005047/RC/22012034837505 — CC ROAD NIRMAN SONU THAKUR KE GHAR SE JAVAHAR SINGH NREGA AND 15TH FC GRAM KASHI GP TINDNI | Ongoing | 16000 | 0 | 2025-03-23
JABALPUR / PANAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1733005047/RC/22012034837508 — CC ROAD NIRMAN SONU THAKUR KE GHAR SE JAVAHAR SINGH NREGA AND 15TH FC GRAM KASHI GP TINDNI | Approved | 16542 | 0 | 2024-10-02
JABALPUR / PANAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1733005047/RS/22012034645887 — SAMUDAYAK SWACHCHHTA PARISAR NIRMAN-MADHYAMIK SHALA KE PASS, KASHI_TINDNI | Ongoing | 44000 | 0 | 2022-03-16
JABALPUR / PANAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1733005047/RS/22012035128810 — CC एवं hume pipe नाली निर्माण राकेश मिश्रा के घर से हनुमान मन्दिर | Approved | 0 | 0 | 2024-06-22
JABALPUR / PANAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1733005047/RS/22012035132258 — RCC HUME PIPE NALI NIRMAN NANDU SHRIPAL KE GHAR SE MAIN ROAD TAK 15FC AND NREGA KASHI GP TINDNI | Ongoing | 20900 | 0 | 2025-03-21
JABALPUR / PANAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1733005047/RS/22012035132260 — RCC HUME PIPE NALI NIRMAN SURENDRA BHUMIYA KE GHAR SE BHAGWAN SINGH KE GHAR KI OR KASHI GP TINDNI | Ongoing | 6300 | 0 | 2025-03-21
JABALPUR / PANAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1733005047/RS/22012035132261 — RCC HUME PIPE NALI NIRMAN ANIL RAJPOOT KE GHAR SE DEVI SINGH KE GHAR TAK 15FC AND NREGA KASHI TINDNI | Ongoing | 10000 | 0 | 2025-03-21
JABALPUR / PANAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1733005047/RS/22012035136399 — CC NALI NIRMAN MAHESH PATEL KE GHAR SE SANTOSH KOL KE GHAR TAK NREGA AND 15TH FC TINDNI | Approved | 24700 | 0 | 2024-12-14
JABALPUR / PANAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1733005047/RS/22012035136611 — CC NALI NIRMAN KARYA MAHESH PATEL KE GHAR SE SANTOSH KOL KE GHAR TAK | Approved | 0 | 0 | 2025-01-26
JABALPUR / PANAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1733005047/RS/22012035136612 — CC NALI NIRMAN KARYA MAHESH PATEL KE GHAR SE SANTOSH KOL KE GHAR TAK | Approved | 25000 | 0 | 2025-01-26