## Work List
Exported on: 2026-10-01 22:53:19
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SOUHAD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR / JABALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1733006033/DP/22012034581014 — VRICHHAROPAN KARYA SHANTI DHAM SOHAD 2023-2024 | Ongoing | 806846.25 | 0 | 2023-07-28
JABALPUR / JABALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1733006033/DP/22012034581015 — VRICHHAROPAN KARYA TALAB KI BUND OR SITE GRAM NARRAI 2023-2024 | Ongoing | 427106.07 | 0 | 2023-07-24
JABALPUR / JABALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Line Plantation Forstry Trees-Individual / Wasteland Line Plantation of Forestry Trees for Individuals | Plantation | 1733006033/IF/22012034975772 — HITESHI KOOP NIRMAN KARYA MAGAN LAL NARRAI | Ongoing | 259046.52 | 0 | 2023-05-31
JABALPUR / JABALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1733006033/IF/22012035380599 — Dug well recharge Gora sahu gram narrai gp sohad | Approved | 25899.46 | 0 | 2025-04-15
JABALPUR / JABALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1733006033/IF/22012035380621 — Dug well recharge Rakkhi bai gram sohad | Ongoing | 25899.46 | 0 | 2025-04-30
JABALPUR / JABALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1733006033/IF/22012035380651 — Dug well recharge Kamlesh patel gram sohad | Ongoing | 25899.46 | 0 | 2025-04-30
JABALPUR / JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733006033/IF/22012035606588 — EK BAGIYA MAA KE NAME SWATI KESHARWANI / BASANT KESHARWANI | Ongoing | 171333.47 | 0 | 2025-12-09
JABALPUR / JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733006033/IF/22012035606606 — EK BAGIYA MAA KE NAME MALTI BAI /NOKHE SINGH | Approved | 171333.47 | 0 | 2025-08-01
JABALPUR / JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/1644134 — Construction of IAY House -IAY REG. NO. MP2457762 | Ongoing | 27000 | 0 | 2018-06-01
JABALPUR / JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/1698143 — Construction of IAY House -IAY REG. NO. MP2513353 | Ongoing | 27000 | 0 | 2018-07-04
JABALPUR / JABALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/4313624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3622305 | Approved | 27000 | 0 | 2022-06-30
JABALPUR / JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5134885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118139277 | Ongoing | 27000 | 0 | 2026-02-05
JABALPUR / JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5135154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100789485 | Physically Completed | 27000 | 0 | 2026-02-05 | 2026-09-13
JABALPUR / JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5135743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104922584 | Ongoing | 27000 | 0 | 2025-04-24
JABALPUR / JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5136233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118826103 | Ongoing | 27000 | 0 | 2026-02-05
JABALPUR / JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5138079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114889920 | Ongoing | 27000 | 0 | 2025-05-26
JABALPUR / JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5138081 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114890029 | Ongoing | 27000 | 0 | 2025-08-17
JABALPUR / JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5138774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118138923 | Physically Completed | 23490 | 0 | 2025-05-28 | 2026-07-14
JABALPUR / JABALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5139004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106083071 | Ongoing | 27000 | 0 | 2026-08-04
JABALPUR / JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5139079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106921797 | Physically Completed | 23490 | 0 | 2026-02-05 | 2026-08-02
JABALPUR / JABALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5139739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121989432 | Ongoing | 27000 | 4176 | 2026-07-29
JABALPUR / JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5141857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150585363 | Approved | 27000 | 0 | 2025-02-12
JABALPUR / JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5142232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146468419 | Approved | 27000 | 0 | 2025-02-14
JABALPUR / JABALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5142233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146468593 | Ongoing | 27000 | 0 | 2026-08-26
JABALPUR / JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5142236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146468817 | Ongoing | 27000 | 0 | 2025-04-24
JABALPUR / JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5142237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146468879 | Approved | 27000 | 0 | 2025-02-12
JABALPUR / JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5142278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106865657 | Ongoing | 27000 | 0 | 2025-05-26
JABALPUR / JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5143646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107079270 | Approved | 27000 | 0 | 2025-02-12
JABALPUR / JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5470914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113724168 | Approved | 27000 | 0 | 2025-02-12
JABALPUR / JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5702614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114889963 | Approved | 27000 | 0 | 2025-02-12
JABALPUR / JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5703073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116355195 | Ongoing | 27000 | 0 | 2026-02-05
JABALPUR / JABALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/584510 — Construction of IAY House -IAY REG. NO. MP1447088 | Ongoing | 27000 | 0 | 2017-02-07
JABALPUR / JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5884799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146468344 | Approved | 27000 | 0 | 2025-02-12
JABALPUR / JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006033/IF/IAY/5884860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146469001 | Approved | 27000 | 0 | 2025-02-14
JABALPUR / JABALPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733006033/RC/22012034844680 — cc road nirman karya mandir se nale ki aur | Ongoing | 41000 | 0 | 2025-06-23
JABALPUR / JABALPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733006033/RC/22012034849790 — cc road kailash kachhi ke ghar se shakun ke ghar ki aur | Approved | 72000 | 0 | 2025-04-14
JABALPUR / JABALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1733006033/WC/22012035181333 — DOUG POND NIRMAN KARYA SOHAD | New | 0 | 0 | 2024-01-24
JABALPUR / JABALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733006033/WC/22012035182367 — CPT WORK SOHAD | Ongoing | 241796.47 | 0 | 2024-03-10