## Work List
Exported on: 2026-09-08 14:40:27
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KUDOHARDULI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR / KUNDAM | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1733007026/DP/22012034589373 — वसुधा वंदन (अमृत वाटिका) खेल मैदान के पास ग्राम सातनझिर ग्रा.पं. कुड़ेहरदुली | Ongoing | 55847.4 | 0 | 2023-09-09
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1733007026/DP/22012034621075 — सामुदायिक वृक्षारोपण कार्य छिदन वाले में ग्राम सातनझिर | Approved | 0 | 0 | 2024-06-08
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1733007026/DP/22012034623167 — सामुदायिक वृक्षारोपण कार्य छिदन वाले में ग्राम सातनझिर | Ongoing | 453563.17 | 0 | 2024-07-11
JABALPUR / KUNDAM | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733007026/IF/22012034586962 — खेत में वृक्षारोपण - भारत सिंह/कालू | Ongoing | 115360 | 0 | 2020-08-27
JABALPUR / KUNDAM | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1733007026/IF/22012034592687 — खेत के मेढ पर वृक्षारोपण कार्य हितग्राही - गिरिजा बाई/सरूप सिंह ग्राम तौरी | Ongoing | 216874.14 | 0 | 2020-08-27
JABALPUR / KUNDAM | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1733007026/IF/22012034592690 — खेत के मेढ पर वृक्षारोपण कार्य हितग्राही - रूकमणी बाई/डुमारी सिंह ग्राम सातनझिर | Ongoing | 216874.14 | 0 | 2020-09-21
JABALPUR / KUNDAM | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1733007026/IF/22012034592696 — खेत के मेढ पर वृक्षारोपण कार्य हितग्राही - फेरन सिंह/धन सिंह, कृष्ण कुमार/लोटन सिंह ग्राम तौरी | Ongoing | 216874.14 | 0 | 2020-08-26
JABALPUR / KUNDAM | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733007026/IF/22012034605692 — निजी खेत पर वृक्षारोपण समनूसिंह /रतिया | Ongoing | 115360 | 0 | 2020-10-14
JABALPUR / KUNDAM | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733007026/IF/22012034605696 — निजी खेत पर वृक्षारोपण ठाकुरसिंह/गुलैया | Ongoing | 115360 | 0 | 2020-09-23
JABALPUR / KUNDAM | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733007026/IF/22012034605706 — निजी खेत पर वृक्षारोपण सोनसिंह /जयसिंह | Ongoing | 115360 | 0 | 2020-10-29
JABALPUR / KUNDAM | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733007026/IF/22012034605712 — निजी खेत पर वृक्षारोपण सावित्री बाई/अमरसिंहू | Ongoing | 115360 | 0 | 2020-09-21
JABALPUR / KUNDAM | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733007026/IF/22012034605717 — निजी खेत पर वृक्षारोपण नरेन्द्र /बुधगनेश | Ongoing | 115360 | 0 | 2020-09-21
JABALPUR / KUNDAM | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733007026/IF/22012034605721 — निजी खेत पर वृक्षारोपण रामकली /पंचू | Ongoing | 115360 | 0 | 2020-09-23
JABALPUR / KUNDAM | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733007026/IF/22012034711169 — CTR -Khet Talab Nirman Ramesh Singh/Hira Lal Gram Satanjhir | Ongoing | 337715.44 | 0 | 2021-05-01
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733007026/IF/22012035546054 — JGSA खेत तालाब निर्माण कार्य नेमनाथ मरावी/ सुख लाल ग्राम सातनझिर ग्राम पंचायत कुडेहरदुली | New | 0 | 0 | 2025-04-14
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733007026/IF/22012035546081 — JGSA खेत तालाब निर्माण कार्य समदायिक ग्राम तोरी ग्राम पंचायत कुडेहरदुली | New | 0 | 0 | 2025-04-14
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733007026/IF/22012035601982 — एक बगिया मां के नाम ओमती बाई/सुरेश सिंह ग्राम सातनझिर ग्राम पंचायत कुडेहरदुली | Ongoing | 134371.62 | 5689.04 | 2025-08-29
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733007026/IF/22012035601993 — एक बगिया मां के नाम सुषमा बाई/मुकेश सिंह ग्राम सातनझिर ग्राम पंचायत कुडेहरदुली | Ongoing | 134371.62 | 5117 | 2025-08-29
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733007026/IF/22012035605144 — एक बगिया माँ के नाम जग्गो बाई/ध्रुप लाल ग्राम सतानझिर ग्राम पंचायत कुड़ेहरदुली | Ongoing | 266674.03 | 5689.04 | 2025-09-06
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733007026/IF/22012035605185 — एक बगिया माँ के नाम भागवती बाई /बुद्धु सिंह ग्राम सतानझिर ग्राम पंचायत कुड़ेहरदुली | Ongoing | 266448.03 | 5689.04 | 2025-09-06
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733007026/IF/22012035605215 — एक बगिया माँ के नाम सुहद्रीबाई/रमेश सिंह ग्राम सतानझिर ग्राम पंचायत कुड़ेहरदुली | New | 0 | 0 | 2025-07-12
JABALPUR / KUNDAM | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/1403910 — Construction of IAY House -IAY REG. NO. MP2458143 | Approved | 27000 | 0 | 2018-03-06
JABALPUR / KUNDAM | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/3260864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4103961 | Ongoing | 27000 | 0 | 2024-04-06
JABALPUR / KUNDAM | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/3301423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4318200 | Approved | 27000 | 0 | 2021-10-27
JABALPUR / KUNDAM | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/3301512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4368730 | Approved | 27000 | 0 | 2021-10-27
JABALPUR / KUNDAM | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/3304073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5296795 | Approved | 27000 | 0 | 2021-10-27
JABALPUR / KUNDAM | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/3365370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5330971 | Approved | 27000 | 0 | 2021-11-16
JABALPUR / KUNDAM | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/3365999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5390194 | Approved | 27000 | 0 | 2021-11-16
JABALPUR / KUNDAM | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/3366025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5393095 | Approved | 27000 | 0 | 2021-11-16
JABALPUR / KUNDAM | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/3366544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5460044 | Approved | 27000 | 0 | 2021-11-16
JABALPUR / KUNDAM | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/3367830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5629577 | Approved | 27000 | 0 | 2021-11-16
JABALPUR / KUNDAM | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/3367945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5646763 | Approved | 27000 | 0 | 2021-11-16
JABALPUR / KUNDAM | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/3367959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5648189 | Ongoing | 27000 | 0 | 2022-04-01
JABALPUR / KUNDAM | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/3457469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5621039 | Approved | 27000 | 0 | 2021-12-03
JABALPUR / KUNDAM | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/4420274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151965875 | Ongoing | 27000 | 0 | 2024-02-05
JABALPUR / KUNDAM | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/4434206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151927998 | Ongoing | 27000 | 0 | 2024-02-05
JABALPUR / KUNDAM | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/4436823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151929722 | Ongoing | 27000 | 0 | 2024-02-05
JABALPUR / KUNDAM | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/4480983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152023890 | Ongoing | 27000 | 0 | 2024-05-11
JABALPUR / KUNDAM | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/4793786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145648427 | Ongoing | 27000 | 0 | 2025-01-15
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5156568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145691814 | Ongoing | 27000 | 0 | 2025-10-11
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5161447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145652330 | Ongoing | 27000 | 0 | 2025-07-14
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5165738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146277110 | Ongoing | 27000 | 0 | 2026-02-04
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5172862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145654266 | Ongoing | 27000 | 0 | 2025-08-29
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5179802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146276643 | Ongoing | 27000 | 0 | 2026-03-13
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5193128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146275186 | Ongoing | 27000 | 0 | 2026-03-13
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5193573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146274560 | Ongoing | 27000 | 0 | 2026-02-04
JABALPUR / KUNDAM | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5193582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145648014 | Approved | 27000 | 0 | 2025-03-23
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5200930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146275322 | Ongoing | 27000 | 0 | 2026-03-13
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5204768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145655654 | Ongoing | 27000 | 0 | 2025-08-23
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5219640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145654986 | Ongoing | 27000 | 0 | 2025-05-26
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5220194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147411750 | Ongoing | 27000 | 0 | 2026-03-13
JABALPUR / KUNDAM | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5220407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146647391 | Ongoing | 27000 | 0 | 2026-04-24
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5221727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145655127 | Ongoing | 27000 | 0 | 2025-05-15
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5221953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146274621 | Ongoing | 27000 | 0 | 2025-09-26
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5235455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145656794 | Ongoing | 27000 | 0 | 2025-10-11
JABALPUR / KUNDAM | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5241074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147410078 | Ongoing | 27000 | 0 | 2026-04-24
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5241243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146274491 | Ongoing | 27000 | 0 | 2025-09-26
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5246720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145424935 | Ongoing | 27000 | 0 | 2025-05-26
JABALPUR / KUNDAM | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5248503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119674804 | Ongoing | 27000 | 0 | 2026-07-14
JABALPUR / KUNDAM | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5249937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145662694 | Approved | 27000 | 0 | 2025-03-26
JABALPUR / KUNDAM | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5253388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146274317 | Approved | 27000 | 0 | 2025-03-28
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5256508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145664682 | Ongoing | 27000 | 0 | 2025-11-06
JABALPUR / KUNDAM | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5261329 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145655288 | Ongoing | 27000 | 0 | 2026-04-24
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5263749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147623968 | Ongoing | 27000 | 0 | 2026-03-13
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5270448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117528377 | Ongoing | 27000 | 0 | 2026-03-13
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5272424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146652968 | Ongoing | 27000 | 0 | 2025-10-10
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5275380 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145661417 | Ongoing | 27000 | 0 | 2025-10-11
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5280020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146277921 | Ongoing | 27000 | 0 | 2025-08-29
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5288043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145648052 | Ongoing | 27000 | 0 | 2025-05-15
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5288811 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145655605 | Ongoing | 27000 | 0 | 2025-10-11
JABALPUR / KUNDAM | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5301944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146636782 | Approved | 27000 | 0 | 2025-03-28
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5302382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146275248 | Ongoing | 27000 | 0 | 2025-05-15
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5302739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146656569 | Ongoing | 27000 | 0 | 2025-10-08
JABALPUR / KUNDAM | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5305835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145656539 | Ongoing | 27000 | 0 | 2026-08-24
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5309388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146273734 | Ongoing | 27000 | 0 | 2025-10-08
JABALPUR / KUNDAM | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5326708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145426750 | Ongoing | 27000 | 0 | 2026-04-24
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5329909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117795514 | Ongoing | 27000 | 0 | 2026-03-13
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5331524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146274390 | Ongoing | 27000 | 0 | 2025-10-08
JABALPUR / KUNDAM | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5337970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146274244 | Approved | 27000 | 0 | 2025-03-28
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5343690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145656604 | Ongoing | 27000 | 0 | 2025-11-06
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5344051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146658225 | Ongoing | 27000 | 0 | 2026-01-15
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5345827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146277282 | Ongoing | 27000 | 0 | 2025-10-08
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5352510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146275817 | Ongoing | 27000 | 0 | 2026-03-13
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5354256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146646458 | Ongoing | 27000 | 0 | 2025-11-06
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5355044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146273821 | Ongoing | 27000 | 0 | 2025-10-08
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5356000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147412780 | Ongoing | 27000 | 0 | 2025-11-25
JABALPUR / KUNDAM | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5403612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146655811 | Approved | 27000 | 0 | 2025-03-29
JABALPUR / KUNDAM | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5405422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146273618 | Approved | 27000 | 0 | 2025-03-29
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5570666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147412035 | Ongoing | 27000 | 0 | 2026-03-13
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5571869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146637896 | Ongoing | 27000 | 0 | 2025-12-20
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5571955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146654148 | Ongoing | 27000 | 0 | 2026-03-13
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5670806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147409147 | Ongoing | 27000 | 0 | 2025-10-10
JABALPUR / KUNDAM | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/5671067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147410626 | Approved | 27000 | 0 | 2025-03-23
JABALPUR / KUNDAM | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733007026/IF/IAY/696716 — Construction of IAY House -IAY REG. NO. MP1383566 | Ongoing | 27000 | 0 | 2017-10-18
JABALPUR / KUNDAM | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1733007026/RC/22012034646541 — पेबर ब्‍लाक निर्माण कार्य प्रा.शा. सातनझिर | Ongoing | 34000 | 0 | 2023-08-12
JABALPUR / KUNDAM | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1733007026/RC/22012034834947 — सुदूर सडक निर्माण कार्य मुख्‍यमार्ग से कुटी घाट तक ग्राम सातनझिर | Approved | 0 | 0 | 2024-10-02