## Work List
Exported on: 2026-10-09 17:45:58
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SEHADRA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR / KUNDAM | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1733007033/AV/22012034614056 — ग्राम पंचायत भवन निर्माण कार्य सहदरा ग्राम पंचायत सहदरा | Ongoing | 1000000 | 0 | 2022-02-23
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Check Dam for Individual | Construction of Check Dam/Stop Dam | 1733007033/IF/22012035269330 — बोल्डर का चेक डैम निर्माण सामुदायिक बधेनी नाला नारायण के खेत के पास ग्राम सहदरा | New | 0 | 0 | 2024-09-22
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1733007033/IF/22012035486388 — JGSA KHET TALAB NIRMAAN KARYA SANDEEP SINGH / SHAHMEN SINGH GRAM RANGIRI GRAM PANCHAYAT SAHDARA | Ongoing | 450885.64 | 0 | 2025-05-17
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1733007033/IF/22012035565613 — JGSA खेत तालाब निर्माण कार्य सुदीना सिंह पिता श्यामलाल ग्राम रनगिरी ग्राम पंचायत सहदरा | Approved | 0 | 0 | 2025-04-18
JABALPUR / KUNDAM | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/2254594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3256038 | Ongoing | 27000 | 0 | 2019-10-15
JABALPUR / KUNDAM | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/2485075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4150546 | Ongoing | 27000 | 0 | 2020-06-30
JABALPUR / KUNDAM | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/2512446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4504928 | Ongoing | 27000 | 0 | 2020-06-30
JABALPUR / KUNDAM | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/412633 — Construction of IAY House -IAY REG. NO. MP1290496 | Ongoing | 27000 | 0 | 2017-01-31
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/5149375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145159642 | Completed | 27000 | 0 | 2025-07-16 | 2026-09-07
JABALPUR / KUNDAM | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/5168549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145443864 | Ongoing | 27000 | 0 | 2026-05-01
JABALPUR / KUNDAM | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/5196043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147707128 | Approved | 27000 | 0 | 2025-02-19
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/5208276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145570094 | Completed | 27000 | 0 | 2025-05-29 | 2026-09-07
JABALPUR / KUNDAM | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/5223913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147707914 | Completed | 27000 | 0 | 2025-11-01 | 2026-09-07
JABALPUR / KUNDAM | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/5349889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147708103 | Ongoing | 27000 | 0 | 2026-10-06
JABALPUR / KUNDAM | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/5753289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143648577 | Completed | 27000 | 0 | 2026-05-01 | 2026-09-07
JABALPUR / KUNDAM | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/60669 — Construction of IAY House -IAY REG. NO. MP-33-007-033-002/23611533 | Approved | 27000 | 0 | 2015-12-14
JABALPUR / KUNDAM | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/60672 — Construction of IAY House -IAY REG. NO. MP-33-007-033-002/23644146 | Approved | 27000 | 0 | 2015-12-14
JABALPUR / KUNDAM | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/60676 — Construction of IAY House -IAY REG. NO. MP-33-007-033-002/23669469 | Approved | 27000 | 0 | 2015-12-14
JABALPUR / KUNDAM | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/60679 — Construction of IAY House -IAY REG. NO. MP-33-007-033-003/21671543 | Approved | 27000 | 0 | 2015-12-14
JABALPUR / KUNDAM | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/60681 — Construction of IAY House -IAY REG. NO. MP-33-007-033-003/22332579 | Approved | 27000 | 0 | 2015-12-14
JABALPUR / KUNDAM | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/6384474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145205650 | Approved | 27000 | 0 | 2024-09-11
JABALPUR / KUNDAM | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/68942 — Construction of IAY House -IAY REG. NO. MP-33-007-033-003/22971408 | Approved | 27000 | 0 | 2015-12-31
JABALPUR / KUNDAM | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/780064 — Construction of IAY House -IAY REG. NO. MP1461303 | Ongoing | 27000 | 0 | 2017-05-23
JABALPUR / KUNDAM | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733007033/IF/IAY/966991 — Construction of IAY House -IAY REG. NO. MP3472934 | Approved | 27000 | 0 | 2017-04-20
JABALPUR / KUNDAM | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1733007033/RC/VB/22012034854444 — सुदूर सड़क निर्माण कार्य हर्रा टोला से केरीटोला तक ग्राम सहदरा ग्राम पंचायत सहदरा | Approved | 0 | 0 | 2026-04-14
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1733007033/WC/22012035211291 — LOOJ BOLDER CHECK DEM NIRMAAN GAJIYA WALW NALA GRAM SALHEPANI | Approved | 0 | 0 | 2024-06-08
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1733007033/WC/22012035211300 — LOOJ BOLDER CHECK DEM NIRMAAN BANKI WALE NALA GRAM SALHEPANI | Approved | 0 | 0 | 2024-06-08
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1733007033/WC/22012035211304 — LOOJ BOLDER CHECK DEM PAREVA WALE NALA SADDU SINGH KE KHET KE PASS GRAM SALHEPANI | Approved | 0 | 0 | 2024-06-08
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1733007033/WC/22012035215674 — LOOJ BOLDER CHECK DEM NIRMAAN KUNHA NALA GRAM RANGIRI | Approved | 0 | 0 | 2024-06-16
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1733007033/WC/22012035215687 — LOOJ BOLDER CHECK DEM NIRMAAN MUNDI WALE NALA GRAM RANGIRI | Approved | 0 | 0 | 2024-06-16
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1733007033/WC/22012035215691 — LOOJ BOLDER CHECK DEM NIRMAAN OSRI WALE NALA GRAM RANGIRI | Approved | 0 | 0 | 2024-06-16
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1733007033/WC/22012035227116 — बोल्डर का चेक डैम निर्माण सामुदायिक बधेनी नाला नारायण के खेत के पास ग्राम सहदरा | Approved | 0 | 0 | 2024-09-22
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1733007033/WC/22012035240207 — CTR CONTOUR TRENCH NIRMAAN - PANGHATA PAHAD GRAM SALHEPANI | New | 0 | 0 | 2024-10-02
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1733007033/WC/22012035240213 — LOOJ BOLDER CHECK DEM NIRMAAN KARYA BAANKI WALE NALA GRAM SALHEPANI | Approved | 0 | 0 | 2024-10-02
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1733007033/WC/22012035246623 — CONTOUR TRENCH NIRMAAN - KAIEMA WALE PAHAD GRAM SEHADRA | Approved | 0 | 0 | 2025-01-26
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1733007033/WC/22012035246634 — CONTOUR TRENCH NIRMAAN - KUNHA PAHAD KUVAR SINGH KE KHET KE PASS GRAM RANGIRI | Approved | 0 | 0 | 2025-01-26
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1733007033/WC/22012035247199 — CONTOUR TRENCH NIRMAAN - SURYARI PAHAD GRAM SEHADRA | New | 0 | 0 | 2025-01-26
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1733007033/WC/22012035257286 — CONTOUR TRENCH NIRMAAN - GAJIYA WALE PAHAD GRAM SEHADRA | Approved | 0 | 0 | 2025-01-26
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1733007033/WC/22012035257289 — CTR CONTOUR TRENCH NIRMAAN - TALAB WALE PAHAD GRAM SEHADRA | New | 0 | 0 | 2025-01-26
JABALPUR / KUNDAM | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1733007033/WC/22012035257290 — CONTOUR TRENCH NIRMAAN - TALAB WALE PAHAD GRAM SEHADRA | Approved | 0 | 0 | 2025-01-26
JABALPUR / KUNDAM | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1733007033/WC/22012035328432 — BOLDER CHECK NIRMAAN KARYA MARGHATAI NALA GRAM SAHDARA GRAM PANCHAYAT SAHDARA | Approved | 0 | 0 | 2026-01-26
JABALPUR / KUNDAM | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1733007033/WC/22012035328433 — BOLDER CHECK NIRMAAN KARYA TALAB WALE NALA GRAM SAHDARA GRAM PANCHAYAT SAHDARA | Approved | 0 | 0 | 2026-01-26
JABALPUR / KUNDAM | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1733007033/WC/22012035328434 — BOLDER CHECK NIRMAAN KARYA OSRI GHUGHRA NALA GRAM RANGIRI GRAM PANCHAYAT SAHDARA | Approved | 287062.42 | 0 | 2026-01-26
JABALPUR / KUNDAM | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1733007033/WC/22012035328436 — BOLDER CHECK NIRMAAN KARYA KUNHA NALA GRAM RANGIRI GRAM PANCHAYAT SAHDARA | Ongoing | 299765.54 | 3758.07 | 2026-03-10
JABALPUR / KUNDAM | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1733007033/WC/VB/22012035329794 — CANTURE TRENCH NIRMAN PIPAL PAHAD GRAM RANGIRI G P SAHDRA | Approved | 0 | 0 | 2026-06-12
JABALPUR / KUNDAM | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1733007033/WC/VB/22012035329796 — CANTOURE TRENCH NIRMAN JHIRIYA PAHAD GRAM RANGIRI G P SAHDRA | Approved | 0 | 0 | 2026-06-12
JABALPUR / KUNDAM | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1733007033/WC/VB/22012035330243 — CONTOUR TRENCH NIRMAAN KARYA PIPAL WALE PAHAD GRAM RANGIRI | New | 0 | 0 | 2026-06-05
JABALPUR / KUNDAM | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1733007033/WC/VB/22012035330246 — CONTOUR TRENCH NIRMAAN KARYA PIPAL WALE PAHAD GRAM RANGIRI | Approved | 0 | 0 | 2026-06-05
JABALPUR / KUNDAM | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1733007033/WC/VB/22012035330250 — बोल्डर चेक निर्माण कार्य मरघटाई वाले नाला में ग्राम सहदरा | Approved | 0 | 0 | 2026-06-05
JABALPUR / KUNDAM | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1733007033/WC/VB/22012035330285 — CONTOUR TRENCH NIRMAAN KARYA JHIRIYA WALE PAHAD GRAM RANGIRI | Approved | 0 | 0 | 2026-06-05
JABALPUR / KUNDAM | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1733007033/WC/VB/22012035330287 — CONTOUR TRENCH NIRMAAN KARYA PIPAL WALE PAHAD GRAM SAHDARA | Approved | 0 | 0 | 2026-06-05
JABALPUR / KUNDAM | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1733007033/WC/VB/22012035330290 — बोल्डर चेक निर्माण कार्य गिलची नाला में ग्राम सहदरा | Approved | 0 | 0 | 2026-06-05
JABALPUR / KUNDAM | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1733007033/WC/VB/22012035330295 — बोल्डर चेक निर्माण कार्य खिलहा पीपल नाला में ग्राम सहदरा | Approved | 0 | 0 | 2026-06-05