## Work List
Exported on: 2026-10-06 16:00:14
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: GORTALA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARSINGHPUR / GOTEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1734001060/IF/22012035308698 — खेत तालाब निर्माण कार्य गोविन्‍द आशीष फूलसिंह गोंड गौरतला | Approved | 422356.09 | 0 | 2025-03-01
NARSINGHPUR / GOTEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734001060/IF/IAY/4666087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151149613 | Ongoing | 27000 | 0 | 2024-11-12
NARSINGHPUR / GOTEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734001060/IF/IAY/4666127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151170804 | Ongoing | 27000 | 0 | 2024-11-06
NARSINGHPUR / GOTEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734001060/IF/IAY/5388437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125480710 | Completed | 23490 | 3300 | 2025-07-09 | 2026-09-22
NARSINGHPUR / GOTEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734001060/IF/IAY/5405339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150139582 | Ongoing | 27000 | 0 | 2025-07-09
NARSINGHPUR / GOTEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734001060/IF/IAY/5406932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150937781 | Ongoing | 27000 | 5400 | 2025-07-16
NARSINGHPUR / GOTEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734001060/IF/IAY/5757865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150617808 | Ongoing | 27000 | 900 | 2025-09-03
NARSINGHPUR / GOTEGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Dev of Silvipasture Grassslands for Community / Raising of Fodder Cultivation for Community | Grass Land Development | 1734001060/LD/22012034529700 — गौशाला परियोजना अंतर्गत चारागाह विकास कार्य गौरतला | Ongoing | 1015107.09 | 0 | 2021-03-24
NARSINGHPUR / GOTEGAON | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1734001060/RC/22012034838416 — सीसीरोड निर्माण कार्य कन्‍वर्जेंस 15Vitt Brijlal to Girdhari Home 45Mt मजनी गौरतला | Approved | 21000 | 0 | 2025-03-03
NARSINGHPUR / GOTEGAON | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1734001060/RC/22012034851505 — सीसीरोड निर्माण कार्य कन्‍वर्जेंस 5Vitt Main Road to Shantidham 100Mt मजनी गौरतला | Completed | 51200 | 0 | 2026-02-12 | 2026-10-02
NARSINGHPUR / GOTEGAON | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1734001060/RC/22012034853729 — सीसीरोड निर्माण कार्य कन्‍वर्जेंस 15Vitt Khermata Prishar 95Mt गौरतला | Ongoing | 36900 | 10800 | 2026-06-10
NARSINGHPUR / GOTEGAON | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1734001060/RS/22012035136143 — पीवीसी नाली निर्माण कार्य कन्‍वर्जेंस 15Vitt Sheru to Ataru Home 100Mt मजनी गौरतला | Approved | 27000 | 0 | 2025-01-15
NARSINGHPUR / GOTEGAON | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1734001060/RS/22012035136732 — सीसीनाली निर्माण कार्य कन्‍वर्जेंस 15Vitt Ramsevak to Main Road 220Mt मजनी गौरतला | Approved | 56000 | 0 | 2025-03-07
NARSINGHPUR / GOTEGAON | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1734001060/RS/22012035136734 — सीसीनाली निर्माण कार्य कन्‍वर्जेंस 15Vitt Sunil to Mandir 50Mt मजनी गौरतला | Approved | 15000 | 0 | 2025-03-07
NARSINGHPUR / GOTEGAON | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost Structure for Community | Construction of NADEP/Vermi Compost Pit | 1734001060/RS/22012035136772 — वर्मी कम्‍पोस्‍ट पिट संरचना निर्माण कार्य गौशाला के पास गौरतला | Approved | 99968.76 | 0 | 2025-03-01
NARSINGHPUR / GOTEGAON | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1734001060/RS/22012035139300 — पीवीसी पाईप नाली निर्माण कार्य कन्‍वर्जेंस 15Vitt Raghunat to Shankarji Ki Madiya 107Mt मजनी गौरतला | Approved | 27000 | 0 | 2026-01-21
NARSINGHPUR / GOTEGAON | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1734001060/RS/22012035139301 — पीवीसी पाईप नाली निर्माण कार्य कन्‍वर्जेंस 15Vitt Mahesh Home to PS 147Mt गौरतला | Completed | 36000 | 0 | 2026-04-29 | 2026-10-02
NARSINGHPUR / GOTEGAON | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1734001060/RS/VB/22012035139762 — सोकपिट निर्माण कार्य आंगनवाडी भवन वाले हेंडपंप क पास मजनी गौरतला | Ongoing | 29509.74 | 9900 | 2026-08-24
NARSINGHPUR / GOTEGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1734001060/WC/22012034559275 — तलाब सौर्न्‍दकरण कार्य ग्राम रातामाटीीग्राम पंचसत गौरतला | Ongoing | 576537.04 | 0 | 2021-03-24
NARSINGHPUR / GOTEGAON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1734001060/WC/22012035194484 — वोल्डर चेक डेम निर्माण कार्य राशिद के खेत के पास रातामाटी | Ongoing | 81100.15 | 0 | 2024-06-11
NARSINGHPUR / GOTEGAON | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734001060/WC/VB/22012035331734 — रूफ वाटर हार्वेस्टिंग निर्माण कार्य पंचायत भवन गौरतला | Ongoing | 29509.74 | 3300 | 2026-09-01