## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
MANDLA / BIJADANDI / KHANORA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1735001042/AV/22012034644398 — puliya nirman khanora gowari tola se tinsai part 1 | Completed | 633648.73 | 616998.27 | 2023-10-09 - 2024-06-27
MANDLA / BIJADANDI / KHANORA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1735001042/AV/22012034644399 — puliya nirman tinsi gwari tola tinsi part 2 | Completed | 1393067 | 1377420.48 | 2023-12-21 - 2024-04-15
MANDLA / BIJADANDI / KHANORA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1735001042/AV/22012034646522 — Puliya Nirman Karya Hemraj road Par khanoura | Closed | 0 | 0 | 2023-08-25 -
MANDLA / BIJADANDI / KHANORA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1735001042/AV/22012034653105 — puliya nirman khakhrol nala khanora | Completed | 1000653.5 | 976245.4 | 2024-03-16 - 2024-10-22
MANDLA / BIJADANDI / KHANORA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1735001042/AV/22012034653816 — puliya nirmad tinsai sikari tola | Completed | 1069012.38 | 1028136.16 | 2024-06-26 - 2026-02-18
MANDLA / BIJADANDI / KHANORA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1735001042/AV/22012034653817 — puliya nirmad tinsai sikari tola | New | 0 | 0 | 2024-01-27 -
MANDLA / BIJADANDI / KHANORA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1735001042/AV/22012034653818 — grewal rode khanora se Bhatadungariya | New | 0 | 0 | 2024-01-27 -
MANDLA / BIJADANDI / KHANORA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1735001042/AV/22012034654979 — Puliya nirman ratan ke Ghar Ke pas tinsi | Deleted | 0 | 0 | 2024-01-26 -
MANDLA / BIJADANDI / KHANORA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1735001042/AV/22012034654980 — Puliya nirman m.s. school ke same tinsi | Deleted | 0 | 0 | 2024-01-26 -
MANDLA / BIJADANDI / KHANORA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1735001042/AV/22012034655163 — puliya nirman khakhrol nala part 02 khanora | Closed | 0 | 0 | 2023-12-13 -
MANDLA / BIJADANDI / KHANORA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1735001042/AV/22012034655164 — puliya nirman khakhrol nala part 02 khanora | Closed | 0 | 0 | 2023-12-13 -
MANDLA / BIJADANDI / KHANORA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1735001042/AV/22012034655246 — Puliya Nirmad Khakhrol nala part 02 Hemraj tola | Completed | 1253816.74 | 1220223.46 | 2024-03-16 - 2024-10-22
MANDLA / BIJADANDI / KHANORA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1735001042/AV/22012034656009 — puliya nirman karya ratan ke ghar ke pass | Closed | 0 | 0 | 2023-04-15 -
MANDLA / BIJADANDI / KHANORA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1735001042/AV/22012034656010 — puliya nirman karya ms school ke pass | Closed | 0 | 0 | 2023-04-15 -
MANDLA / BIJADANDI / KHANORA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1735001042/AV/22012034656410 — Puliya nirmad shikari tola | Closed | 0 | 0 | 2024-01-26 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1735001042/DP/22012034598899 — Vasundh Bandhan Vracharopan Karya Talab khanoura | Completed | 55847.4 | 24849.96 | 2024-02-29 - 2026-01-25
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1735001042/DP/22012034617210 — sadak kinare vrkcharopad | New | 0 | 0 | 2024-04-04 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1735001042/DP/22012034617237 — vraksharopan karya tinsai say khanora | Ongoing | 453563.17 | 124272.59 | 2024-07-03 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043373 — PADAT BHUMI SUDHAR RAMLAL/BALMA | Completed | 168542.96 | 141282 | 2022-12-26 - 2024-01-31
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043378 — PADAT BHUMI SUDHAR RAMLAL/DYAL | Completed | 96330.91 | 76860 | 2023-02-04 - 2024-06-09
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043382 — PADAT BHUMI SUDHAR CHAMROO/PACHLOO | Completed | 120172.1 | 101892 | 2023-01-05 - 2023-07-06
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043385 — PADAT BHUMI SUDHAR MANGAL/CHAMRA | Completed | 210017.3 | 172893 | 2022-12-28 - 2023-07-06
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043388 — PADAT BUMI SUDHAR AKAL/DADULAL | Completed | 229778.6 | 186925 | 2022-12-28 - 2023-07-06
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043394 — PADAT BHUMI SUDHAR JANKA BAI/BHANSINGH | Closed | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043399 — PADAT BHUMI SUDHAR GOVIND/DHANU | Closed | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043403 — PADAT BHUMI SUDHAR HARESINGH/HARDYAL | Closed | 0 | 0 | 2022-08-15 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043415 — PADAT BHUMI SUDHAR KALESINGH/RAMSINGH | Closed | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043420 — PADAT BHUMI SUDHAR MADAN/SUKAL | Closed | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043441 — PADAT BHUMI SUDHAR BABULAL/PYARELAL | Closed | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043488 — PADAT BHUMI SUDHAR CHOTELAL/RAMA | Closed | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043492 — PADAT BHUMI SUDHAR BHANWATI/KOMAL | Closed | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043493 — PADAT BHUMI BHAVANI/SUMRAT | Closed | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043495 — PADAT BHUMI SUDHAR POHAP/MIHILAL | Completed | 50514.26 | 40487 | 2023-01-14 - 2023-07-06
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035043500 — PADAT BHUMI SUDHAR MUNNA/TITROO | Closed | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1735001042/IF/22012035052962 — KAPIL DARA KOOP AMAR SINGH/AGHNOO | Deleted | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1735001042/IF/22012035052963 — KAPIL DARA KOOP AMAR SINGH/AGHNOO | Deleted | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1735001042/IF/22012035052964 — KAPIL DARA KOOP AMAR SINGH/AGHNOO | Closed | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1735001042/IF/22012035052965 — KAPIL DARA KOOP REVTIBAI/PRABHU | Closed | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1735001042/IF/22012035052967 — KAPIL DARA KOOP SAROJBAI/DHARAM | Closed | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1735001042/IF/22012035053004 — PADAT BHUMI SUDHAR RAVISHANKAR | Completed | 76954.6 | 57954 | 2023-01-20 - 2023-07-06
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1735001042/IF/22012035053008 — PADAT BHUMI SUDHAR EMRAT/MIHILAL | Completed | 76954.6 | 63717 | 2023-01-14 - 2023-07-06
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1735001042/IF/22012035053009 — PADAT BHUMI SUDHAR EMRAT/MIHILAL | Deleted | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1735001042/IF/22012035053012 — PADAT BHUMI SUDHAR SUKAL/MUNNALAL | Closed | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1735001042/IF/22012035067639 — PASHU SED SUNDAR/SAHAN SINGH | Closed | 0 | 0 | 2023-01-28 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1735001042/IF/22012035067640 — PASHU SHED PESHI LAL/JUGAL | Closed | 0 | 0 | 2023-01-28 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035067790 — Pashu sed Chamri Bai/Giran singh KHANOURA | Deleted | 0 | 0 | 2023-01-28 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035067791 — Pashu sed Chamri Bai/Giran singh KHANOURA | Closed | 0 | 0 | 2023-01-28 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035098900 — Padat bhumi Sudhar chandrawati/vishram | Completed | 84839.57 | 62921 | 2024-03-15 - 2024-06-27
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1735001042/IF/22012035098904 — Padat bhumi Sudhar kuvar/laljoo | Completed | 93901.42 | 73277.1 | 2024-03-16 - 2024-06-08
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1735001042/IF/22012035098911 — Padat bhumi Sudhar gangaram/jugal | Completed | 214367.95 | 164436 | 2023-10-06 - 2024-01-31
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1735001042/IF/22012035098915 — Padat bhumi Sudhar sundar/sahansingh | Completed | 81919.73 | 60280 | 2023-06-19 - 2024-01-02
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1735001042/IF/22012035098922 — Padat bhumi Sudhar sunita/maniram | Closed | 0 | 0 | 2023-05-12 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099095 — BHUMI SAAMTALIKARAN AANANDI/SAHDEV | Completed | 51871.93 | 40900 | 2024-02-29 - 2024-05-29
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099106 — BHUMI SAAMTALIKARAN DHANIRAM/JETU | Closed | 0 | 0 | 2023-04-16 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099111 — BHUMI SAAMTALIKARAN MANOJ/AANTAR | Closed | 0 | 0 | 2023-04-16 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099113 — BHUMI SAAMTALIKARAN MANOJ/AANTAR | Closed | 0 | 0 | 2023-04-16 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099116 — BHUMI SAAMTALIKARAN MANOJ/AANTAR | Completed | 97853.28 | 76299 | 2023-10-02 - 2024-02-24
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099121 — BHUMI SAAMTALIKARAN GULAB/VISHNOO | Closed | 0 | 0 | 2023-04-16 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099124 — BHUMI SAAMTALIKARAN SUKAL/TEEKARAM | Completed | 172494.62 | 132452 | 2023-06-22 - 2024-03-31
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099129 — BHUMI SAAMTALIKARAN BABULAL | Completed | 161648.5 | 121537 | 2023-07-03 - 2024-02-22
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099131 — BHUMI SAAMTALIKARAN TILOK/SURAJ | Completed | 204575.28 | 116370 | 2023-06-22 - 2024-02-13
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099138 — BHUMI SAAMTALIKARAN MAHESH/VISHNOO | Closed | 0 | 0 | 2023-04-16 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099143 — PADAT BHUMI SUDHAR SHANKAR/RAMA | Completed | 220386.79 | 165335.4 | 2023-08-06 - 2024-02-24
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099146 — PADAT BHUMI SUDHAR HEMSINGH/RAMLAL | Completed | 92643.81 | 72362 | 2023-06-19 - 2024-01-07
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099151 — PADAT BHUMI SUDHAR DHANIRAM/BRAJ LAL | Completed | 78331.43 | 62672.22 | 2024-06-27 - 2025-02-12
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099152 — PADAT BHUMI SUDHAR DHANIRAM/BRAJ LAL | Closed | 0 | 0 | 2023-04-16 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099156 — PADAT BHUMI SUDHAR JANKI BAI/PUNNU | Closed | 0 | 0 | 2023-04-16 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099160 — PADAT BHUMI SUDHAR AAMARSINGH/AGHNU | Completed | 119331.93 | 92741 | 2023-09-09 - 2024-06-08
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035099165 — PADAT BHUMI SUDHAR MUNNALAL/TITRU | Completed | 60563.13 | 46746 | 2023-12-21 - 2024-06-08
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035110013 — PADAT BHUMI SUDHAR AKALSINGH/GIRANSINGH | Completed | 193363.06 | 149377 | 2023-06-19 - 2024-01-31
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035110019 — PADAT BHUMI SUDHAR GOVIND/DHANU | Completed | 93116.18 | 72200 | 2023-06-19 - 2024-01-02
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035126940 — Padat Bhumi sudhar Chetram/Baldev | Closed | 0 | 0 | 2023-05-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035126946 — Padat bhumi sudhar Loksingh/Chamroo | Completed | 189032.51 | 140752 | 2024-03-16 - 2024-06-08
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035132134 — Padat bhumi sudhar Dasrath/devsingh | Deleted | 91244.07 | 0 | 2023-05-24 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1735001042/IF/22012035149923 — Pasu shed kashiram/komal | Closed | 0 | 0 | 2023-08-25 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035149926 — Pashu shed Manoj/Amar singh | Closed | 0 | 0 | 2023-08-25 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035158174 — Padat Bhumi sudhar Mansingh/Chamm | Completed | 111866.84 | 87390 | 2024-06-13 - 2024-07-26
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035158176 — Padat Bhumi sudhar Mangalsingh/manohar | Completed | 87090.51 | 70083 | 2023-12-21 - 2024-02-21
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035158179 — Padat Bhumi sudhar Sonkali/kaluram | Completed | 182649.49 | 148856 | 2024-01-06 - 2024-03-04
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035158182 — Padat Bhumi sudhar Dasrath/Mangal | Closed | 0 | 0 | 2023-08-25 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035158183 — Padat Bhumi sudhar Punulal/Sumera | Closed | 0 | 0 | 2023-09-09 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035158188 — Padat Bhumi sudhar Pritam/Dhanoo | Completed | 55122.37 | 42658 | 2023-12-21 - 2024-02-24
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035158194 — Padat Bhumi sudhar Hemsingh/Sahjoo | Completed | 120141.43 | 96359 | 2023-10-09 - 2024-01-31
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1735001042/IF/22012035158200 — Padat Bhumi sudhar Maltibai/Dinesh | Closed | 0 | 0 | 2023-09-09 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035158208 — Padat Bhumi sudhar Jhankabai/Bhansingh | Completed | 101749.55 | 75860.1 | 2024-03-16 - 2024-06-09
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035158224 — Padat Bhumi sudhar Pesilal/Jugal | Completed | 142022.26 | 114739 | 2023-10-09 - 2024-02-24
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035162090 — Padat Bhumi sudhar Roshan/kandhi | Completed | 40176.98 | 31817.5 | 2024-02-29 - 2024-03-18
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035162121 — Padat Bhumi sudhar Jankibai/Ramsahay | Completed | 75080.29 | 60572 | 2023-10-09 - 2024-01-05
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035162129 — Padat Bhumi sudhar Pyarelal/mangal | Completed | 105934.26 | 85128.76 | 2023-10-09 - 2024-12-06
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035162135 — Padat Bhumi sudhar Jhadu/Hiralal | Completed | 90744.61 | 72190.1 | 2024-03-16 - 2024-05-23
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035162141 — Padat Bhumi sudhar Hansram/buddsen | Completed | 24711.7 | 18765 | 2024-04-20 - 2024-05-23
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035162151 — Padat Bhumi sudhar Sukhmaniya/Chotelal | Completed | 124337.41 | 100851.1 | 2024-03-16 - 2024-07-26
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1735001042/IF/22012035163693 — Padat bhumi sudhar Dasrath/Devsingh | Completed | 158481 | 123136.72 | 2024-06-12 - 2025-02-12
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035210196 — harisingh /gorelal bhumi sudhar | New | 0 | 0 | 2024-01-27 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035212658 — bolder medh bandhan hari singh /herdayal | New | 0 | 0 | 2024-01-26 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035221517 — Padat bhumi sudhar Biniyabai/Hemsingh | New | 0 | 0 | 2024-01-27 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035221519 — Padat bhumi sudhar Biniyabai/Hemsingh | New | 0 | 0 | 2024-01-27 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035221522 — Padat bhumi sudhar Biniyabai/Hemsingh | New | 0 | 0 | 2024-01-27 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035221526 — Padat bhumi sudhar Kaliram/Babulal | New | 0 | 0 | 2024-01-27 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035221545 — padat bhumi sudhar Biniyabai/hemsingh | New | 0 | 0 | 2024-01-27 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035221570 — padat bhumi sudhar Kopsingh/sambhu | New | 0 | 0 | 2024-01-27 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035221587 — padat bhumi sudhar Kuvar/Babulal | New | 0 | 0 | 2024-01-27 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035221589 — padat bhumi sudhar Kuvar/Babulal | New | 0 | 0 | 2024-01-27 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035221592 — padat bhumi sudhar Kuvar/Babulal | New | 0 | 0 | 2024-01-27 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035221594 — padat bhumi sudhar Kuvar/Babulal | New | 0 | 0 | 2024-01-27 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035230930 — khet talab ramdyal/syamlal | New | 0 | 0 | 2024-06-06 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035231253 — padat bhumi | New | 0 | 0 | 2024-04-01 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035232140 — khet talab ramdyal/shyamlal | Approved | 0 | 0 | 2024-06-06 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035232157 — padat bhumi sudhar Sonsingh/Sahjoo | Completed | 99683.55 | 80604.1 | 2024-06-19 - 2024-07-27
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035232171 — padat bhumi sudhar preetam/dhanu | Completed | 41031.13 | 31443.28 | 2024-06-19 - 2024-07-27
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035232184 — padat bhumi sudhar Rajkumar/Laljoo | Completed | 165252.75 | 129127.12 | 2024-06-20 - 2024-07-27
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035235795 — Padat bhumi sudhar kamalkishor/sahdevsingh | Approved | 0 | 0 | 2024-06-14 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035235802 — padat bhumi sudhar kamalkisor/sehdev | New | 0 | 0 | 2024-06-14 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035235808 — padat bhumi sudhar kamalkisor/sehdev | Completed | 175723.23 | 136947.25 | 2024-12-12 - 2025-04-22
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035235817 — Padat bhumi sudhar Biniyabai/Hemsingh | Completed | 44440.57 | 35202.24 | 2024-06-27 - 2024-07-27
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1735001042/IF/22012035235940 — vraksharopan Tulsiram/chamru | Ongoing | 145050.83 | 65621.26 | 2024-07-04 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735001042/IF/22012035251113 — Pasused nirmad kirpal/suraj | Completed | 114547.9 | 96510.02 | 2025-01-14 - 2026-02-17
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035251118 — nadeb nirmad hitgrahi tularam/chamru dhansingh/chamra mangal/chamra shiriram/Amrsingh Hemsingh/sahjo | Approved | 0 | 0 | 2024-06-14 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035264512 — khet talab chandarsingh/balaram | Completed | 298266.3 | 241271.93 | 2024-10-23 - 2025-04-20
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035267132 — khet talab santoshkumar/mangal | New | 0 | 0 | 2024-10-05 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035267133 — khet talab santoshkumar/mangal | Completed | 296819.64 | 224689.75 | 2024-11-06 - 2025-04-10
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035272490 — Boldar medbadhan Indrwati/Rameshwar | Completed | 186503.95 | 147835.44 | 2024-12-12 - 2025-02-20
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035272497 — boldar med badhan Dumarilal/Dasar | Completed | 63298.4 | 48928.14 | 2024-12-19 - 2025-06-19
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035273809 — boldar med badhan KUWAR/BABULAL | Completed | 199776.18 | 160561.53 | 2025-03-06 - 2025-12-03
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035278689 — boldar med badhan Sunita/Maniram | New | 0 | 0 | 2024-11-18 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035278690 — boldar med badhan Ramesh/Tirth | Completed | 115588.29 | 79251.43 | 2024-12-27 - 2025-06-19
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035278691 — boldar med badhan Devanti/Aghnu | Completed | 162674.22 | 128027.88 | 2025-01-04 - 2025-04-10
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035278692 — boldar med badhan Sundhar/sahan | Completed | 126593.25 | 98949.61 | 2025-02-13 - 2025-06-25
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035278693 — boldar med badhan tularam/chamru | Completed | 87430.56 | 62810.63 | 2025-01-23 - 2025-03-05
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035278696 — boldar med badhan Sunita/Maniram | Completed | 63298.4 | 49233.54 | 2025-02-13 - 2025-11-05
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035284985 — boldar med badhan Sewaram/Dasar | Completed | 87430.56 | 70614.26 | 2025-02-22 - 2025-12-18
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035284987 — boldar med badhan Chattaesingh/Bhaiyaji | Completed | 81924.17 | 59915.7 | 2025-02-22 - 2025-06-25
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035295799 — Boldar Med Badhan Girani/Jethu | Completed | 40561.05 | 28908.44 | 2025-04-11 - 2025-05-25
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035295803 — Boldar med suraj/Chital | Approved | 0 | 0 | 2024-11-18 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035301471 — boldar med badhan Indharsingh/dharamsingh | Completed | 197432.87 | 161049.35 | 2025-03-06 - 2026-01-07
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035301476 — boldar med badhan Kajalsimgh/ | New | 0 | 0 | 2024-11-18 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035301477 — boldar med badhan Kajalsimgh/ | Completed | 131056.65 | 94077.75 | 2025-02-27 - 2025-12-03
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1735001042/IF/22012035311082 — Boldar med badhane suraj/Cheetal | Approved | 0 | 0 | 2025-01-26 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035339804 — boldar med medhan chetram/baldev | Completed | 125826.41 | 98215.12 | 2025-06-05 - 2025-12-03
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035339852 — boldar med medhan sonkali/kaluram | Approved | 0 | 0 | 2025-04-04 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035339893 — boldar med medhan Roopsingh/Amarsingh | Completed | 40597.78 | 28746 | 2025-12-26 - 2026-02-17
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035339944 — boldar med medhan Ramkali/Munnalal | Completed | 89470.02 | 66705.65 | 2025-06-12 - 2025-10-22
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035375582 — Khettalab nirmad jankabai/Bhansingh | Approved | 0 | 0 | 2025-04-15 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1735001042/IF/22012035423151 — JGSA Recharge pit Hitgrahi Amarsingh/Aghnu | Approved | 0 | 0 | 2025-04-18 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1735001042/IF/22012035423876 — JGSA Recharge pit Hitgrahi Jhadu/Heera | New | 0 | 0 | 2025-04-18 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1735001042/IF/22012035423935 — JGSA Recharge pit Hitgrahi Amarsingh/Aghnu | Completed | 25899.46 | 21365.13 | 2025-05-10 - 2026-06-02
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1735001042/IF/22012035423960 — JGSA Recharge pit Hitgrahi Jhadu/Heera | Completed | 25899.46 | 22579.01 | 2025-05-10 - 2026-06-02
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035463279 — Khet talab Sundar/sahan | Approved | 0 | 0 | 2025-04-15 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035463608 — Khettalab nirmad Sundar/sahen | Completed | 329563.83 | 199599.52 | 2025-05-06 - 2026-01-22
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035463637 — Khettalab nirmad jankabai/Bhansingh | Completed | 329563.83 | 259850.97 | 2025-05-06 - 2026-01-22
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035503207 — PHeriphriwel Nirmad Sonkali/Kaluram | Completed | 145174.85 | 104918.04 | 2025-05-22 - 2025-12-18
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1735001042/IF/22012035503258 — PHeriphriwel Nirmad Rupsingh/Amarsingh | Approved | 0 | 0 | 2025-04-15 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035503311 — PHeriphriwel Nirmad Ramkali/Munnalal | Approved | 0 | 0 | 2025-04-18 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035503346 — PHeriphriwel Nirmad Chetram/Baldev | Approved | 0 | 0 | 2025-04-18 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035503384 — PHeriphriwel Nirmad DhanRaj/sahdev | Completed | 106521.58 | 82832.44 | 2025-09-25 - 2026-01-22
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035517596 — Khettalab nirmad Radhelal/Suraj | Completed | 329563.83 | 183170.7 | 2025-05-20 - 2026-04-09
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1735001042/IF/22012035619977 — Ek bagiya maa ke naam birajo workade / dhaniram | New | 0 | 0 | 2025-08-15 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1735001042/IF/22012035619987 — Ek bagiya maa ke naam maya / kripal | New | 0 | 0 | 2025-08-15 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1735001042/IF/22012035628544 — ek bagiya maa ke naam birajo varkade | New | 0 | 0 | 2025-08-15 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1735001042/IF/22012035628547 — ek bagiya maa ke naam maya bai | New | 0 | 0 | 2025-08-15 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035631089 — peripheriwel Hitgrahi sundar /sehan | Completed | 192796.77 | 155533.75 | 2025-11-20 - 2026-03-23
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1735001042/IF/22012035631629 — Ek bagiya maa ke naam Maya Bai | Ongoing | 269386.03 | 86670.91 | 2025-10-30 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035647223 — peripheriwel Hitgrahi devanti/aghnu | Completed | 198802.86 | 149499.22 | 2025-12-12 - 2026-05-17
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035647230 — peripheriwel Hitgrahi chandar/balaram | Completed | 164945.24 | 105315.75 | 2026-01-15 - 2026-06-01
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735001042/IF/22012035649174 — peripheriwel Hitgrahi suraj/chital | Completed | 138896.86 | 111203.42 | 2026-01-01 - 2026-03-23
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035651321 — peripheriwel Hitgrahi Kasturiya bai/Anandi | Completed | 91424.17 | 71671.44 | 2026-01-03 - 2026-03-23
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035651328 — peripheriwel Hitgrahi Haresingh/gorelal | Approved | 0 | 0 | 2025-10-04 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035651332 — peripheriwel Hitgrahi Haresingh/gorelal | Approved | 0 | 0 | 2025-10-04 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035652663 — peripheriwel Hitgrahi Akalsingh/Giran | Completed | 104987.79 | 68109.94 | 2026-02-05 - 2026-05-17
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035652680 — peripheriwel Hitgrahi pancham/kandhee | Ongoing | 99336.29 | 39974.14 | 2026-01-01 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735001042/IF/22012035652685 — peripheriwel Hitgrahi siyabai/premlal | Ongoing | 84067.83 | 51567.32 | 2026-03-12 -
MANDLA / BIJADANDI / KHANORA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735001042/IF/IAY/4667075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114711849 | Completed | 23085 | 23085 | 2024-10-23 - 2025-02-12
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1735001042/LD/22012034950637 — Stone peripheral wall Puliya ke pass se revat ke badee ke or Khanora | Ongoing | 99699.5 | 47704.05 | 2026-01-08 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1735001042/LD/22012034950638 — Stone peripheral wall DHaram ke ghar se Grampanchayat ke or Khanora | Ongoing | 229415.07 | 128632.52 | 2025-04-11 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1735001042/WC/22012035024718 — GALI PLAG CHEK DEM BAJAR KE PASS TINSAI | Completed | 98682.87 | 72320 | 2023-01-14 - 2024-02-13
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1735001042/WC/22012035024729 — GALI PLAG chek dem harranala tinsai | Completed | 118379.46 | 86336 | 2023-06-15 - 2024-02-13
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735001042/WC/22012035035141 — GALI PLAG BOLDAR CHEK DEM KOHVA NALA TINSAI | Deleted | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735001042/WC/22012035035142 — GALI PLAG BOLDAR CHEK DEM KOHVA NALA TINSAI | Closed | 0 | 0 | 2022-11-24 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1735001042/WC/22012035130249 — Gebiyan bal dibra nala mai khanoura Part -1 | Closed | 0 | 0 | 2023-08-25 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1735001042/WC/22012035130261 — Gebiyan bal dibra nala mai khanoura part -2 | Closed | 0 | 0 | 2023-08-25 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1735001042/WC/22012035130271 — Gebiyan bal jharna ke pass khanoura-1 | Closed | 0 | 0 | 2023-08-25 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1735001042/WC/22012035130277 — Gebiyan bal shamshan ghat ke pass khanoura | Closed | 0 | 0 | 2023-08-25 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735001042/WC/22012035153957 — Boldar chek demekhakharol ghat nala | Closed | 0 | 0 | 2023-12-13 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735001042/WC/22012035153958 — Boldar chek demekhakharol ghat nala | Closed | 0 | 0 | 2023-12-13 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735001042/WC/22012035153959 — Boldar chek demekhakharol ghat nala | Completed | 123913.19 | 101322 | 2024-02-23 - 2024-06-19
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1735001042/WC/22012035170873 — stap dem nirman | Completed | 1451515.53 | 1405255.01 | 2024-03-16 - 2024-10-28
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1735001042/WC/22012035210693 — Geviyan nirmad sikaritola ke pass wale nala me | New | 0 | 0 | 2024-06-14 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1735001042/WC/22012035210703 — Geviyan nirmad sikaritola ke pass wale nala me | New | 0 | 0 | 2024-06-14 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1735001042/WC/22012035210710 — Geviyan nirmad sikari tola ke pass wale nala me | Approved | 235900.94 | 0 | 2024-06-14 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1735001042/WC/22012035217940 — Geviyan nirmad dibra nala part 1 | Completed | 295874.07 | 262039.67 | 2024-09-04 - 2026-02-18
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1735001042/WC/22012035217941 — Geviyan nirmad dibra nala part 02 | Completed | 375656.4 | 344440.71 | 2024-09-01 - 2025-09-24
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1735001042/WC/22012035218317 — Geviyan nirmad dibra nala part 03 | New | 0 | 0 | 2024-06-14 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1735001042/WC/22012035218318 — Geviyan nirmad dibra nala part 03 | New | 0 | 0 | 2024-06-14 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1735001042/WC/22012035218337 — Geviyan nirmad dibra nala part 03 | Completed | 376984.83 | 353301.15 | 2024-09-01 - 2025-09-24
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1735001042/WC/22012035250837 — Stone peripheral wall Puliya ke pass se revat ke badee ke or | New | 0 | 0 | 2025-01-27 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1735001042/WC/22012035257966 — sarvjanik koop nirmad khanora khirkhadad ke pass | Approved | 0 | 0 | 2025-04-03 -
MANDLA / BIJADANDI / KHANORA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1735001042/WC/22012035273175 — JGSA Recharge pitsarvjanik koop khanora | Physically Completed | 25899.46 | 21700.87 | 2025-04-30 - 2026-04-13