## Work List
Exported on: 2026-09-08 13:23:11
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SINGODHA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Unskilled wage for Bio gas plant for community / Unskilled wage component towards the construction of Bio-gas plant for community | Bio-gas plant | 1735002012/AV/22012034663411 — Kantur nirman tikra Barra singodha | New | 0 | 0 | 2025-01-09
MANDLA / NARAYANGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Farm Forestry -Comm / Wasteland Block Plantation of Farm Forestry Trees for Community | Plantation | 1735002012/DP/22012034591468 — वसुधा वंदन अमृत वाटिका बड़ा तालाब ग्राम देहरा ग्राम पंचायत - सिगौधा | Ongoing | 55847.4 | 0 | 2023-09-23
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1735002012/IF/22012035381958 — khet talab nirman dhanraj /ram singh | Ongoing | 312775.97 | 0 | 2025-04-26
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735002012/IF/22012035497773 — Khet Talab Nrman Karya dashrath /kamal gp singodha | Ongoing | 312775.97 | 0 | 2025-05-22
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735002012/IF/22012035520618 — Khet Talab Nrman Karya Dhanraj / Ram Singh Singodha | Approved | 0 | 0 | 2025-04-14
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1735002012/IF/22012035547671 — khet talab nirman jagarnatha soyam /raghuveer soyam | Approved | 0 | 0 | 2025-04-14
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735002012/IF/22012035618072 — EK BAGIYA MAA KE NAM | New | 0 | 0 | 2025-08-16
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735002012/IF/22012035637302 — Ek bagiya ma ke name hitgrahi sarasvati/bharat | Ongoing | 283818.41 | 0 | 2025-11-13
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735002012/IF/22012035637312 — Ek bagiya maa ke name sumta/sukhchain | Ongoing | 283818.41 | 0 | 2025-11-13
MANDLA / NARAYANGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/2649044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4466699 | Ongoing | 28500 | 0 | 2021-07-08
MANDLA / NARAYANGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/2649277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4272452 | Ongoing | 28500 | 0 | 2021-07-08
MANDLA / NARAYANGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/2663327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4035006 | Ongoing | 28500 | 0 | 2021-07-01
MANDLA / NARAYANGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/2663998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4169062 | Ongoing | 28500 | 0 | 2022-05-01
MANDLA / NARAYANGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/2665236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4228325 | Ongoing | 28500 | 0 | 2021-07-08
MANDLA / NARAYANGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/2667083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4461994 | Ongoing | 28500 | 0 | 2021-07-01
MANDLA / NARAYANGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/3125531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4153142 | Ongoing | 28500 | 0 | 2021-07-01
MANDLA / NARAYANGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/3141362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5164330 | Ongoing | 28500 | 0 | 2021-07-08
MANDLA / NARAYANGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/3271540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5071375 | Ongoing | 28500 | 0 | 2022-03-14
MANDLA / NARAYANGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/3275503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5338274 | Ongoing | 28500 | 0 | 2022-02-04
MANDLA / NARAYANGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/3278570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5547477 | Ongoing | 28500 | 0 | 2022-03-14
MANDLA / NARAYANGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/3300906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4016647 | Ongoing | 28500 | 0 | 2022-04-11
MANDLA / NARAYANGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/3303295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5035800 | Ongoing | 28500 | 0 | 2022-05-01
MANDLA / NARAYANGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/3303413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5065033 | Ongoing | 28500 | 0 | 2022-05-01
MANDLA / NARAYANGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/3303825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5217925 | Ongoing | 28500 | 0 | 2022-05-01
MANDLA / NARAYANGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/3304492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5436708 | Ongoing | 28500 | 0 | 2022-03-14
MANDLA / NARAYANGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/3401543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4308607 | Ongoing | 28500 | 0 | 2022-05-01
MANDLA / NARAYANGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/3416869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4830919 | Ongoing | 28500 | 0 | 2022-04-15
MANDLA / NARAYANGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/3423511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5069123 | Ongoing | 28500 | 1750 | 2022-05-01
MANDLA / NARAYANGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/3541676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4669695 | Ongoing | 28500 | 0 | 2022-04-15
MANDLA / NARAYANGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/3603028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4032237 | Ongoing | 28500 | 0 | 2022-04-11
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/4489545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151977106 | Ongoing | 28500 | 0 | 2025-03-02
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/4657194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147808370 | Ongoing | 28500 | 0 | 2025-03-02
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735002012/IF/IAY/5347233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147807586 | Ongoing | 28500 | 0 | 2025-07-13
MANDLA / NARAYANGANJ | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1735002012/WC/22012034592153 — sarvjanik koop nirman mohgaov khermai ke pas | Ongoing | 470874.11 | 0 | 2021-01-06
MANDLA / NARAYANGANJ | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1735002012/WC/22012035163478 — sarvjanik koop nirman | New | 0 | 0 | 2023-01-25
MANDLA / NARAYANGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1735002012/WC/22012035181493 — chek dem nirman kunda tola dehar | Ongoing | 1353023.79 | 0 | 2024-03-16
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735002012/WC/22012035220820 — kantur nirman karya madiya kol dehra | New | 0 | 0 | 2024-08-17
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735002012/WC/22012035220821 — kantur nirman karya madiya kol dehra | Approved | 0 | 0 | 2024-08-17
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735002012/WC/22012035220832 — kantur nirman kay badi tola tikra kol singodha | Approved | 0 | 0 | 2024-08-17
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735002012/WC/22012035220845 — kantur nirman tikra barra tari me | Approved | 0 | 0 | 2024-08-17
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735002012/WC/22012035220849 — kantur nirman pitambar kol mohgav | Approved | 0 | 0 | 2024-08-17
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1735002012/WC/22012035223438 — saravajanik purculetion taink singodha | Approved | 0 | 0 | 2024-10-03
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1735002012/WC/22012035223469 — saravajanik percolation tanks singodha talaeya jheel | Approved | 0 | 0 | 2024-10-03
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1735002012/WC/22012035226374 — percolation tank usari kol dehra | Approved | 0 | 0 | 2024-10-03
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1735002012/WC/22012035226378 — percolation tank hajariya kol dehra | Approved | 0 | 0 | 2024-10-03
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735002012/WC/22012035229468 — kantur niraman kotvar kol mohgaon | Approved | 0 | 0 | 2024-11-15
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735002012/WC/22012035229469 — kantur niraman shanti dham tari mohgaon | Approved | 0 | 0 | 2024-11-15
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735002012/WC/22012035230114 — kantur niraman tikra barra ke pas singodha | Approved | 0 | 0 | 2024-11-15
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735002012/WC/22012035230126 — kantur niraman chhota patpara ke upar taraph songodha | Approved | 0 | 0 | 2024-11-15
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735002012/WC/22012035230129 — kantur niraman shiddha vala tari dehra | Approved | 0 | 0 | 2024-11-15
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1735002012/WC/22012035241757 — Kantur nirman jheel ke pass kunda tol dehra | Approved | 462182.57 | 0 | 2025-01-09
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1735002012/WC/22012035241763 — Kantur nirman kamani kol mohgaov | Approved | 0 | 0 | 2025-01-09
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1735002012/WC/22012035261431 — JGSA-2025 Recharde structure Sarvjanik koop chimka tola Dehra | New | 0 | 0 | 2025-04-11
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1735002012/WC/22012035261441 — JGSA-2025 Recharde structure Sarvjanik koop madiya vala beech tola Dehra | Approved | 0 | 0 | 2025-04-11
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735002012/WC/22012035320062 — kantur nirman pat vale tari me dehra | Approved | 0 | 0 | 2025-08-18
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735002012/WC/22012035328300 — KANTUR NIRMAR MARGHAT CHHETRA SINGODHA | Approved | 0 | 0 | 2026-01-26
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735002012/WC/22012035328302 — KANTUR NIRMAR BUCHI DAI CHHETRA SINGODHA | Approved | 0 | 0 | 2026-01-26
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735002012/WC/22012035328304 — KANTUR NIRMAR GABHI GHAT CHHETRA MOHGAOV | New | 0 | 0 | 2026-01-26
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735002012/WC/22012035328305 — KANTUR NIRMAR GABHI GHAT CHHETRA MOHGAOV | Approved | 0 | 0 | 2026-01-26
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735002012/WC/22012035328307 — KANTUR NIRMAR emli kol dehra | Approved | 0 | 0 | 2026-01-26
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735002012/WC/22012035328310 — KANTUR NIRMAR bajrahi CHHETRA dehra | Approved | 0 | 0 | 2026-01-26
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735002012/WC/22012035328312 — KANTUR NIRMAR ber vale tari part 2 dehra kunda tola | Approved | 0 | 0 | 2026-01-26
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1735002012/WC/VB/22012035330266 — CONSTRUTION OFSTAGGERED CONTURE TRENCH BAKHARA KOL TALAB KE UPAR DEHRA | Approved | 356403.89 | 0 | 2026-07-23
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1735002012/WC/VB/22012035330276 — CONSTRUTION OFSTAGGERED CONTURE TRENCH MAHUYA KOL PAHADI MOHGAOV | Approved | 356403.89 | 0 | 2026-07-23
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1735002012/WC/VB/22012035330281 — CONSTRUTION OFSTAGGERED CONTURE TRENCH NIRMAN KARIYA KOL SINGODHA | Approved | 0 | 0 | 2026-07-23
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1735002012/WC/VB/22012035330286 — CONSTRUTION OFSTAGGERED CONTURE TRENCH NIRMAN RANI KOL PAHADI KUNDA TOLA DEHRA | Approved | 0 | 0 | 2026-07-23
MANDLA / NARAYANGANJ | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1735/RC/22012034827140 — RES Gravel Road Singodha se Mohgoan tak | Ongoing | 2767000 | 0 | 2024-12-12