## Work List
Exported on: 2026-10-07 07:27:32
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KUDAMAILI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Unskilled wage for Bio gas plant for community / Construction of Biogas Plant for Community | Bio-gas plant | 1735002022/AV/22012034658052 — वृक्षारोपड कूड़ा मैली से जंगल सरहद तक | New | 0 | 0 | 2024-06-24
MANDLA / NARAYANGANJ | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1735002022/DP/22012034563286 — samudaik posand watika ps school ke piche kudaaili | Ongoing | 925000 | 0 | 2022-09-15
MANDLA / NARAYANGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1735002022/DP/22012034591365 — वसुधा वंदन अमृत वाटिका चरगांव तालाब के पास | Ongoing | 55847.4 | 0 | 2023-09-16
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Plantation in Coastal Area for Community | Plantation | 1735002022/DP/22012034620881 — POUDHAROPAN MEDHO CHABUTRA SE JANGAL SARHAD | Ongoing | 305761.26 | 0 | 2024-07-08
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735002022/IF/22012035290936 — Bhumi sudhar sdukhlal/nadlal | Approved | 0 | 0 | 2024-08-15
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735002022/IF/22012035290968 — Faival band niramDhaniya/pancham | Approved | 0 | 0 | 2024-08-15
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735002022/IF/22012035293291 — Cantur trench purane pani kol kudamaili | New | 0 | 0 | 2024-08-15
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735002022/IF/22012035295392 — khet talab birsing/dhokal | Approved | 0 | 0 | 2025-01-25
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735002022/IF/22012035295397 — boldar med bandhan kehar/mulva | Approved | 0 | 0 | 2025-01-25
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735002022/IF/22012035300138 — bhumi sudhar gopal/halkeram | Approved | 0 | 0 | 2024-08-16
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735002022/IF/22012035313908 — खेत तालाब निर्माण(बीरसिंह/धोकल )गोंड चरगांव | Approved | 296479.41 | 0 | 2025-03-15
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1735002022/IF/22012035418371 — sarvjanik koop nirman bhachatola | New | 0 | 0 | 2025-04-24
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735002022/IF/22012035495594 — Khet Talab Nrman Karya shanri bai /veeran gp kudamaili | Physically Completed | 312775.97 | 0 | 2025-05-16 | 2026-07-12
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1735002022/IF/22012035639820 — Feriphrral band niram/sanehi/aghanu | Ongoing | 191886.11 | 0 | 2025-12-29
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735002022/IF/22012035660195 — feripheyal band niram /peetam /motti | Approved | 0 | 0 | 2026-01-23
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1735002022/IF/IAY/1574965 — Construction of IAY House -IAY REG. NO. MP2110200 | Ongoing | 28500 | 0 | 2024-12-03
MANDLA / NARAYANGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002022/IF/IAY/2703093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5471544 | Completed | 24795 | 0 | 2021-09-17 | 2026-08-18
MANDLA / NARAYANGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002022/IF/IAY/3512800 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2080397 | Completed | 24795 | 0 | 2022-03-15 | 2026-08-18
MANDLA / NARAYANGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002022/IF/IAY/4358276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3295316 | Approved | 28500 | 0 | 2022-06-24
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002022/IF/IAY/4662739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149984427 | Approved | 28500 | 0 | 2024-09-14
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002022/IF/IAY/4664735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150539808 | Approved | 28500 | 0 | 2024-09-09
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002022/IF/IAY/4787222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131304245 | Physically Completed | 28500 | 0 | 2024-10-17 | 2026-09-13
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1735002022/LD/22012034945879 — खेल मैदान कूड़ामेली | Approved | 0 | 0 | 2024-10-02
MANDLA / NARAYANGANJ | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair and maintenance of WBM Roads for Community / Repair & Maintenance of WBM Road for Community | Repair & maint of Road | 1735002022/RC/22012034676298 — sudur sadak niramd Kudamaili sarhad se chargon | New | 0 | 0 | 2024-01-26
MANDLA / NARAYANGANJ | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair and Maintenance of Stone Spur for Community / Repair & Maintenance of Stone Spur for Community | Repair & maint of Water Harvesting Structures | 1735002022/WC/22012035163968 — parkoleshan tenk dumari ke khet ke pass | New | 0 | 0 | 2024-01-27
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735002022/WC/22012035231324 — Gali plag Junvani Nala Kudameli | Approved | 0 | 0 | 2024-08-27
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Borewell for Community | Well Recharge | 1735002022/WC/22012035243490 — Cantur trench purane pani kol kudamaili | Approved | 0 | 0 | 2024-08-15
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735002022/WC/22012035245397 — Cantur trench mutiya tarer kudamaili | Approved | 0 | 0 | 2024-08-15
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1735002022/WC/22012035247397 — Bhumi sudhar sona/mansingh | New | 0 | 0 | 2024-08-15
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1735002022/WC/22012035250851 — gp kudamaili nistari talab nirman kary gram chargaon | New | 0 | 0 | 2025-02-20
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1735002022/WC/22012035250857 — gp kudamaili nistari talab nirman kary gram chargaon | Approved | 2352094.37 | 0 | 2025-02-20
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1735002022/WC/VB/22012035330947 — CONSTRUTION OF STAGGERED CONTURE TRENCH MASRAHI KOL CHARGAOM GP KUDAMAILI | Ongoing | 356403.89 | 167050 | 2026-08-06
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1735002022/WC/VB/22012035330949 — CONSTRUTION OF STAGGERED CONTURE TRENCH MARGHATI KOL KUDAMAILI GP KUDAMAILI | Ongoing | 356403.89 | 1275 | 2026-09-03