## Work List
Exported on: 2026-10-11 04:00:10
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JEWRA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDLA / NARAYANGANJ | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1735002039/AV/22012034623489 — CONSTRSION OF ANGANWADI CHHATI TOLA DADARGAON | Ongoing | 500000 | 0 | 2022-12-14
MANDLA / NARAYANGANJ | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1735002039/AV/22012034661715 — p s jewra me samtalikarn | New | 0 | 0 | 2024-04-15
MANDLA / NARAYANGANJ | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1735002039/AV/VB/YD/22012034669622 — Construction of Play field PS Building Dadargaon | New | 0 | 0 | 2026-08-15
MANDLA / NARAYANGANJ | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1735002039/DP/22012034564731 — pavdh ropan Jagat/faggan | Ongoing | 124487.29 | 0 | 2022-09-03
MANDLA / NARAYANGANJ | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1735002039/DP/22012034564738 — pavdha ropan rancharan /ramsingh | Ongoing | 124487.29 | 0 | 2022-09-03
MANDLA / NARAYANGANJ | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1735002039/DP/22012034564742 — pavdha ropan nuniya bai/kashiram | Ongoing | 124487.29 | 2240 | 2022-09-03
MANDLA / NARAYANGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Avenue Plantation for Community | Plantation | 1735002039/DP/22012034591370 — वसुधा वंदन अमृत वाटिका प्रथमिक शाला परिसर ग्राम दादरगांव ग्रामपंचायत जेवरा | Ongoing | 55847.4 | 19060.63 | 2023-08-20
MANDLA / NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Avenue Plantation for Community | Plantation | 1735002039/DP/22012034621654 — वृक्षरोपण ग्राम पंचायत के सामने रोड के दोनों ओर | Approved | 308751.16 | 0 | 2024-06-08
MANDLA / NARAYANGANJ | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Check Dam for Individual | Construction of Check Dam/Stop Dam | 1735002039/IF/22012034959813 — खेत तालाब निर्माण रामप्यारे /सोभन सिंह जेवरा | Ongoing | 485877.63 | 0 | 2022-04-20
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735002039/IF/22012035316711 — खेत तालाब निर्माण कार्य हितग्राही सुरजीत/जगत सिंह ग्राम जेवरा। | Approved | 449511.02 | 0 | 2025-01-24
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735002039/IF/22012035596433 — EK BAGIYA MAA KE NAME SUBANSHA/RAJENDRA MP1735002039/49B | Ongoing | 283816.51 | 534.56 | 2025-09-24
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735002039/IF/22012035596436 — EK BAGIYA MAA KE NAME RAMOTI/LAMMU MP35002039/66A | Approved | 0 | 0 | 2025-08-15
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735002039/IF/22012035596437 — EK BAGIYA MAA KE NAME PREM BAI/RAJARAM MP35002039/49B | Ongoing | 283816.51 | 793.32 | 2025-09-24
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735002039/IF/22012035622213 — EK BAGIYA MAA KE NAM SUBHANSA /RAJENDRA GRAM JEWRA GP JEWRA | New | 0 | 0 | 2025-08-16
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735002039/IF/22012035622214 — EK BAGIYA MAA KE NAM PREM BAI / RAJARAM | New | 0 | 0 | 2025-08-16
MANDLA / NARAYANGANJ | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/2614225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5345103 | Ongoing | 28500 | 1300 | 2021-02-28
MANDLA / NARAYANGANJ | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/2616095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5334859 | Completed | 24795 | 0 | 2021-02-28 | 2026-08-17
MANDLA / NARAYANGANJ | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/3252865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1550545 | Approved | 28500 | 0 | 2020-11-11
MANDLA / NARAYANGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/3387015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2576455 | Completed | 24795 | 0 | 2022-03-12 | 2026-08-17
MANDLA / NARAYANGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/3453971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4549768 | Ongoing | 28500 | 0 | 2022-02-28
MANDLA / NARAYANGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/3716330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114941014 | Completed | 24795 | 0 | 2022-05-14 | 2026-08-17
MANDLA / NARAYANGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/4339982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114940279 | Ongoing | 28500 | 0 | 2026-04-14
MANDLA / NARAYANGANJ | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/43879 — Construction of IAY House -IAY REG. NO. MP-35-002-039-001/5851 | Ongoing | 28500 | 0 | 2023-07-28
MANDLA / NARAYANGANJ | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/43880 — Construction of IAY House -IAY REG. NO. MP-35-002-039-001/5970 | Ongoing | 28500 | 0 | 2023-11-23
MANDLA / NARAYANGANJ | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/43881 — Construction of IAY House -IAY REG. NO. MP-35-002-039-002/5816 | Ongoing | 28500 | 0 | 2023-07-28
MANDLA / NARAYANGANJ | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/43882 — Construction of IAY House -IAY REG. NO. MP-35-002-039-003/11686 | Ongoing | 28500 | 0 | 2023-12-07
MANDLA / NARAYANGANJ | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/43883 — Construction of IAY House -IAY REG. NO. MP-35-002-039-003/11714 | Ongoing | 28500 | 0 | 2023-11-23
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/4639436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131839189 | Ongoing | 28500 | 0 | 2025-03-05
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/4745016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114940305 | Physically Completed | 24795 | 0 | 2025-03-05 | 2026-08-17
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/4745020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114940928 | Completed | 24795 | 0 | 2025-03-05 | 2026-07-28
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/4810081 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152055690 | Ongoing | 28500 | 0 | 2025-03-05
MANDLA / NARAYANGANJ | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1735002039/IF/IAY/848576 — Construction of IAY House -IAY REG. NO. MP1472516 | Ongoing | 28500 | 0 | 2018-12-28
MANDLA / NARAYANGANJ | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1735002039/WC/22012034920154 — स्टाप डेम जीडोद्वार पिपरहा नाला | Ongoing | 127624.24 | 0 | 2022-05-05
MANDLA / NARAYANGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Mini Percolation Tank for Comm / Repair & Maintenance of Percolation Tank for Community | Repair & maint of Percolation Tank | 1735002039/WC/22012035161897 — PARKOLATION TENK MARGHAT NALA | New | 0 | 0 | 2024-01-26
MANDLA / NARAYANGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1735002039/WC/22012035161900 — PARKOLATION TENK MANJEERA NALA | New | 0 | 0 | 2024-01-26
MANDLA / NARAYANGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1735002039/WC/22012035161906 — PARKOLATION TENK MANJEERA NALA | New | 0 | 0 | 2024-01-26
MANDLA / NARAYANGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1735002039/WC/22012035161914 — PARKOLATION TENK BHALVA NALA | New | 0 | 0 | 2024-01-26
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1735002039/WC/22012035289923 — JGSA-2025 डगवेल रिचार्ज स्ट्रक्चर सार्वजनिक कूप बड़ा टोला ग्राम भैंसवाही। | Ongoing | 25899.46 | 0 | 2025-05-20
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1735002039/WC/22012035289927 — JGSA-2025 डगवेल रिचार्ज स्ट्रक्चर सार्वजनिक कूप खाली टोला ग्राम जेवरा। | Ongoing | 25899.46 | 0 | 2025-06-04
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1735002039/WC/22012035323574 — कंटूर ट्रेंच निर्माण राढ़ी पहाड़ी भैसवाही | Ongoing | 336021.06 | 0 | 2026-02-12
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735002039/WC/VB/22012035330299 — CONTUR TRENCH SARDAR PAHADI DADARGAON | Approved | 0 | 0 | 2026-04-14
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735002039/WC/VB/22012035330305 — CONTUR TRENCH AMA KHUDRA PAHADI DADARGAON | Approved | 0 | 0 | 2026-04-14
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735002039/WC/VB/22012035330311 — CONTUR TRENCH KERAV PAHADI DADARGAON | Approved | 0 | 0 | 2026-04-14
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735002039/WC/VB/22012035330319 — CONTUR TRENCH UMRAHA PAHADI BHAINSWAHI | Approved | 0 | 0 | 2026-04-14
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735002039/WC/VB/22012035331768 — Constructions Of Contour Trench Aama Khudra Pahadi Gram Dadargaon | Ongoing | 340672.58 | 248783 | 2026-09-05
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735002039/WC/VB/22012035331771 — Constructions Of Contour Trench Korva Pahadi Gram Dadargaon | Ongoing | 374393.04 | 250085.88 | 2026-08-19
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735002039/WC/VB/22012035331774 — Constructions Of Contour Trench Sardar Pahadi Gram Dadargaon | Ongoing | 408605.49 | 42280 | 2026-09-19
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735002039/WC/VB/22012035331777 — Constructions Of Contour Trench Umraha Pahadi Gram Bhaiswahi | Approved | 425465.72 | 0 | 2026-06-24
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735002039/WC/VB/22012035331824 — Constructions Of Contour Trench Kuteli Pahadi Gram Jewra | Approved | 357532.81 | 0 | 2026-06-24
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002039/WC/VB/22012035332467 — Gabion Nirman Sovni Nala Gram Dadargaon Jewra | Approved | 0 | 0 | 2026-04-14
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002039/WC/VB/22012035332714 — Gabion Nirman Bhadoriya Nala Gram Dadargaon Jewra | Approved | 0 | 0 | 2026-04-14
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002039/WC/VB/22012035332717 — Gabion Nirman Tenduva Nala Gram Dadargaon Jewra | Approved | 0 | 0 | 2026-04-14
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002039/WC/VB/22012035332722 — Gabion Nirman Jamneswari Nala Gram Jewra | Approved | 0 | 0 | 2026-04-14
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002039/WC/VB/22012035334347 — Gabion Nirman Channdi Nala Gram Bhainswahi Jewra | Approved | 0 | 0 | 2026-04-14