## Work List
Exported on: 2026-10-10 13:43:54
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: DEORI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDLA / NARAYANGANJ | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1735002050/AV/22012034652380 — Panchayat bhavan | Approved | 0 | 0 | 2023-10-02
MANDLA / NARAYANGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1735002050/DP/22012034613180 — vraxaropan kary devri | New | 0 | 0 | 2023-10-02
MANDLA / NARAYANGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1735002050/DP/22012034613544 — Vraxaropan kary | New | 0 | 0 | 2023-10-02
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1735002050/DP/22012034630152 — Block Plantation of Forestry Trees in Fields for Community devri contoor parisar par | Approved | 0 | 0 | 2025-04-14
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1735002050/DP/22012034630153 — Block Plantation of Forestry Trees in Fields for Community khuri contoor parisar | Approved | 0 | 0 | 2025-04-14
MANDLA / NARAYANGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Check Dam for Individual | Construction of Check Dam/Stop Dam | 1735002050/IF/22012035198501 — Bhumi sudhar kary | New | 0 | 0 | 2023-10-02
MANDLA / NARAYANGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Check Dam for Individual | Construction of Check Dam/Stop Dam | 1735002050/IF/22012035198507 — bhumi sudhar kary | New | 0 | 0 | 2023-10-02
MANDLA / NARAYANGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1735002050/IF/22012035201649 — Bhumi sudhar ravi | New | 0 | 0 | 2023-10-02
MANDLA / NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002050/IF/IAY/4610071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124531219 | Ongoing | 28500 | 0 | 2024-09-25
MANDLA / NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002050/IF/IAY/5822336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127991046 | Completed | 24795 | 261 | 2025-10-29 | 2026-08-17
MANDLA / NARAYANGANJ | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1735002050/RC/22012034674938 — puliya nirman mukhy marg se basti pahuch marg tak | New | 0 | 0 | 2023-10-02
MANDLA / NARAYANGANJ | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1735002050/RC/22012034674940 — graval marg mundi tola | New | 0 | 0 | 2023-10-02
MANDLA / NARAYANGANJ | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1735002050/RC/22012034676116 — Greval rod talab pahuch marg | New | 0 | 0 | 2023-10-02
MANDLA / NARAYANGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735002050/WC/22012035161371 — Kantoor trench devri | New | 0 | 0 | 2023-10-02
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735002050/WC/22012035257662 — contraction of percolation tank devri kol par | Approved | 0 | 0 | 2025-04-01
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735002050/WC/22012035257663 — contraction of percolation tank khuri kol par | Approved | 0 | 0 | 2025-04-01
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1735002050/WC/22012035307578 — JGSA 2025 dugwell Recharchge structure narsari kup | Approved | 0 | 0 | 2025-04-14
MANDLA / NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1735002050/WC/22012035307580 — JGSA 2025 dugwell Recharchge structure basti andar kup | Approved | 0 | 0 | 2025-04-14
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1735002050/WC/VB/22012035329417 — Kantoor trench staggard nirman deori pahadi par part 3 | Approved | 0 | 0 | 2026-06-05
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735002050/WC/VB/22012035329652 — Construction of staggered contour trench for community Khurri Pahadi GP Deori | Approved | 357403.89 | 0 | 2026-04-26
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1735002050/WC/VB/22012035329656 — Construction of staggered contour trench for community Bagdari kol GP Deori | Ongoing | 118475.7 | 74745 | 2026-08-05
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002050/WC/VB/22012035330675 — Construction Of Gabion Structure Matta ke Pass Nala G P Devri | Approved | 0 | 0 | 2026-07-10
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002050/WC/VB/22012035330685 — Construction Of Gabion Structure Mahuaa Nala Mahuaa Ke Pass g p Devri | Approved | 0 | 0 | 2026-07-10
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002050/WC/VB/22012035330690 — Construction Of Gabion Structure Neel kol Nala Neel Kol Me gp Devri | Approved | 0 | 0 | 2026-07-10
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002050/WC/VB/22012035330694 — Construction Of Gabion Structure Talab Nala Talab Ke Pass Khurri GP Devri | Approved | 0 | 0 | 2026-07-10
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002050/WC/VB/22012035330729 — Construction Of Gabion Structure Neel Khurril Nala Vidhya Ke Khet Ke Pass gp Devri | Approved | 0 | 0 | 2026-07-10
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002050/WC/VB/22012035330738 — Construction Of Gabion Structure khurri Shaya Ke Khet Ke Pass gp Devri | Approved | 0 | 0 | 2026-07-10
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1735002050/WC/VB/22012035330743 — Construction Of Staggrerd Contur Trench Jamunai Tekti Par Khurri GP Devri | Approved | 133267.69 | 0 | 2026-07-10
MANDLA / NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1735002050/WC/VB/22012035330745 — Construction Of Staggrerd Contur Trench Bhalu Kol Tekri Gp Devri | Ongoing | 224095.4 | 15840 | 2026-09-02