## Work List
Exported on: 2026-09-08 20:45:43
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SUKHARISANGRAMPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDLA / NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1735003009/DP/22012034624382 — Amrit sarovar plantion sukhri sangrampur | New | 0 | 0 | 2024-04-15
MANDLA / NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1735003009/DP/22012034624383 — amrit sarovar plantion sukharisangrampur | Approved | 0 | 0 | 2024-04-15
MANDLA / NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1735003009/IF/22012035188235 — bolder med bandhan(kali bai/siddhi)sukhri | Ongoing | 169283.96 | 0 | 2025-06-08
MANDLA / NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1735003009/IF/22012035272471 — khet talab nirmaantilak singh/gore lal kharkhara | Approved | 0 | 0 | 2024-04-24
MANDLA / NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1735003009/IF/22012035557257 — golu ke koop ke pass dugwell recharge | Approved | 0 | 0 | 2025-04-25
MANDLA / NIWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735003009/IF/22012035623801 — Eak Bagiya Maa Ke Nam Hiteshi Omti Bai/Sumeri Lal sukharisangrampur | Ongoing | 141999.68 | 0 | 2025-10-24
MANDLA / NIWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735003009/IF/22012035624352 — EK BAGIYA MAA K NAAM PARVATI BAI MARAVI/ TIRATH JALDHARA | Ongoing | 142000.22 | 809.7 | 2025-10-24
MANDLA / NIWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735003009/IF/22012035627339 — Eak Bagiya Maa Ke Nam Hiteshi Vandana Bai / Kushal | Ongoing | 142000.22 | 12918.88 | 2025-10-30
MANDLA / NIWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735003009/IF/22012035627541 — Eak Bagiya Maa Ke Nam Hiteshi Susheela/Raju | Ongoing | 142000.22 | 0 | 2025-10-30
MANDLA / NIWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735003009/IF/22012035628201 — Eak Bagiya Maa Ke Nam Hiteswhi Amrati Bai/ RamLochan GP Sukharisangrampur | Ongoing | 142000.22 | 6780.2 | 2025-10-30
MANDLA / NIWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735003009/IF/22012035628204 — Eak Bagiya Maa Ke Nam Hiteshi Kanti Bai/ Kaluram | Ongoing | 142000.22 | 16325.1 | 2025-10-24
MANDLA / NIWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735003009/IF/22012035629026 — Eak Bagiya Maa Ke Nam Hiteshi Gyan bai / Ratan | Ongoing | 142000.22 | 0 | 2025-10-30
MANDLA / NIWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735003009/IF/22012035629211 — Eak Bagiya Maa Ke Nam Mango Bai / Ramasingh | Ongoing | 142000.22 | 0 | 2025-10-30
MANDLA / NIWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735003009/IF/22012035652517 — एक बगिया मां के नाम हितग्राही सुनीता बाई/कालूराम ग्राम खरखरा ग्राम पंचायत सुखरी संग्रामपुर। | New | 0 | 0 | 2025-10-02
MANDLA / NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1735003009/IF/22012035655229 — sarvjanik koop marammat karya jhiriya nala sukhri | Approved | 0 | 0 | 2025-04-25
MANDLA / NIWAS | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735003009/IF/IAY/4034024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138970118 | Ongoing | 28500 | 0 | 2023-09-09
MANDLA / NIWAS | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735003009/IF/IAY/4604853 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124733659 | Ongoing | 28500 | 0 | 2025-01-10
MANDLA / NIWAS | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735003009/IF/IAY/4644632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138514683 | Ongoing | 28500 | 0 | 2025-03-05
MANDLA / NIWAS | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735003009/IF/IAY/4883922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124537032 | Ongoing | 28500 | 0 | 2025-03-05
MANDLA / NIWAS | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735003009/IF/IAY/6085222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124731160 | Approved | 28500 | 0 | 2025-03-11
MANDLA / NIWAS | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735003009/IF/IAY/6085223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124731799 | Approved | 28500 | 0 | 2025-03-11
MANDLA / NIWAS | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735003009/IF/IAY/6095264 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138503431 | Approved | 28500 | 0 | 2025-03-11
MANDLA / NIWAS | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735003009/IF/IAY/6095265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138503435 | Approved | 28500 | 0 | 2025-03-11
MANDLA / NIWAS | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735003009/IF/IAY/6095299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138970102 | Approved | 28500 | 0 | 2025-03-11
MANDLA / NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1735003009/LD/22012034944376 — Cpt Bund kharkhara | Approved | 0 | 0 | 2024-04-13
MANDLA / NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1735003009/LD/22012034961521 — sarvjanik bolder chek dem nirmaan kharkhara | Approved | 0 | 0 | 2025-04-25
MANDLA / NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1735003009/LD/22012034961522 — sarvjanik bolder chek dem nirmaan sukhri jhiriya nala | Approved | 0 | 0 | 2025-04-25
MANDLA / NIWAS | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1735003009/RS/22012035126631 — सुकरी चक्र घटा पुलिया निर्माण कार्य ग्राम पंचायत सखी संग्रामपुर | Ongoing | 2312100.48 | 0 | 2024-06-23
MANDLA / NIWAS | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1735003009/WC/22012034987818 — bolder med bandhan( chhote gond) | Ongoing | 115518.04 | 0 | 2023-03-12
MANDLA / NIWAS | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003009/WC/22012035165004 — BCD Sukhari | New | 0 | 0 | 2023-04-15
MANDLA / NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735003009/WC/22012035215773 — sarvjanik geviyan nirmaan 01 | Approved | 0 | 0 | 2024-04-22
MANDLA / NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735003009/WC/22012035215775 — sarvjanik geviyan nirmaan 02 | Approved | 0 | 0 | 2024-04-22
MANDLA / NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735003009/WC/22012035215776 — sarvjanik geviyan nirmaan 03 | Approved | 0 | 0 | 2024-04-22
MANDLA / NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735003009/WC/22012035216526 — sarvjanik braksharopan amrat sarover ke pass kharkhara | Approved | 0 | 0 | 2024-04-22
MANDLA / NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735003009/WC/22012035216527 — sadak kinare mukhya marg se panchayat bhavan tak praksharopan | Approved | 0 | 0 | 2024-04-22
MANDLA / NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1735003009/WC/22012035307078 — JGSA Dugwell recharge Sukhri | Approved | 0 | 0 | 2025-04-24
MANDLA / NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1735003009/WC/22012035312358 — sarvjanik koop ke pass dugwell recharge sukhri | Approved | 0 | 0 | 2025-04-25
MANDLA / NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1735003009/WC/22012035312359 — sarvjanik jhiriya nala ke pass dugwell recharge | Approved | 0 | 0 | 2025-04-25
MANDLA / NIWAS | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003009/WC/VB/22012035330923 — sarvjanik bolder chek dem nirmaan sukhri | Approved | 0 | 0 | 2026-04-25
MANDLA / NIWAS | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003009/WC/VB/22012035330924 — sarvjanik bolder chek dem nirmaan sukhri 01 | Approved | 0 | 0 | 2026-04-25
MANDLA / NIWAS | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003009/WC/VB/22012035330926 — sarvjanik bolder chek dem nirmaan kharkhara | Approved | 0 | 0 | 2026-04-25
MANDLA / NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1735003009/WH/22012034941829 — sarvjanik geviyan nirmaan 04 | Approved | 0 | 0 | 2024-04-22
MANDLA / NIWAS | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1735/WC/22012035034979 — RES-Amrit Sarovar Nirman Jaldhara | Ongoing | 5300000 | 0 | 2023-01-12