## Work List
Exported on: 2026-09-08 12:46:16
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KHUKSAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDLA / MANDLA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1735004006/DP/22012034433995 — KHUKSAR MUDADEEHMAL PLANTATION SHANTIDHAM | Ongoing | 342000 | 13582.12 | 2018-12-12
MANDLA / MANDLA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1735004006/IF/22012034582041 — khuksar mudadeeh mal plantion dan sindh/nanhe singh | Ongoing | 135219.86 | 0 | 2020-07-25
MANDLA / MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735004006/IF/22012035322313 — Gp khuksar khet talab dalpat | Ongoing | 404007.02 | 0 | 2025-04-27
MANDLA / MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735004006/IF/22012035615183 — Ek bagiya maa ke naam dhanno bai/amru | Ongoing | 269189.85 | 0 | 2025-10-08
MANDLA / MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735004006/IF/22012035615185 — Ek bagiya maa ke naam nuniya bai/chatte lal | Ongoing | 268737.85 | 3075.38 | 2025-10-08
MANDLA / MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735004006/IF/22012035661320 — GP KHUKSAR KHET TALAB SUNIL KUMAR | Ongoing | 344696.33 | 0 | 2026-03-18
MANDLA / MANDLA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004006/IF/IAY/3284774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4868043 | Approved | 28500 | 0 | 2021-10-24
MANDLA / MANDLA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004006/IF/IAY/3284785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4873685 | Approved | 28500 | 0 | 2021-10-24
MANDLA / MANDLA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004006/IF/IAY/3285431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5128129 | Approved | 28500 | 0 | 2021-10-24
MANDLA / MANDLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1735004006/IF/VB/22012035663295 — ग्राम पंचायत ख़ुक्सर बकरी शेड दान सिंह मूडाडीह am | New | 0 | 0 | 2026-08-09
MANDLA / MANDLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1735004006/IF/VB/22012035663302 — ग्राम पंचायत ख़ुक्सर बकरी शेड दान सिंह मूडाडीह | New | 0 | 0 | 2026-08-09
MANDLA / MANDLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1735004006/IF/VB/22012035663303 — ग्राम पंचायत खुक्सर दान सिह बकरी शेड | Approved | 0 | 0 | 2026-06-24
MANDLA / MANDLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1735004006/WC/22012034644166 — GP khuksar sarvajanik koop bor ke pas | Ongoing | 473791.69 | 0 | 2021-04-28
MANDLA / MANDLA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation of Forestry-Community / Canal Line Plantation of Forestry Trees for Community | Plantation | 1735004006/WC/22012035097622 — VASUDHA VANDAN AMRIT VATIKA Khuksar | Ongoing | 55847.4 | 614.55 | 2023-09-06
MANDLA / MANDLA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1735004006/WC/22012035177602 — Contour trench nirman karya | New | 0 | 0 | 2024-01-26
MANDLA / MANDLA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1735004006/WC/22012035190445 — ग्राम पंचायत खुक्सर तट बंद निर्माण कार्य बेल घाट के पास खुक्सर | Ongoing | 1070428.33 | 0 | 2024-03-15
MANDLA / MANDLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735004006/WC/22012035201600 — खुकसर चेकडेम निमार्ण कार्य प्रताप के घर के पास मराम्मत कार्य | Approved | 0 | 0 | 2024-06-01
MANDLA / MANDLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735004006/WC/22012035202773 — GABION STRUCTURE NIRMAN PATPARJHODINALLAH DUNGRIYA | Ongoing | 459939.16 | 0 | 2024-06-29
MANDLA / MANDLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735004006/WC/22012035228966 — BOULDER CHEK NIRMAN PATPARJHODI NALA DUNGRIYA | Approved | 0 | 0 | 2024-10-02
MANDLA / MANDLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735004006/WC/22012035228969 — BOULDER CHEK NIRMAN SUKALNALA DUNGRIYA | Approved | 0 | 0 | 2024-10-02
MANDLA / MANDLA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735004006/WC/VB/22012035329762 — gp khuksar gabion structure kharojhodi nala dungriya | Approved | 199202.08 | 0 | 2026-06-24
MANDLA / MANDLA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735004006/WC/VB/22012035329861 — ग्राम पंचायत खुक्सर गेबियन संरचना कार्य गुडाखू झोडी के नाला मे | Approved | 199973.21 | 0 | 2026-06-24
MANDLA / MANDLA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735004006/WC/VB/22012035330852 — GABION ANNICUT NIRMAN BLAU JHODI DUNGARIYA GP KHUKSAR | Approved | 434850.19 | 0 | 2026-04-16
MANDLA / MANDLA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735004006/WC/VB/22012035330853 — GABION ANNICUT NIRMAN KHERO JHODI NALA DUNGARIYA GP KHUKSAR | Approved | 475395.43 | 0 | 2026-04-16
MANDLA / MANDLA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735004006/WC/VB/22012035330855 — GABION ANNICUT NIRMAN GUDAKHU JHODI NALA PART 2 DUNGARIYA GP KHUKSAR | Approved | 435850.08 | 0 | 2026-04-16