## Work List
Exported on: 2026-10-17 21:43:23
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MAWAIJAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDLA / MANDLA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1735004034/AV/22012034660266 — ANGANWADI BHAWAN MAWAIJAR (KARDHAN TOLA) | Ongoing | 500000 | 5590 | 2024-10-17
MANDLA / MANDLA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Line Plantation of Horticulture Trees for Community | Plantation | 1735004034/DP/22012034557647 — MAA KI BAGIYA MAWAIJAR PANCHAYAT BHAWAN | Ongoing | 33000 | 0 | 2022-07-27
MANDLA / MANDLA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Line Plantation of Horticulture Trees for Community | Plantation | 1735004034/DP/22012034559792 — block plantation mawaijar pahadi | Ongoing | 713000 | 0 | 2022-07-30
MANDLA / MANDLA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735004034/IF/22012034680776 — MAWAIJAR KAPIL DHARA KOOP RAMVATI/DILLE | Ongoing | 307338.68 | 0 | 2021-05-15
MANDLA / MANDLA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735004034/IF/22012035102662 — kapil dhara koop poonaram/ chootu | Ongoing | 324898.07 | 0 | 2023-06-21
MANDLA / MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735004034/IF/22012035322082 — KHET TALAB MAWAIJAR SHIVLAL/GANPAT | Ongoing | 450482.54 | 0 | 2025-04-27
MANDLA / MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735004034/IF/22012035661770 — KHET TALAB MAWAIJAR RAMESWAR/BHUJBAL SINGH | New | 0 | 0 | 2026-01-28
MANDLA / MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735004034/IF/22012035661983 — KHET TALAB MAWAIJAR CHARGOAN DAYARAM/HAMER SINGH | New | 0 | 0 | 2026-01-28
MANDLA / MANDLA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735004034/IF/IAY/3163123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4898308 | Approved | 28500 | 0 | 2021-06-08
MANDLA / MANDLA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1735004034/IF/IAY/769868 — Construction of IAY House -IAY REG. NO. MP3427848 | Ongoing | 28500 | 0 | 2019-08-02
MANDLA / MANDLA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1735004034/LD/VB/22012034961761 — Gabian structure Ratiram ke gahr ke Pass | Approved | 0 | 0 | 2026-07-21
MANDLA / MANDLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1735004034/WH/22012034921696 — Stop dem renovation khermai ke pass | Ongoing | 93183.68 | 3753.9 | 2022-03-30
MANDLA / MANDLA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1735004034/WH/22012034921699 — Stop dem kindri nala ke pass | Ongoing | 98914 | 0 | 2022-04-11
MANDLA / MANDLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1735004034/WH/22012034921704 — Stop dem karodi ghat ke pass | Ongoing | 96927.43 | 1610 | 2022-03-30
MANDLA / MANDLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1735004034/WH/22012034921707 — Stop dem panda ghat ke pass | Ongoing | 94860.12 | 0 | 2022-03-30