## Work List
Exported on: 2026-10-06 00:54:52
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JHIRIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDLA / NAINPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Farm Forestry -Comm / Agro Forestry Block Plantation in Waste Lands for Community | Plantation | 1735006011/DP/22012034568160 — CLF GP JHRIYA SE MALDHA ROAD SIDE PLANTION | Ongoing | 282000 | 0 | 2022-09-21
MANDLA / NAINPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1735006011/DP/22012034620967 — झिरिया - पौधरोपण कार्य प्रमारी स्कूल और हाई स्कूल के ग्राऊंड के आस पास | Ongoing | 177891.65 | 0 | 2024-07-12
MANDLA / NAINPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1735006011/DP/22012034620968 — झिरिया - पौधरोपण कार्य झिरिया से मलधा रोड साइड | Ongoing | 309689.07 | 0 | 2024-07-13
MANDLA / NAINPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Medicinal Trees for Community | Plantation | 1735006011/DP/22012034620970 — झिरिया - झिरिया के पोषक ग्राम डुंडा मै नाला के आस पास पौधरोपण कार्य | Ongoing | 309689.07 | 0 | 2024-07-18
MANDLA / NAINPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735006011/IF/22012034649066 — Kapildhara Kup Manoj / Sonu | Ongoing | 246126.86 | 0 | 2021-04-17
MANDLA / NAINPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735006011/IF/22012034649067 — Kapil Dhara Kup Rafayl / Bakhla | Ongoing | 246126.86 | 0 | 2021-05-14
MANDLA / NAINPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735006011/IF/22012034944187 — GP JHIRIYA KAPIL DHARA KOOP NIRMIN BRAJNARESH MAGRE / LALLA | Ongoing | 252665.32 | 0 | 2022-04-30
MANDLA / NAINPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Drainage of chaur/waterlogged Land for Indiv / Construction of Drainage Works in Waterlogged Land for Individual | Land Development | 1735006011/IF/22012034964504 — JAA GP JHIRIYAPUSAM /GENDLAL KAPIL DHARA KOOP NIRMAN KARY | Ongoing | 171290.73 | 2508 | 2022-04-30
MANDLA / NAINPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735006011/IF/22012035201515 — JHIRIYA kapildhara koop nirman karya chatar singh /mihilal | New | 0 | 0 | 2024-04-01
MANDLA / NAINPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735006011/IF/22012035270263 — Jhiriya khet talab nirman karya atarlal | New | 0 | 0 | 2024-10-03
MANDLA / NAINPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735006011/IF/22012035270264 — Jhiriya khet talab nirman karya atarlal | New | 0 | 0 | 2024-10-03
MANDLA / NAINPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735006011/IF/22012035270454 — Jhiriya khet talab nirman karya atarlal | New | 0 | 0 | 2024-10-03
MANDLA / NAINPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735006011/IF/22012035282276 — JHIRIYA khet talab nirman karya Ashish / Amarsingh | Approved | 0 | 0 | 2024-10-03
MANDLA / NAINPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735006011/IF/22012035293662 — JHIRIYA KHET TALAB NIRMAN KARYA CHHADAMI / DHANSING | New | 0 | 0 | 2024-11-16
MANDLA / NAINPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735006011/IF/22012035294234 — Jhiriya khet talab nirman karya pyare lal uikey /maniram | Approved | 0 | 0 | 2024-11-16
MANDLA / NAINPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735006011/IF/22012035294235 — JHIRIYA - Stonbund pyare lal / maniram | Approved | 0 | 0 | 2024-11-16
MANDLA / NAINPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735006011/IF/22012035321198 — झिरिया खेततालाब निर्माण कार्य कोहलू / भादू | Approved | 499266.74 | 0 | 2025-04-01
MANDLA / NAINPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735006011/IF/22012035321204 — झिरिया खेततालाब कार्य दसरू / सुखराम | Approved | 499266.74 | 0 | 2025-04-01
MANDLA / NAINPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735006011/IF/22012035555507 — झिरिया कपिलधारा कूप निर्माण कार्य दीपसिंह / भान सिंह | Ongoing | 322434.5 | 0 | 2025-06-12
MANDLA / NAINPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735006011/IF/22012035623558 — एक बगिया मा के नाम सिया बाई उइके/भारत उइके | Ongoing | 174233.32 | 8151 | 2026-03-01
MANDLA / NAINPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735006011/IF/22012035624157 — एक बगिया मां के नाम लोंगवती उइके/अतर लाल | Ongoing | 174233.32 | 4702.5 | 2026-03-01
MANDLA / NAINPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735006011/IF/IAY/4414035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151757202 | Ongoing | 28500 | 3000 | 2024-02-07
MANDLA / NAINPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735006011/IF/IAY/4450568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151983238 | Ongoing | 28500 | 0 | 2024-02-07
MANDLA / NAINPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735006011/IF/IAY/4451160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151984392 | Ongoing | 28500 | 0 | 2024-02-16
MANDLA / NAINPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735006011/IF/IAY/4455761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151769341 | Ongoing | 28500 | 0 | 2024-02-07
MANDLA / NAINPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735006011/IF/IAY/4456029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151769931 | Ongoing | 28500 | 0 | 2024-02-22
MANDLA / NAINPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1735006011/LD/22012034942186 — JHIRIYA - PODHAROPAN KARYA PRIMARY SCL AVAM HIGH SCL GROUND KE AAS PASS | Approved | 0 | 0 | 2024-04-26
MANDLA / NAINPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1735006011/LD/22012034942188 — JHIRIYA - PODHAROPAN KARYA JHIRIYA SE MALDHA ROAD SIDE PLANTATION | New | 0 | 0 | 2024-06-15
MANDLA / NAINPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1735006011/LD/22012034942189 — JHIRIYA - PODHAROPAN KARYA JHIRIYA SE MALDHA ROAD SIDE | Approved | 0 | 0 | 2024-06-15
MANDLA / NAINPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1735006011/LD/22012034942190 — JHIRIYA poshak gram dunda me nala ke aas pass plantation | Approved | 0 | 0 | 2024-06-15
MANDLA / NAINPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1735006011/LD/22012034961649 — JHIRIYA माधामिक शाला के पीछे मैदान समतलीकरण झिरिया | Approved | 0 | 0 | 2026-02-02
MANDLA / NAINPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1735006011/RC/22012034582307 — Jhriya cc road kisan ke ghar se sarjvnik koop tak | Ongoing | 46000 | 0 | 2021-09-08
MANDLA / NAINPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1735006011/WC/22012034970456 — GP JHIRIYA ME BAVADI KE PAS VRAKSHAROPAN NIRMAN KARY | Ongoing | 133850.24 | 0 | 2022-05-18
MANDLA / NAINPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1735006011/WC/22012035280635 — jhiriya sarvjanik koop jamuntola me mantri ke ghar ke pass richarge pit | Approved | 0 | 0 | 2025-04-01
MANDLA / NAINPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1735006011/WC/22012035280754 — jhiriya sarvjanik koop dunda upertola me richarge pit | Approved | 0 | 0 | 2025-04-01
MANDLA / NAINPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1735006011/WC/22012035281322 — jhiriya sarvjanik koop dunda upertola me richarge pit | Approved | 0 | 0 | 2025-04-01
MANDLA / NAINPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1735006011/WC/22012035281387 — jhiriya sarvjanik koop dunda barratola me richarge pit | Approved | 0 | 0 | 2025-04-01
MANDLA / NAINPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1735006011/WC/22012035288245 — झिरिया सार्वजनिक कूप मंत्री के घर के पास रिचार्ज पिट निर्माण कार्य | Approved | 0 | 0 | 2025-04-01