## Work List
Exported on: 2026-09-15 10:58:17
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SAHJAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDLA / GHUGHRI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1735007014/AV/22012034629986 — AANGANWADI BHAWAN NIRMAN PARIYA KSAHJAR | Ongoing | 500000 | 0 | 2023-10-08
MANDLA / GHUGHRI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1735007014/DP/22012034562404 — PLANTATION CONTUR TRENCH KHURSIJHIRYA SAHJAR | Ongoing | 408000 | 0 | 2022-09-01
MANDLA / GHUGHRI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1735007014/DP/22012034620533 — Road side plantation men rod se bulda rod tak sahjar | Ongoing | 453625.26 | 0 | 2024-07-24
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735007014/IF/22012035271422 — KHET TALAB NIRMAN KARY /RATAN SINGH / HAMMI LAL SAHJAR | Approved | 450885.64 | 0 | 2024-10-07
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735007014/IF/22012035299366 — KAPIL DHARA KOOP NIRMAN KARYA PHULLU SINGH / GOKAL SAHJAR | Approved | 0 | 0 | 2024-10-07
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735007014/IF/22012035661935 — Construction of Stone peripheral stone bund / RATAN SINGH / HAMMI LAL SAHJAR | Ongoing | 198596.77 | 0 | 2026-04-05
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735007014/IF/22012035662303 — Construction of Stone peripheral stone bund / JATAN / CHAOUDHRI SAHJAR | Approved | 0 | 0 | 2026-01-26
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735007014/IF/IAY/4836283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151271732 | Approved | 28500 | 0 | 2024-10-03
MANDLA / GHUGHRI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1735007014/RC/22012034388360 — C C rod nirman kary Ashok ke ghar se jheeman ke ghar tak manjhni tola | Ongoing | 717600 | 0 | 2018-06-20
MANDLA / GHUGHRI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007014/WC/22012034940455 — स्टाप डेम निर्माण कार्य - कमको नाला सहजर | Ongoing | 2489871.93 | 0 | 2022-05-14
MANDLA / GHUGHRI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1735007014/WC/22012034940694 — सार्वजनिक कूप निर्माण कार्य - मुकादम टोला सहजर | Ongoing | 423100.2 | 0 | 2024-01-27
MANDLA / GHUGHRI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007014/WC/22012035247942 — BOULDER CHECK DEM NIRMAN KARY KALVA KONHA NALA ME 6 NANG SAHJAR | Approved | 0 | 0 | 2024-10-07
MANDLA / GHUGHRI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007014/WC/22012035247945 — BOULDER CHECK DEM NIRMAN KARY GADAYIN AAMA NALA ME 6 NANG SAHJAR | Approved | 299877.01 | 0 | 2024-10-07
MANDLA / GHUGHRI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007014/WC/22012035247946 — BOULDER CHECK DEM NIRMAN KARY PULIYA NALA ME 6 NANG SAHJAR | Approved | 0 | 0 | 2024-10-07
MANDLA / GHUGHRI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1735007014/WC/22012035302044 — JGSA 2025 DUGWELL RECHARGE PIT SARVJANIK KOOP MUHFAR KOOP SAHJAR | Approved | 25899.46 | 0 | 2025-04-18
MANDLA / GHUGHRI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1735007014/WC/22012035302047 — JGSA 2025 DUGWELL RECHARGE PIT SARVJANIK KOOP VARD NO 18 PIPARIYA KHURD | Approved | 0 | 0 | 2025-04-18
MANDLA / GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735007014/WC/VB/22012035329864 — GAIBIYAN NIRMAN KARY MAHUVA NALA SAHJAR | Ongoing | 154740.88 | 0 | 2026-09-09
MANDLA / GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735007014/WC/VB/22012035329870 — GAIBIYAN NIRMAN KARY BAILAHI NALA SAHJAR | Ongoing | 155503.63 | 0 | 2026-09-09
MANDLA / GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735007014/WC/VB/22012035329873 — GAIBIYAN NIRMAN KARY BHALVA NALA SAGONA PED KE PAS SAHJAR | Ongoing | 156864.1 | 0 | 2026-09-02
MANDLA / GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735007014/WC/VB/22012035329876 — GAIBIYAN NIRMAN KARY NEEM NALA SAHJAR | Ongoing | 157776.25 | 0 | 2026-09-02
MANDLA / GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735007014/WC/VB/22012035329880 — GAIBIYAN NIRMAN KARY BER NALA SAHJAR | Approved | 0 | 0 | 2026-07-25
MANDLA / GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735007014/WC/VB/22012035330776 — GAIBIYAN NIRMAN KARY JAMUN NALA SAHJAR | Approved | 158157.62 | 0 | 2026-07-25
MANDLA / GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735007014/WC/VB/22012035330778 — GAIBIYAN NIRMAN KARY SAGOUNA NALA 02 SAHJAR | Approved | 0 | 0 | 2026-07-25
MANDLA / GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735007014/WC/VB/22012035330779 — GAIBIYAN NIRMAN KARY CHHIVLA NALA 02 SAHJAR | Approved | 0 | 0 | 2026-07-25
MANDLA / GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735007014/WC/VB/22012035330784 — GAIBIYAN NIRMAN KARY SAJA NALA 02SAHJAR | Approved | 0 | 0 | 2026-07-25
MANDLA / GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735007014/WC/VB/22012035330794 — GAIBIYAN NIRMAN KARY HARDU NALA 02 SAHJAR | Approved | 0 | 0 | 2026-07-25
MANDLA / GHUGHRI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1735007014/WH/22012034940997 — CHECKDAM MARMMAT KARY BELAPAT NALA SAHJAR | New | 0 | 0 | 2024-06-13